## CGS ESTIMATE INITIAL
Assuming : | Level 1 Project
No User Interaction
Estimated Course Length: | 1 | hours
Estimated Development Time: | 50 | hours
| Percentage of Time | Time (hours)
Front End Analysis: | 9% | 4.5
Instructional Design: | 13% | 6.5
Storyboarding: | 11% | 5.5
Graphic Production: | 12% | 6
Video Production: | 6% | 3
Audio Production: | 6% | 3
Authoring/Programming: | 20% | 10
QA Testing: | 6% | 3
Project Management: | 6% | 3
SME/Stakeholder Reviews: | 6% | 3
Pilot Test: | 4% | 2
Other: | 1% | 0.5
Total | 100% | 50

## CGS ESTIMATE 2
Assuming : | Level 1 Project
No User Interaction
Estimated Course Length: | 1 | hours
Estimated Development Time: | 79 | hours
| Percentage of Time | Time (hours)
Front End Analysis: | 9% | 7.11
Instructional Design: | 13% | 10.27
Storyboarding: | 11% | 8.69
Graphic Production: | 12% | 9.48
Video Production: | 6% | 4.74
Audio Production: | 6% | 4.74
Authoring/Programming: | 20% | 15.8
QA Testing: | 6% | 4.74
Project Management: | 6% | 4.74
SME/Stakeholder Reviews: | 6% | 4.74
Pilot Test: | 4% | 3.16
Other: | 1% | 0.79
Total | 100% | 79

## CGS ESTIMATE 3
Assuming : | Level 1 Project
No User Interaction
Estimated Course Length: | 1 | hours
Estimated Development Time: | 78-97 | hours
| Percentage of Time | Time (hours)
Front End Analysis: |  | 5 | - | 8
Instructional Design: |  | 10 | - | 12
Storyboarding: |  | 3 | - | 5
Graphic Production: |  | 10 | - | 10
Animation Production: |  | 5 | - | 6
Audio Production: |  | 5 | - | 6
Authoring/Programming: |  | 17 | - | 25
QA Testing: |  | 4 | - | 6
Project Management: |  | 5 | - | 6
SME/Stakeholder Reviews: |  | 5 | - | 6
Pilot Test: |  | 4 | - | 5
Other: |  | 5 | - | 5
Total |  | 78 | - | 100

## Chapman Alliance
http://www.chapmanalliance.com/howlong/
Executive Summary:
Research Participants: 249 companies organizations, representing 3,947 learning development professionals, who have created content consumed by 19,875,946 learners.
All results are shown as ratios, showing number of hours of development to create 1 finished hour of learning (output)
Instructor-Led Training - including front end analysis, design, lesson plans, handouts, workbooks, PowerPoint, SME reviews of content to be used during live, face-to-face learning events.
22:1 - ILT training, Simple learning content, possible repurposing of learning source material, with minimal learning support materials
43:1 - ILT training, average project for creating corporate ILT class with well documented deliverables (Lesson Plan, Handouts, Workbooks, PowerPoint Visuals)
82:1 - ILT training, Complex subject matter, very custom, extended time spent on formatting classroom deliverables
Level 1 eLearning (Basic) - Including content pages, text, graphics, perhaps simple audio, perhaps simple video, test questions. NOTE: PowerPoint-to-eLearning often falls into this category. Basically pages with assessment
49:1 - eLearning output, Rapid Development, Simple Content, Specialized Authoring Tools (i.e. PowerPoint to eLearning tools)
79:1 - eLearning output, Most typical (average) Level 1 eLearning Content
125:1 - eLearning output, Complex projects, difficult to produce, more media production
Level 2 eLearning (Interactive) - Level 1 eLearning content plus 25% (or more) interactive exercises, allowing learners to perform virtual "try it" exercises, liberal use of multimedia (audio, video, and animations)
127:1 - eLearning output, Rapid development through templated interactions, simple animation, efficient or low-end media production
184:1 - eLearning output, Most typical (average) Level 2 projects
267:1 - eLearning output, advanced and custom interactions, embedded simulation activities and lots of media
Level 3 eLearning (Advanced) - Highly interactive, possibly simulation or serious game-based, use of avatars, custom interactions, award-winning caliber courseware
217:1 - eLearning output, templated interactions, templated games and simulations, efficient simulation development practices (rapid development)
490:1 - eLearning output, Most typical (average) Level 3 projects
716:1 - eLearning output, complex projects, advanced learning simulations and games, extensive media production NOTE: Several respondents listed times greater than 2000+ hours of development per finished hour (very advanced learning simulations and games)

## ATD
https://www.td.org/Publications/Newsletters/Learning-Circuits/Learning-Circuits-Archives/2009/08/Time-to-Develop-One-Hour-of-Training
Type of Training per 1 hour | Low Hours | High Hours | Low Hours | High Hours
| Per hour of Instruction | Per Hour of Instruction | Per hour of Instruction | Per Hour of Instruction
| -2009 | -2009 | -2003 | -2003
Stand-up training (classroom) | 43 | 185 | 20 | 70
Self-instructional print | 40 | 93 | 80 | 125
Instructor-led, Web-based training delivery (using software such as Centra, Adobe Connect, or WebEx-two-way live audio with PowerPoint) | 49 | 89 | 30 | 80
E-learning Developed without a Template
Text-only; limited interactivity; no animations | 93 | 152 | 100 | 150
Moderate interactivity; limited animations | 122 | 186 | 250 | 400
High interactivity; multiple animations | 154 | 243 | 400 | 600
E-learning Developed within a Template
Limited interactivity; no animations (using software such as Lectora, Captivate, ToolBook, TrainerSoft) | 118 | 365 | 40 | 100
Moderate interactivity; limited animations (using software such as Lectora, Captivate, ToolBook, TrainerSoft) | 90 | 240 | 150 | 200
High interactivity; multiple animations (using software such as Lectora, Captivate, ToolBook, TrainerSoft) | 136 | 324 | 60 | 300
Limited interactivity; no animations (using software such as Articulate) | 73 | 116 | NA | NA
Moderate interactivity; limited animations (using software such as Articulate) | 97 | 154 | NA | NA
High interactivity; multiple animations (using software such as Articulate) | 132 | 214 | NA | NA
Simulations
Equipment or hardware (equipment emulation) | 949 | 1743 | 600 | 1000
Softskills (sales, leadership, ethics, diversity, etc.) | 320 | 731 | NA | NA

## Chapman
https://christytucker.wordpress.com/2014/03/18/time-estimates-for-e-learning-development/
Chapman’s study provides this breakdown of tasks and the percentage of time for each (see slide 18).
Front End Analysis: 9%
Instructional Design: 13%
Storyboarding: 11%
Graphic Production: 12%
Video Production: 6%
Audio Production: 6%
Authoring/Programming: 18%
QA Testing: 6%
Project Management: 6%
SME/Stakeholder Reviews: 6%
Pilot Test: 4%
Other: 1%

## Captivate
http://iconlogic.blogs.com/weblog/2013/03/adobe-captivate-techsmith-camtasia-studio-articulate-storyline-production-times.html
Captivate: | 2hours labor/1 minute eLearning
Camtasia: | 1.5hours labor/1 minute eLearning
Storyline: | 2hours labor/1 minute eLearning
Writing an eLearning script. I've found that it could take between 40-80 hours to write a script for 60-minutes of eLearning content.
Rehearsing the script. Once you're written the script, you'll likely need to run through it multiple times to ensure it's accurate.
Writing an Audio Script. If you're going to include voiceover audio (and I highly suggest that you do since audio has been shown to improve the learner experience), you should create an audio script. It could easily take you 40 hours or more to prepare an audio script.
Recording. Once you've written a script, recording screen actions in any of the eLearning tools is simple and shouldn't take more than the actions detailed in the script. For instance, if the script has you recording a 3-minute process in Microsoft Word, it should only take 3-minutes to record the process.
Developing Assets Externally. I mention below that you can save production time in your eLearning tool by creating as much of the course assets as possible outside of the eLearning tool. Many people create the content in PowerPoint and simply import the content into the eLearning tool. While that means there will be less content to create in the eLearning tool, don't overlook the fact that the content still needs to be created in that other tool. In my experience, creating content in PowerPoint is easy. However, it still takes time. In fact, I'd put the development time in PowerPoint at about the same development time as working within Camtasia (1.5 hours for every minute or presentation play time).