## Slide 1: NAME OF COURSE
While we wait for everyone to join, think about the scenario below:
Think of a recent situation where you felt anxious, frustrated, disappointed, or any other unpleasant emotion.
How did you address it?
(Do not share your answers!)
Our session will begin shortly
BECAME ANGRY
BECAME STRESSED OUT
FOCUSED ON SOMETHING ELSE
REDIRECED THOUGHTS / ACTIONS
FELT OR GOT SICK
IGNORED IT
ISD to Update
Notes: SLIDE TIME: 15 minutes BEFORE START OF SESSION
Facilitator Note
Repeat SAY1 several times, as needed as participants join the session. This will talking as soon as they arrive.
Say1
Welcome! Thank you for joining the session [participant name], where are you joining us from today?
Facilitator Note
Wait for a response and then say thank you for sharing and then go to the next person.
This session will start in approximately __________-minutes.
Phone lines are, and will remain, open. However, if you anticipate background noise, please mute your phone or computer line or it will be muted for you.
Transition:
SAY
It looks like just about all participants are on, we will wait about a minute more before we begin.

## Slide 2: Name of course
Slide and Script complete. Do not alter.
Update Image
Notes: Slide Time: 2:00
FACILITATOR PRE-COURSE PREP: Create a 30-second brief about your background experience , degrees, years facilitating, etc.
SAY/EXPLAIN
Hello and welcome to Leadership and Influence Strategies. Thank you for joining our session today. My name is [_____], I live in [city/state/providence] and work with 327 Solutions. For the last two decades, 327 Solutions provides and supports a national client base, creating and delivering customized courses globally, for Thomson Reuters, as well as other organizations such as the US Department of Defense and countless university graduate programs, just to name a few.
A little about me, (insert your 30-second brief about your background experience , degrees, years facilitating, etc.) and I’ll be your facilitator today. I enjoy having an opportunity to see familiar names in these sessions, so if you could introduce yourselves in the chat box, providing your name, title and area of the company, that would be great!
Phone lines are, and will remain open as I expect you to drive the discussion, sharing from your experience and applying the concepts to your everyday environment. If you anticipate any background noise, please be sure to manage the mute function on your phone or computer; if we experience any distracting noises, your line will be muted for you. Please do not, at anytime during this session, place your phone on HOLD, as it broadcasts a repetitive music which disrupts the time we have together. Thank you so much for your understanding.
Transition:
SAY
Now, let’s review general house keeping items, our virtual environment, and what we will cover today.

## Slide 3: Our Virtual Environment
Slide and Script complete. Do not alter.
ASK
xxxxxxxxxxx
USE THE HAND RAISE ICON TO SHARE YOUR RESPONSE.
ASK
xxxxxxx
USE YOUR POINTER TOOL and place it in a ROW THAT BEST PROVIDES YOUR ANSWER.
ASK
xxxxxxx
USE THE CHAT BOX TO PROVIDE YOUR ANSWER.
ASK
xxxxxxxxxxxxxxxxxxx
USE THE GREEN CHECKMARK for you have smart goals OR a RED X for your goals Not yet clearly defined.
Slide Time: x:00
FACILITATOR NOTEs & Tips For Slide
Call on participants and discuss their answers. Start a verbal dialog. Don’t forget to check/repeat some of the responses provided in chat.
Use participant names and thank them for responding and sharing.
SAY
xxxxxxxxxx
ASK:
xxxxxx
FACILITATOR NOTEs: Remember to clear icons before moving on.
Ask if there are any questions before moving on.
Transition: Click next slide.
Listen for possible answers for question
Further discussion: Ask participants if they would like to brainstorm ways to make eating their or possibly someone else's frog easier.
Notes: Slide Time: 6:00
FACILITATOR NOTEs
Demonstrate by using the pointer tool or thin dark line to show each of the tools and features that you will be using during the session. Ask participants to follow along by using their tools during your walk through. Check to see if all participants are doing it. Call out those that are not, to see if they are having difficulties. Preference, “I will do my best to pronounce some of your names and really apologize if I mispronounce it. Please correct me.”
Facilitator Note – WEBEX FILE TRANSFER – WORKSHOP HANDOUT
Mention there is a participant handout that accompanies this session. Provide the “Workshop Handout” file through WebEx file transfer functionality. Suggest to participants to save the workbook to their desktop to be able to reference after the class. Suggest to participants to use the handout as a refresher as they work through challenges they face throughout the day. It has a notes section to jot down new things learned and ideas on how to incorporate the strategies discussed.
SAY
Let’s look at the technology we will be using today. Many of you may have already used these tools, however, for the benefit for everyone, let’s take a quick tour. Also, keep in mind that this is an active class where your participation is key to the level of learning and sharing.
Starting at the upper Left hand corner is the pointer tool, which is arrow pointing to the right.
ASK
Click on the pointer tool and then click on your location of where you are currently taking this webinar.
SAY
In the Right side of your screen is the list of Attendees and below that the tool bar. The first icon is the hand icon.
ASK
Everyone click on the Hand Icon to show me that you located it. This is another way to get my attention if you have a question or comment.
SAY
The two other icons directly to the left of the hand raise icon is a green check mark which can mean you agree or yes; a red x means you disagree or no. Let’s put this one into apply!
Sometimes people like to jot down notes throughout the session, which is totally optional. In a moment, you will see on your screen a File Transfer prompt. I am going to use the WEBEX FILE TRANSFER function to provide you the Workshop Handout. It has keep points we are covering today and also has open areas for those that like to capture notes. You can always have it in the background, which is completely up to you. Click the Download button on the upper left side of the prompt box and save the workshop handout somewhere on your computer for future reference and if you desire to capture notes.
ASK
Give me a green check mark after you have downloaded the workshop handout. That way, I will know you received the file.
Below the tool bar is the chat box. In the Chat Box, Where it says, Send to: keep the default to “All Participants”. During this session feel free to respond to your colleagues and use this as a place to also ask questions. Should you need assistance during the class and want to send a message to me, change the SEND TO option to “Host”.
ASK
Let’s give this a try and type in the chat window a brief introduction that includes your business unit and role at Thomson Reuters. <Note: Call out several participants names and roles.>
Again, if you are having any technical difficulties, use the Chat to let me know. The issue may be a one-off type of thing. If we are finding the technical difficulty is preventing us from continuing the session, I will stop and address it right away. I don’t foresee any challenges, yet I would like us prepared, if it does occur.
The last item in our virtual environment that I want to discuss are the icons on the far right side of the screen. These are visual cues and reminders of tools we will use for particular activities. They will show in the upper right corner. Here we can see what we have the pointer, hand raise, yes/no and chat icons.
FACILITATOR NOTEs: CLEAR ALL PARTICIPANT ICONS BEFORE MOVING ON.
Transition:
ASK
Okay, I would like you to give me a green check mark if you are comfortable with using the technology or the red X if there you have any questions using the tools.
FACILITATOR NOTEs: Remember to clear icons before moving on.

## Slide 4: Setting the Stage
ASK:
Possible POLL: What is your comfort level in [self-awareness]?
Facilitator/Producer Notes: REQUEST #1.
THIS SLIDE: Capture discussion notes of what people are saying/typing for the reason why & expectation they are taking the course.
Email all request from this training session to learn@aim2train.com after course delivery with the following:
EMAIL SUBECT LINE: FEEDBACK – COURSE NAME
IN BODY OF EMAIL:
The Course Name:
Class Date & Time Delivered:
Your Name (Facilitator):
Request #: The discussion answers to the question(s):
Request #: The discussion answers to the question(s):
Request #: The discussion answers to the question(s):
Why is leadership and influence interesting or important for you?
What are your learning expectations for the course today?
ISD to Update
Notes: Slide Time: 2:00
FACILITATOR NOTEs & Tips For Slide
Call on participants and discuss their answers. Start a verbal dialog. Don’t forget to check/repeat some of the responses provided in chat.
Use engagement open-ended questions to gain more details to an answer or statement.
Use participant names and thank them for responding and sharing.
FACILITATOR/PRODUCER NOTES: REQUEST #1: Capture discussion notes of what people are saying/typing for the reason why & expectation they are taking the course.
SAY
I would like to start by asking you a few questions!
ASK
Why is leadership and influence interesting or important for you?
What are your learning expectations for the course today?
Raise your hand and I will call on your name to share your answers. <offer and/or for large classes> If you feel more comfortable using the Chat box, type your answers to the following two questions.
USE THE HAND RAISE ICON TO SHARE YOUR RESPONSE.
FACILITATOR NOTEs: Remember to clear icons before moving on.
Transition:
SAY
Thank you for sharing! Your answers are a wonderful segway into what we plan to cover in this class.

## Slide 5: Session Objectives
Performing in a remote workforce
High performance team characteristics
Understand the importance of communication
Managing for high performance
Effective team meeting techniques
ISD to Update
Notes: Slide Time: 1:00
SAY
Working in a remote team is already be a reality for many of you. However this workshop will focus on success factors for how to work effectively in a remote and virtual environment. Take note, that working remotely is not for everyone and not everyone works well within a remote environment. Today, we will discuss tools and proven strategies to increase your success in performing in a remote environment.
Research has consistently demonstrated that when clear goals are presented, learning occurs more easily and rapidly, so let’s review our objectives for today.
At the end of this workshop, you should be able to:
Define Remote Teams and Discuss the Benefits and Challenges of Working Remotely
Understand the elements of successful team dynamics
Describe characteristics that drive high performance in a Remote Environment
Recognize how and when to transform challenges into success factors for preforming effectively in a Remote Environment
Transition: Click next slide.

## Slide 6: Section 1
xxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxx
xxxxxxxxxxxx
Notes: Slide Time: .30 seconds
SAY
As long as there have been leaders, there have been those who tried to determine how and why they were successful. Leadership itself has not evolved, but our understanding of it has. It is important to understand why very different leadership styles can be effective, why the same leadership techniques will not work in every situation, and which leadership style fits your personality best. Everyone has leadership potential within them, but understanding these concepts will help you maximize your leadership ability.
Transition: Click next slide.

## Slide 7: Hello and welcome to the Accelerated Instructional Media Webinar – Course Name.
BECAME ANGRY
BECAME STRESSED OUT
FOCUSED ON SOMETHING ELSE
REDIRECED THOUGHTS / ACTIONS
FELT OR GOT SICK
IGNORED IT
ISD to Update
While we wait for everyone to join, think about the scenario below:
Think of a recent situation where you felt anxious, frustrated, disappointed, or any other unpleasant emotion.
How did you address it?
(Do not share your answers!)
Welcome! Our Session Will Begin Shortly
Notes: SLIDE TIME: 15 minutes BEFORE START OF SESSION
Facilitator Note
Repeat SAY1 several times, as needed as participants join the session. This will talking as soon as they arrive.
Say1
Welcome! Thank you for joining the session [participant name], where are you joining us from today?
Facilitator Note
Wait for a response and then say thank you for sharing and then go to the next person.
This session will start in approximately __________-minutes.
Phone lines are, and will remain, open. However, if you anticipate background noise, please mute your phone or computer line or it will be muted for you.
Transition:
SAY
It looks like just about all participants are on, we will wait about a minute more before we begin.

## Slide 8
AIM INC Color Specifications
Slide and Script complete. Do not alter.
Notes: Slide Time: 2:00
FACILITATOR PRE-COURSE PREP: Create a 30-second brief about your background experience , degrees, years facilitating, etc.
SAY/EXPLAIN
Hello and welcome to (COURSE NAME). Thank you for joining our session today. My name is [_____], I live in [city/state/providence] and work with 327 Solutions. For the last two decades, 327 Solutions provides and supports a national client base, creating and delivering customized courses globally, for Thomson Reuters, as well as other organizations such as the US Department of Defense and countless university graduate programs, just to name a few.
A little about me, (insert your 30-second brief about your background experience , degrees, years facilitating, etc.) and I’ll be your facilitator today. I enjoy having an opportunity to see familiar names in these sessions, so if you could introduce yourselves in the chat box, providing your name, title and area of the company, that would be great!
Phone lines are, and will remain open as I expect you to drive the discussion, sharing from your experience and applying the concepts to your everyday environment. If you anticipate any background noise, please be sure to manage the mute function on your phone or computer; if we experience any distracting noises, your line will be muted for you. Please do not, at anytime during this session, place your phone on HOLD, as it broadcasts a repetitive music which disrupts the time we have together. Thank you so much for your understanding.
Transition:
SAY
Now, let’s review general house keeping items, our virtual environment, and what we will cover today.

## Slide 9: Session Objectives
Today’s Path
ISD to Update
Discuss the Benefits and Challenges of Working Remotely
Understand the elements of successful team dynamics
Describe characteristics that drive high performance in a Remote Environment
Recognize how and when to transform challenges into success factors
Notes: Slide Time: 1:00
SAY
Working in a remote team is already be a reality for many of you. However this workshop will focus on success factors for how to work effectively in a remote and virtual environment. Take note, that working remotely is not for everyone and not everyone works well within a remote environment. Today, we will discuss tools and proven strategies to increase your success in performing in a remote environment.
Research has consistently demonstrated that when clear goals are presented, learning occurs more easily and rapidly, so let’s review our objectives for today.
At the end of this workshop, you should be able to:
Define Remote Teams and Discuss the Benefits and Challenges of Working Remotely
Understand the elements of successful team dynamics
Describe characteristics that drive high performance in a Remote Environment
Recognize how and when to transform challenges into success factors for preforming effectively in a Remote Environment
Transition: Click next slide.

## Slide 12
AIM INC Color Specifications
Slide and Script complete. Do not alter.
Project Management
Notes: Slide Time: 2:00
FACILITATOR PRE-COURSE PREP: Create a 30-second brief about your background experience , degrees, years facilitating, etc.
SAY/EXPLAIN
Hello and welcome to (COURSE NAME). Thank you for joining our session today. My name is [_____], I live in [city/state/providence] and work with 327 Solutions. For the last two decades, 327 Solutions provides and supports a national client base, creating and delivering customized courses globally, for Thomson Reuters, as well as other organizations such as the US Department of Defense and countless university graduate programs, just to name a few.
A little about me, (insert your 30-second brief about your background experience , degrees, years facilitating, etc.) and I’ll be your facilitator today. I enjoy having an opportunity to see familiar names in these sessions, so if you could introduce yourselves in the chat box, providing your name, title and area of the company, that would be great!
Phone lines are, and will remain open as I expect you to drive the discussion, sharing from your experience and applying the concepts to your everyday environment. If you anticipate any background noise, please be sure to manage the mute function on your phone or computer; if we experience any distracting noises, your line will be muted for you. Please do not, at anytime during this session, place your phone on HOLD, as it broadcasts a repetitive music which disrupts the time we have together. Thank you so much for your understanding.
Transition:
SAY
Now, let’s review general house keeping items, our virtual environment, and what we will cover today.

## Slide 13: Module One: Getting Started
It must be considered that there is nothing more difficult to carry out nor more doubtful of success nor more dangerous to handle than to initiate a new order of things.
Machiavelli
In the past few decades, organizations have discovered something incredible: principles that have been used to create enormous successes in large projects can be applied to projects of any size to create amazing success. As a result, many employees are expected to understand project management techniques and how to apply them to projects of any size.
Notes: It must be considered that there is nothing more difficult to carry out nor more doubtful of success nor more dangerous to handle than to initiate a new order of things.
Machiavelli
Welcome to the Project Management workshop. In the past few decades, organizations have discovered something incredible: principles that have been used to create enormous successes in large projects can be applied to projects of any size to create amazing success. As a result, many employees are expected to understand project management techniques and how to apply them to projects of any size. This workshop will give participants an overview of the entire project management process, as well as key project management tools that they can use every day.

## Slide 14: Workshop Objectives
Define projects
Project needs assessment
Project schedule
Planning tools
Notes: Research has consistently demonstrated that when clear goals are associated with learning that the learning occurs more easily and rapidly. With that in mind, let’s review our goals for today.
By the end of this workshop, participants will be able to:
Define projects, project management, and project managers
Identify the importance of the PMBOK and PMI
Identify the five process groups and ten knowledge areas as defined by the PMI
Describe the triple constraint
Perform a project needs assessment and write goals, requirements, and deliverables
Create key project documents, including the statement of work, project planning worksheet, and project charter
Build a project schedule by estimating time, costs, and resources
Understand and use the work breakdown structure
Create project planning documents, such as a schedule, risk management plan, and communication plan
Use planning tools, including the Gantt chart, network diagram, and RACI chart
Establish and use baselines
Monitor and maintain the project
Perform basic management tasks, including leading status meetings and ensuring all documents are complete at the end of the project

## Slide 15: Module Two: Key Concepts (I)
Do not repeat the tactics which have gained you one victory, but let your methods be regulated by the infinite variety of circumstances.
Sun Tzu
Before we get started, let’s make sure we all understand just what we mean by a project and by project management. We’ll also look at what a project manager’s role is.
Notes: Do not repeat the tactics which have gained you one victory, but let your methods be regulated by the infinite variety of circumstances.
Sun Tzu
Before we get started, let’s make sure we all understand just what we mean by a project and by project management. We’ll also look at what a project manager’s role is.

## Slide 16: What is a Project?
Limited endeavor
Start and end date
Clear goals
Defined responsibility
Notes: A project is a limited endeavor (meaning it has specific start and finish dates) that is undertaken to meet particular goals and objectives. Projects are different than processes or everyday operations, which are repetitive, permanent, or semi-permanent functional work taken on to produce products or services.
All successful projects share the following characteristics:
Clear goals
Defined ownership/responsibility
Timeline
Dedicated team
Defined methodology
Controlled execution
Completion evaluated based on original plan
Linked to business objectives
Supported by an organization’s management team
-------------------------------------
Estimated Time
10 minutes
Topic Objective
To understand what is meant by the term “project.”
Topic Summary
A project is a limited endeavor (meaning it has specific start and finish dates) that is undertaken to meet particular goals and objectives.
Materials Required
List of projects
Planning Checklist
Before the workshop, write the following list on the flip chart.
Daily invoice processing
Planning for annual picnic
Construction of a new home
Widget manufacturing
Widget manufacturing process review
Installation of a new computer system
Recommended Activity
Review the list with the class and determine which items could be classified as a project. Here are our answers.
Daily invoice processing: No
Planning for annual picnic: Yes
Construction of a new home: Yes
Widget manufacturing: No
Widget manufacturing process review: Yes
Installation of a new computer system: Yes
Delivery Tips
This activity can be performed in small or large groups.
Review Questions
What is one characteristic of a successful project?

## Slide 17: What is a Project Management?
Planning and organizing
Managing resources
Within budget
Notes: Project management is the combined art and science of planning, organizing, and managing resources to get a particular project done on time, within budget, and with the results that the organization set out to achieve.
There are many types of project management designed for different scenarios and different industries. This workshop will focus on the traditional method, used by the Project Management Institute, which follows five process groups. (See Module Three for more information.)
-------------------------------------
Estimated Time
10 minutes
Topic Objective
To understand what is meant by “project management.”
Topic Summary
Project management is the combined art and science of planning, organizing, and managing resources to get a particular project done on time, within budget, and with the results that the organization set out to achieve.
Recommended Activity
Have group members share uses of project management in their organization.
Stories to Share
The Apollo program conducted by NASA in the 1960’s is considered the dawn of project management.
Delivery Tips
This activity can be performed in small or large groups.
Review Questions
Which project management approach will this workshop use?

## Slide 18: What is Project Manager?
Responsible and accountable
Setting objectives
Balance wants and needs
Notes: A project manager is the person responsible and accountable for accomplishing the stated project objectives. Key project management responsibilities include creating clear and attainable project objectives, building the project requirements, and managing the triple constraint for projects.
The project manager is often required to perform a juggling act, balancing what the customer wants, and needs with what the team can provide in a particular time frame and with a particular budget. A successful project manager has a hodgepodge of skills and continues learning.
Key skills include:
Leadership
Negotiation
Influence and persuasion
Project management
Communication
Time management
Stress and anger management
Although you do need project management skills to be a project manager, you don’t need to be a project manager to use project management skills. You will find uses for most of the tools that we discuss today in your day-to-day life, both personal and professional.
-------------------------------------
Estimated Time
10 minutes
Topic Objective
To understand what the role of project manager encompasses.
Topic Summary
A project manager is the person responsible and accountable for accomplishing the stated project objectives.
Materials Required
Action plans
Planning Checklist
Print out one action plan per participant.
Recommended Activity
Have participants review the project management skill areas listed in the Student Training Guide and on the next page. Then, ask participants to choose three skill areas that they would like to work on and list them in their action plan.
If participants think of skill areas that are not listed, encourage them to share the area with the class.
Delivery Tips
If you handed out the action plans at the beginning of the workshop, this activity should go smoothly.
Review Questions
Do you need to be a project manager to use project management skills?

## Slide 19: Module Two: Review Questions
What is the definition of a project?
A planned series of future events, items, or performances.
A meeting of people face to face, especially for consultation.
A limited endeavor that is undertaken to meet particular goals and objectives.
An assembly of people, especially the members of a society or committee, for discussion or entertainment.
What is an example of a characteristic of a successful project?
Defined ownership and responsibility
Vague goals
A timeline that changes frequently
Methodology that is “plan-as-you-go”

## Slide 20: Module Two: Review Questions
What is not an example of a characteristic of a successful project?
Ambiguous communication
Dedicated team
Completion evaluated based on original plan
Supported by an organization’s management team
What can be defined as “the combined art and science of planning, organizing, and managing resources to get a particular project done on time, within budget, and with the results that the organization set out to achieve”?
Meeting planning
Project planning
Office management
Project management

## Slide 21: Module Two: Review Questions
Which of these statements is true of project management?
Project management involves repetitive, permanent, or semi-permanent functional activities to produce products or services.
Project management is just like meeting management, involving a chairperson, minute taker, and attendee participation.
There are many types of project management designed for different scenarios and different industries.
There is only one trusted method for project management, and that method is the traditional method.
What is the definition of a project manager?
The profession involving office supervisory positions.
The person responsible and accountable for accomplishing the stated project objectives.
The person ultimately responsible for the day-to-day operations or an organization.
The person who presides over a meeting, committee, or board.

## Slide 22: Module Two: Review Questions
What is not an example of a key project management responsibility?
Organizing the office before the project begins
Deconstructing the project requirements
Managing the triple constraint for projects
All of the above
What job is the project manager often required to do?
Balancing what the customer wants, and needs with what the team can provide in a particular time frame and with a particular budget.
Focusing on consistent and permanent projects that the company needs on a rolling basis.
Giving a brief explanation of the purpose of the meeting and an idea of what you are looking for in terms of topics.
Maintains focus while writing down information during the project’s many meetings.

## Slide 23: Module Two: Review Questions
Which of these is not a key skill of a project manager?
Excellent at taking orders from the team
Negotiation
Leadership
Stress and anger management
Which of these statement is true of project management?
A successful project manager has a basic skill set and is focused on application of these skills, not on learning new ones.
A project manager is the person who delegates responsibility for accomplishing the stated project objectives.
There is only one type of project management, designed for specific scenarios and specific industries.
One can find uses for most of the project management tools that are discussed in day-to-day life, both personal and professional.

## Slide 24: Module Two: Review Questions
What is the definition of a project?
A planned series of future events, items, or performances.
A meeting of people face to face, especially for consultation.
A limited endeavor that is undertaken to meet particular goals and objectives.
An assembly of people, especially the members of a society or committee, for discussion or entertainment.
What is an example of a characteristic of a successful project?
Defined ownership and responsibility
Vague goals
A timeline that changes frequently
Methodology that is “plan-as-you-go”

## Slide 25: Module Two: Review Questions
What is not an example of a characteristic of a successful project?
Ambiguous communication
Dedicated team
Completion evaluated based on original plan
Supported by an organization’s management team
What can be defined as “the combined art and science of planning, organizing, and managing resources to get a particular project done on time, within budget, and with the results that the organization set out to achieve”?
Meeting planning
Project planning
Office management
Project management

## Slide 26: Module Two: Review Questions
Which of these statements is true of project management?
Project management involves repetitive, permanent, or semi-permanent functional activities to produce products or services.
Project management is just like meeting management, involving a chairperson, minute taker, and attendee participation.
There are many types of project management designed for different scenarios and different industries.
There is only one trusted method for project management, and that method is the traditional method.
What is the definition of a project manager?
The profession involving office supervisory positions.
The person responsible and accountable for accomplishing the stated project objectives.
The person ultimately responsible for the day-to-day operations or an organization.
The person who presides over a meeting, committee, or board.

## Slide 27: Module Two: Review Questions
What is not an example of a key project management responsibility?
Organizing the office before the project begins
Deconstructing the project requirements
Managing the triple constraint for projects
All of the above
What job is the project manager often required to do?
Balancing what the customer wants, and needs with what the team can provide in a particular time frame and with a particular budget.
Focusing on consistent and permanent projects that the company needs on a rolling basis.
Giving a brief explanation of the purpose of the meeting and an idea of what you are looking for in terms of topics.
Maintains focus while writing down information during the project’s many meetings.

## Slide 28: Module Two: Review Questions
Which of these is not a key skill of a project manager?
Excellent at taking orders from the team
Negotiation
Leadership
Stress and anger management
Which of these statement is true of project management?
A successful project manager has a basic skill set and is focused on application of these skills, not on learning new ones.
A project manager is the person who delegates responsibility for accomplishing the stated project objectives.
There is only one type of project management, designed for specific scenarios and specific industries.
One can find uses for most of the project management tools that are discussed in day-to-day life, both personal and professional.

## Slide 29: Module Three: Key Concepts (II)
Life is a do-it-yourself project.
Napoleon Hill
This module will look at the Project
Management Institute, a global project
management group that publishes and
promotes project management
standards, and its core ideas.
Notes: Now that we understand what we mean by projects, project management, and project managers, let’s look at some of the other concepts related to projects. This module will look at the Project Management Institute, a global project management group that publishes and promotes project management standards, and its core ideas.

## Slide 30: The Project Management Institute (PMI)
PMBOK
Project management standards
Techniques
Notes: Project Management Institute (PMI)
The Project Management Institute is a global association for the project management profession. Since being founded in 1969, they have been at the forefront of working with businesses to create project management standards and techniques that work.
Their core ideas include:
The Project Management Body of Knowledge( PMBOK), which we will discuss in a moment
Five process groups, which outline the path a project should take
Ten knowledge areas, which outline various parts of each process group
The triple constraint, which illustrates how a project is balanced
-------------------------------------
Estimated Time
10 minutes
Topic Objective
To understand what the Project Management Institute is.
Topic Summary
The Project Management Institute is a global association for the project management profession. It was founded in 1969.
Recommended Activity
Discuss other alternatives to the PMI, including:
Association for Project Management, based in the UK
Australian Institute for Project Management
The European Institute of Advanced Project and Contract Management
Asia Pacific Regional Project Management Forum
Project Management Institute South Africa
Stories to Share
The PMI was founded by five volunteers in 1969. In 2008, it had over 260,000 members in 150 different countries.
Delivery Tips
Encourage participants to share other organizations that they are familiar with.

## Slide 31: The Project Management Body Of Knowledge (PMBOK)
Processes and knowledge
Best practices
Standards
Notes: The Project Management Body of Knowledge (PMBOK) is the PMI bible. It includes a detailed overview of the processes and knowledge areas promoted by the PMI as best practice within the project management discipline.
This global standard allows consistent procedures, methods, and processes to be applied to any project and measured equally, no matter what the actual project is about.
The guide is built around five process groups and ten knowledge areas.
-------------------------------------
Estimated Time
10 minutes
Topic Objective
To understand what the PMBOK is.
Topic Summary
The Project Management Body of Knowledge (PMBOK) is the PMI bible.
Materials Required
Copy of the PMBOK
Planning Checklist
Obtain a copy of the PMBOK before the workshop.
Recommended Activity
Pass around the PMBOK for participants to look at.
Stories to Share
The PMBOK was first drafted in 1986. The first official edition was published in 1994. The latest version of the PMBOK is the 5th Edition.
Delivery Tips
The latest edition of the PMBOK was released in 2008.
Review Questions
What does PMBOK stand for?

## Slide 32: The Five Process Groups
Initiating
Planning
Executing
Monitoring and Controlling
Closing
Notes: These processes form the core structure of any project. Although they are illustrated here as a continuous process, they can overlap and interact throughout a project.
Processes are described in terms of:
Inputs (documents, plans, designs, etc.)
Tools and Techniques (mechanisms applied to inputs)
Outputs (documents, products, etc.)
-------------------------------------
Estimated Time
10 minutes
Topic Objective
To understand the life cycle of a project.
Topic Summary
The five phases are Initiating, Planning, Executing, Monitoring and Controlling, and Closing.
Materials Required
Prepared sheets of flip chart paper
Sticky notes
Tape
Markers
Planning Checklist
Each sheet of flip chart paper should be divided into five columns. Each column should be headed with a process group name.
Recommended Activity
Divide participants into groups of four to six. Ask each group to write these activities on sticky notes (one activity per note):
Setting project goals
Returning supplies
Deciding who will be on the project team
Building a schedule
Having a success party
Building a prototype widget
Adjusting the schedule due to a worker’s strike
Having weekly status meetings
Installing a new computer system
Setting up the project plan on a computer
Now, ask participants to place the notes in their proper column.
Delivery Tips
We have included the answers in Worksheet One in the activities folder.
Review Questions
Name one process group.

## Slide 33: The Ten Knowledge Areas
Integration
Procurement
Scope
Risk
Time
Communications
Cost
Human Resources
Quality and Stakeholder
Notes: The PMBOK guide focuses on ten knowledge areas that are crucial to the project management processes. The areas are:
Integration Management
Procurement Management
Scope Management
Risk Management
Time Management
Communications Management
Cost Management
Human Resources Management
Quality Management
Stakeholder Management
Each knowledge area contains some or all of the project management processes. For example, Project Procurement Management includes:
Plan Procurement Management
Conduct Procurements
Control Procurements
Close Procurements
-------------------------------------
Estimated Time
10 minutes
Topic Objective
To understand the ten knowledge areas of the PMBOK.
Topic Summary
The PMBOK guide focuses on ten knowledge areas that are crucial to the project management processes.
Integration Management
Procurement Management
Scope Management
Risk Management
Time Management
Communications Management
Cost Management
Human Resources Management
Quality Management
Stakeholder Management
Materials Required
Copy of the PMBOK
Planning Checklist
Obtain a copy of the PMBOK before the workshop.
Recommended Activity
Choose a few knowledge areas of interest to participants. Look these areas up in the PMBOK. This will spur participants to think of areas of further interest, and it will give them some practical experience with the PMBOK.
Delivery Tips
If you have a small group or several copies of the PMBOK, let participants look through the PMBOK on their own.
Review Questions
Name one of the knowledge areas.

## Slide 34: The Triple Constraint
Schedule
(Time)
Scope
Quality
Customer Satisfaction
Budget (Cost)
Resources
Risk
Notes: The Triple Constraint illustrates the balance of the project’s scope, schedule (time), and budget (cost). During the planning phase of a project, the project management team defines the project scope, schedule (time), and budget (cost)of a project. As the process continues, the project managers discover that there may be changes or adjustments to be made in one of these areas. When this happens, the other factors of the triple constraint are likely to be affected as well.
For example, if the budget (cost) increases, it is logical to assume that the scope and schedule (time) will increase as well. The same thing happens if the budget (cost) decreases; the scope and schedule (time) will decrease too.
It is the job of the project manager, and sometimes the project team, to identify how a change to a single element will change the other elements.
-------------------------------------
Estimated Time
10 minutes
Topic Objective
To understand the triangle of factors that can affect a project.
Topic Summary
The Triple Constraint illustrates the balance of the project’s scope, schedule (time), and budget (cost).
Materials Required
Flip chart paper
Markers
Planning Checklist
Review the scenarios below before the workshop and come up with some ideas of your own.
Recommended Activity
Discuss the following scenarios with the group. Explore which constraint in each scenario is changing, and how that could affect the other elements.
Budget is reduced by 25%
Building needs to be completed three months earlier
Product must have 99% purity instead of 95%
Need to renovate three office buildings instead of one
Delivery Tips
There are no “right” answers for this activity. The objective is to have participants see how changes can have a ripple effect.
Review Questions
Name one of the triple constraints.

## Slide 35: Module Three: Review Questions
What is the Global Project Institute?
The process of international integration arising from the interchange of world views, products, ideas, and other aspects of culture.
A global association for the project management profession.
The combined art and science of planning, organizing, and managing resources to get a particular project done on time, within budget, and with the results that the organization set out to achieve.
A society or organization having a particular object or common factor, especially a scientific, educational, or social one.
What is included in the Global Project Institute’s core ideas?
The Project Management Body of Management ( PMBOM).
Five process groups, which outline the path a project should take.
Seven knowledge areas, which outline various parts of each process group.
The double constraint, which illustrates how a project is balanced.

## Slide 36: Module Three: Review Questions
Which of these forms the core structure of any project?
The Five Process Groups
The Five Management Groups
The Four Process Groups
The Four Management Groups
Which of these is a term that could describe the processes?
Means
Products
Amounts
Inputs

## Slide 37: Module Three: Review Questions
How many knowledge areas are crucial to the project management processes?
Thirteen
Ten
Nine
Three
What is not a knowledge area the PMBOK focuses on?
Integration
Settlement
Scope
Procurement

## Slide 38: Module Three: Review Questions
Which of these does Project Procurement Management include?
Elements
Predictions
Human Resources
Contract Administration
What illustrates the balance of the project’s scope, schedule (time), quality, and cost?
The triple constraint
The double constraint
Solicitation Planning
Procurement Planning

## Slide 39: Module Three: Review Questions
During the planning phase of a project, who defines the scope, time, cost, and quality?
Human resources
Solicitation team
Planning resources
Project Management Team
What is the job of the project manager?
To take on long term, permanent projects that are managed on an ongoing basis.
To balance day-to-day office management with project planning.
To identify how a change to a single element will change the other elements.
To procure funds for the projects that are being managed.

## Slide 40: Module Three: Review Questions
What is the Global Project Institute?
The process of international integration arising from the interchange of world views, products, ideas, and other aspects of culture.
A global association for the project management profession.
The combined art and science of planning, organizing, and managing resources to get a particular project done on time, within budget, and with the results that the organization set out to achieve.
A society or organization having a particular object or common factor, especially a scientific, educational, or social one.
What is included in the Global Project Institute’s core ideas?
The Project Management Body of Management ( PMBOM).
Five process groups, which outline the path a project should take.
Seven knowledge areas, which outline various parts of each process group.
The double constraint, which illustrates how a project is balanced.

## Slide 41: Module Three: Review Questions
Which of these forms the core structure of any project?
The Five Process Groups
The Five Management Groups
The Four Process Groups
The Four Management Groups
Which of these is a term that could describe the processes?
Means
Products
Amounts
Inputs

## Slide 42: Module Three: Review Questions
How many knowledge areas are crucial to the project management processes?
Thirteen
Ten
Nine
Three
What is not a knowledge area the PMBOK focuses on?
Integration
Settlement
Scope
Procurement

## Slide 43: Module Three: Review Questions
Which of these does Project Procurement Management include?
Elements
Predictions
Human Resources
Contract Administration
What illustrates the balance of the project’s scope, schedule (time), quality, and cost?
The triple constraint
The double constraint
Solicitation Planning
Procurement Planning

## Slide 44: Module Three: Review Questions
During the planning phase of a project, who defines the scope, time, cost, and quality?
Human resources
Solicitation team
Planning resources
Project Management Team
What is the job of the project manager?
To take on long term, permanent projects that are managed on an ongoing basis.
To balance day-to-day office management with project planning.
To identify how a change to a single element will change the other elements.
To procure funds for the projects that are being managed.

## Slide 45: Module Four: Initiation (I)
No sensible decision can be made without taking into account not only the world as it is, but the world as it will be.
Isaac Asimov
The first phase of project management
is initiation.
This module will explore the first part
of that process: identifying what
success will look like for your particular
project.
Notes: The first phase of project management is initiation. This is where the project starts to take shape. Stakeholders and team member’s work together to identify wants and needs, and then the project team creates a plan to accomplish the objectives with the time and budget available. This module will explore the first part of that process: identifying what success will look like for your particular project.

## Slide 46: Identifying Your Stakeholders
Has an interest
Feedback
Guidance
Who might be affected?
Notes: A stakeholder is someone who has an interest in the development and/or outcome in the project. This person is usually only involved at key project gateways, such as project initiation and evaluation. Their main role is to provide feedback and guidance.
When you are identifying stakeholders, think outside the box. Ask other members of the team and the organization, “Who else should we involve in this? Who might be affected?”
If it turns out you missed a stakeholder, ask them for their feedback. You may not be able to change the project’s course at that point, but you may receive valuable information on possible opportunities or potential issues.
-------------------------------------
Estimated Time
5 minutes
Topic Objective
To understand what is meant by the term “stakeholder” in project management.
Topic Summary
A stakeholder is someone who has an interest in the development and/or outcome in the project.
Materials Required
Worksheet Two Case Study
Module Four Questions from Worksheet Two
Planning Checklist
Print out one copy of the Worksheet Two Case Study and the Module Four Questions for each participant.
Recommended Activity
Divide participants into pairs. Ask them to review the case study and identify possible stakeholders.
Stories to Share
The word “stakeholder” dates from the early 1700’s. It originally meant, “a person who holds the stake(s) in a bet.”
Delivery Tips
If there is time, bring the large group back together, and discuss results.
Review Questions
Encourage participants to think of some stakeholders for their project.

## Slide 47: Assessing Needs and Wants
Decide which items are necessary (needs)
“nice to haves” (wants)
Prioritize the needs
Notes: When stakeholders and other project members begin identifying the goals of the project, encourage them to list any and all possibilities. If the sky is the limit, what would they want the project to accomplish?
Then, they should decide which items are necessary for the project’s success (needs), and which are “nice to haves” (wants). If the list is lengthy, wants and needs can be prioritized to help the project team identify the most important tasks. (Remember, this is not a final list, just brainstorming to kick things off.)
To wow your stakeholders, keep this list on hand during the project. Keep an eye out for ways to incorporate wants and maximize their value.
-------------------------------------
Estimated Time
10 minutes
Topic Objectives
To understand the difference between needs and wants.
To understand how to use “wants” to deliver maximum value.
Topic Summary
When stakeholders and other project members begin identifying the goals of the project, encourage them to list any and all possibilities.
Then, they should decide which items are necessary for the project’s success (needs), and which are “nice to haves” (wants).
Materials Required
Worksheet Two Case Study
Module Four Questions from Worksheet Two
Planning Checklist
Print out one copy of the Worksheet Two Case Study and the Module Four Questions for each participant.
Recommended Activity
Divide the class into teams of ten. Then, divide each team into two parts. Ask one half of the team to take on the role of project team members, and the other half to take on the role of stakeholders. (You may want the team members to elect a project manager too.) Then, have the teams work together to identify needs and wants.
Stories to Share
Wants and needs analysis is a useful tool for many applications.
Delivery Tips
If there is time, have each group present a brief list of their wants and needs.
Review Questions
How can you use wants to wow your stakeholders?

## Slide 48: Setting a SMART Project Goal
Specific
Measurable
Agreed Upon
Relevant
Timed
Notes: Each project should have a goal statement. SMART is a convenient acronym for the set of criteria that a goal must have in order for it to be realized by the goal achiever.
Specific: In order for the project team to achieve a goal, stakeholders must be very clear about what they want. As Jack Canfield says, “Vague goals produce vague results.”
Measurable: It’s crucial that you are able to track your progress towards your goal. That’s why all goals need some form of objective measuring system so that you can stay on track and become motivated when you enjoy the sweet taste of quantifiable progress.
Agreed Upon: All team members and stakeholders must agree on the goal.
Relevant: The goal must be relevant to the business’ purpose.
Timed: In order for a project to be considered a project, it must have a specific start and end date.
Some examples of good project goals:
To upgrade the existing sales system to EasySell 5.1 by January 1, 2015.
To begin production of a new widget by September 1, 2016.
To build a new 5,000 square foot office facility and have all staff relocated to it by December 31, 2015.
-------------------------------------
Estimated Time
10 minutes
Topic Objective
To understand how to write a good project goal.
Topic Summary
Project goals should be SMART.
Specific
Measurable
Agreed upon
Relevant
Timed
Materials Required
Worksheet Two Case Study
Module Four questions from Worksheet Two
Planning Checklist
Print out one copy of the Worksheet Two Case Study and the Module Four questions for each participant.
Recommended Activity
Ask participants to pair off and write a SMART goal for the case study.
Stories to Share
SMART goals can be used to help individuals achieve things, too.
Delivery Tips
After a few minutes, bring the group back together and write a SMART goal as a group.
Review Questions
What does SMART stand for?

## Slide 49: Creating Requirements and Deliverables
What a project must do in order for it to be considered successful
Define what people can expect to hold in their hands after the project is complete
Notes: Now that we have some idea of what we want our project to accomplish, we can begin setting requirements. Requirements outline exactly what a project must do in order for it to be considered successful. Remember, good requirements are highly specific. Although they are particularly useful in IT projects, they should be used for any project that you want to succeed.
For example, let’s say one goal for our project is this: “To reduce the time to process inbound orders to 15 minutes by January 1, 2015.” A corresponding project requirement could be, “Implement version 5.0 of Superior Records Processing on all 14 customer service representative stations.”
As part of this, you should then be able to create your deliverables. These define what people can expect to hold in their hands after the project is complete. These deliverables will help you set clear expectations at the beginning of your project, and maintain a clear idea of what you are doing as you execute the project.
-------------------------------------
Estimated Time
10 minutes
Topic Objective
To understand how to frame project requirements and deliverables.
Topic Summary
Requirements outline exactly what a project must do in order for it to be considered successful. Deliverables define what people can expect to hold in their hands after the project is complete.
Materials Required
Worksheet Two Case Study
Module Four questions from Worksheet Two
Planning Checklist
Print out one copy of the Worksheet Two Case Study and the Module Four questions for each participant.
Recommended Activity
Ask participants to pair off and write two requirements and two deliverables for their case study.
Stories to Share
Requirements are most often used in technology-based projects, but can be useful in other areas.
Delivery Tips
Examples of requirements:
Computer application must support graphic reporting
Office building must have air conditioning
Examples of deliverables:
Installation of EzeeReports 2.5 on 400 systems by September20, 2031
Refurbishment of current heating system to provide heat, air conditioning, humidification, and dehumidification, to be complete by January 1, 2015
Review Questions
What is the difference between a requirement and deliverable?

## Slide 50: Module Four: Review Questions
What is the first phase of project management?
Foundation
Prophase
Initiation
Induction
What is the definition of a stakeholder?
The supervisor who must take responsibility for and is accountable for the success or failure of their particular operation.
Someone who has an interest in the development and/or outcome in the project.
Someone who competes against or fights another in a contest, game, or argument; a rival or adversary.
A person who supervises a person or an activity.

## Slide 51: Module Four: Review Questions
If it turns out that you missed a stakeholder, why should you ask them for their feedback?
You may receive valuable information on possible opportunities or potential issues.
You will be able to change the project’s course at that point.
You will be able to initiate other projects in the future with this person.
You will save the company on time and cost.
When stakeholders and other project members begin identifying the goals of the project, what is the first step should you take?
Work on creating your deliverables.
Get all team members and stakeholders to agree on the goals.
Assemble an outside team to list any and all possibilities.
Encourage them to list any and all possibilities.

## Slide 52: Module Four: Review Questions
What does the “M” in the SMART acronym stand for?
Meaningful
Measurable
Money-making
Matter-of-fact
According to Jack Canfield, what do vague goals produce?
Specific goals
Clear planning
Vague results
Vague stakeholders

## Slide 53: Module Four: Review Questions
In order for a project to be considered a project what does it need?
A transitory name and title
Extra funding to prepare for possible emergencies
A specific start and end date
A vague purpose and results
What is not an example of a good project goal?
To upgrade the existing sales system to EasySell 5.1 by January 1, 2010.
To begin production of a new widget by September 1, 2011.
To build a new 5,000 square foot office facility and have all staff relocated to it by December 31, 2010.
To design a new data entry system to a future buyer at a time to be determined.

## Slide 54: Module Four: Review Questions
Which of these statements is true about setting requirements?
Requirements outline exactly what a project must do in order for it to be considered successful.
Good requirements are at least somewhat specific.
They should not be used for just any project, but are particularly useful in IT projects.
When it comes to requirements it is best to be vague in order to not miss important deadlines.
Which of these describes deliverable?
They define what people can expect to hold in their hands after the project is complete.
They define the goals set by the project management team.
They help you set clear expectations at the end of your project.
They maintain a clear idea of what the stakeholders should be executing.

## Slide 55: Module Four: Review Questions
What is the first phase of project management?
Foundation
Prophase
Initiation
Induction
What is the definition of a stakeholder?
The supervisor who must take responsibility for and is accountable for the success or failure of their particular operation.
Someone who has an interest in the development and/or outcome in the project.
Someone who competes against or fights another in a contest, game, or argument; a rival or adversary.
A person who supervises a person or an activity.

## Slide 56: Module Four: Review Questions
If it turns out that you missed a stakeholder, why should you ask them for their feedback?
You may receive valuable information on possible opportunities or potential issues.
You will be able to change the project’s course at that point.
You will be able to initiate other projects in the future with this person.
You will save the company on time and cost.
When stakeholders and other project members begin identifying the goals of the project, what is the first step should you take?
Work on creating your deliverables.
Get all team members and stakeholders to agree on the goals.
Assemble an outside team to list any and all possibilities.
Encourage them to list any and all possibilities.

## Slide 57: Module Four: Review Questions
What does the “M” in the SMART acronym stand for?
Meaningful
Measurable
Money-making
Matter-of-fact
According to Jack Canfield, what do vague goals produce?
Specific goals
Clear planning
Vague results
Vague stakeholders

## Slide 58: Module Four: Review Questions
In order for a project to be considered a project what does it need?
A transitory name and title
Extra funding to prepare for possible emergencies
A specific start and end date
A vague purpose and results
What is not an example of a good project goal?
To upgrade the existing sales system to EasySell 5.1 by January 1, 2010.
To begin production of a new widget by September 1, 2011.
To build a new 5,000 square foot office facility and have all staff relocated to it by December 31, 2010.
To design a new data entry system to a future buyer at a time to be determined.

## Slide 59: Module Four: Review Questions
Which of these statements is true about setting requirements?
Requirements outline exactly what a project must do in order for it to be considered successful.
Good requirements are at least somewhat specific.
They should not be used for just any project, but are particularly useful in IT projects.
When it comes to requirements it is best to be vague in order to not miss important deadlines.
Which of these describes deliverable?
They define what people can expect to hold in their hands after the project is complete.
They define the goals set by the project management team.
They help you set clear expectations at the end of your project.
They maintain a clear idea of what the stakeholders should be executing.

## Slide 60: Module Five: Initiation (II)
All you need is the plan, the road map, and the courage to press on to your destination.
Earl Nightingale
This module will look at four key
project documents: the statement of
work, the project requirements
document, the project planning
worksheet, and the project charter.
Notes: All you need is the plan, the road map, and the courage to press on to your destination.
Earl Nightingale
Once you have an idea of who your stakeholders are and what the project will achieve, it’s time to put it all in writing. This module will look at four key project documents: the statement of work, the project requirements document, the project planning worksheet, and the project charter.

## Slide 61: Creating a Statement of Work
Defines what the project will do
When it will be done
Contract of expectations
Notes: What is the Statement of Work? The SOW defines what the project will do and when it will be done. It forms a binding contract of expectations between all project stakeholders. As such, it should be created by the project team, and then signed off by the team and the stakeholders. It can be used to create other project documents, including the project charter. The Statement of Work often varies widely between organizations. However, the following basic elements should be included.
Project Team: Include all members of the project team and each person’s role, as well as a list of stakeholders and the sponsor.
Project Details: Include the name of the project, its estimated start and end date, and the client(s) involved. (Every project should have a client, whether it is an internal or external customer.)
Purpose: What is the purpose of the project? Try to keep this as simple and concrete as possible. If a business case or a cost-benefit analysis has been prepared, those documents should be referenced (but not included) here.
Scope: What will the project encompass? What items will the project not encompass? This section is extremely important as it will help avoid miscommunication and disappointment down the road.
Goals, Deliverables, and Requirements: Include your SMART goals, deliverables, and requirements here.
Basic Finances: List applicable rate and payment schedule information.
Assumptions: List any assumptions that have been made in the planning thus far.
Agreements: List any agreements that will apply to this project, such as union contracts or professional service agreements.
-------------------------------------
Estimated Time
10 minutes
Topic Objective
To understand what the Statement of Work is.
Topic Summary
The Statement of Work defines what the project will do and when it will be done.
Materials Required
List of SOW elements
Planning Checklist
Have a copy of the SOW elements (listed on the previous page) on flip chart or PowerPoint slides.
Recommended Activity
Discuss what SOW elements participants would customize for their organization.
Stories to Share
The Statement of Work can take many different forms. Encourage participants to do research on standards for their industry.
Delivery Tips
This list is also in the Student Training Guide.
Review Questions
True or False: The SOW must contain the same elements no matter where or how it is used.

## Slide 62: Completing the Project Planning Worksheet
Project Planning Worksheet |  | 
Part I: Basic Information |  | 
Project Name: |  | Project Team Members:
Estimated Project Start Date: |  | 
Estimated Project End Date: |  | 
Budget Amount (if known): |  | 
Part II: Project Goals |  | 
List your SMART goals here. |  | 
Part III: Milestones |  | 
Milestone | Target Completion Date | 
Approved by: |  | 
Notes: Once the basics of the project are laid out, it’s time to put together your project planning worksheet. While the Statement of Work will remain static throughout the project, your worksheet will be a living, breathing document. As such, there are parts that you will not complete until after the Planning phase, but this worksheet will give you one place to capture the essential information about your project.
Like the SOW, you may need different fields based on your project and your organization, but we have included a sample worksheet on the next page.
-------------------------------------
Estimated Time
10 minutes
Topic Objective
To understand what a project planning worksheet looks like.
Topic Summary
This worksheet will give you one place to capture the essential information about your project.
Materials Required
Sample Project Planning Worksheet template
Planning Checklist
Have copies of the Project Planning Worksheet template (shown on the next page) available for participants to review.
Recommended Activity
As a large group, review the Project Planning Worksheet. Encourage participants to identify customizations and changes.
Delivery Tips
This sample is also in the Student Training Guide.
Review Questions
List one piece of information that should be included in the Project Planning Worksheet.
Project Planning Worksheet
Part I: Basic Information
Project Name:
Project Team Members:
Estimated Project Start Date:
Estimated Project End Date:
Budget Amount (if known):
Part II: Project Goals
List your SMART goals here.
Part III: Milestones
Milestone
Target Completion Date
Approved by:

## Slide 63: Completing the Project Charter
Formal project document
Establishes the project as an entity
Customized for your organization
Notes: The project charter is the final, formal project document. It establishes the project as an entity and it gives the project manager the authority to get started. For small projects, the charter may be just a few pages. For large projects, the charter itself can be hundreds of pages and can take months to build.
Just like other project documents, the charter can be customized for your organization. At a minimum, it should include the following information:
Project name
Project due date
Team list, including responsibility matrix
Stakeholders
In scope and out of scope items
Goals
Requirements
Deliverables
Estimated cost vs. budget
Benefits of project (including cost-benefit analysis if appropriate)
Milestone descriptions and dates
Possible risks and opportunities
Communication plans
Assumptions and Constraints
Plans for documenting lessons learned
A page for sign off by the important parties
Ask your organization if they have a charter form that they would like you to use. This is especially important as a charter can be a legally binding document.
-------------------------------------
Estimated Time
10 minutes
Topic Objective
To understand what the project charter is.
Topic Summary
The project charter is the final, formal project document. It establishes the project as an entity and it gives the project manager the authority to get started.
Materials Required
Project charter examples
Planning Checklist
Prior to the workshop, gather examples of completed project charters and/or templates.
Recommended Activity
Review the various examples with the class. Encourage discussion about what elements they would use, and which they would change.
Delivery Tips
Make sure to obtain proper permissions for the materials you gather.
Review Questions
What is the difference between the charter and the SOW?

## Slide 64: Module Five: Review Questions
Once you have an idea of who your stakeholders are and what the project will achieve, what is the next step?
Achieve the deliverables
Assemble your project management team
Put it all in writing
End the project
What is the statement of work?
The SOW is a basis report on three types of financial activities: operating activities, investing activities, and financing activities.
The SOW is a statement which stakeholders create for the project management team.
The SOW defines the vague overall meaning of the work and is also specific enough that it conveys your unique interpretation.
The SOW defines what the project will do and when it will be done.

## Slide 65: Module Five: Review Questions
Who signs off on the statement of work?
The project management team
The stakeholders
Human resources and upper management
Both a & b
Which of these is not included in the project details?
Name of the project
The products needed
Its estimated state and end date
The client(s) involved

## Slide 66: Module Five: Review Questions
What question does ‘scope’ answer in the statement of work?
What will the project encompass?
What are our deliverables, goals, and requirements?
What is the purpose of the project?
Who is on the project management team?
Which of these statements is true of the project planning worksheet?
It remains static throughout the project.
It is a living, breathing document.
It is never complete.
It gives you several places to capture the essential information about your project.

## Slide 67: Module Five: Review Questions
How is the project planning worksheet similar to the statement of work?
They are both produced by the stakeholders.
They both must be signed off on by a number of supervisors.
In both, you may need different fields based on your project.
In both, you may need to be vague for the betterment of the project.
What is the final, formal project document?
The project planning worksheet
The project planning team
The project charter
The statement of work

## Slide 68: Module Five: Review Questions
How long should the project charter be?
It varies from a few pages to hundreds.
It varies from ten to fifteen pages.
It varies from one hundred to five hundred pages.
It is varies, but is never over one hundred pages.
Which of these would not be included in the project charter?
Estimated cost vs. budget
In house and out of house items.
Milestone descriptions and dates.
Communication plans.

## Slide 69: Module Five: Review Questions
Once you have an idea of who your stakeholders are and what the project will achieve, what is the next step?
Achieve the deliverables
Assemble your project management team
Put it all in writing
End the project
What is the statement of work?
The SOW is a basis report on three types of financial activities: operating activities, investing activities, and financing activities.
The SOW is a statement which stakeholders create for the project management team.
The SOW defines the vague overall meaning of the work and is also specific enough that it conveys your unique interpretation.
The SOW defines what the project will do and when it will be done.

## Slide 70: Module Five: Review Questions
Who signs off on the statement of work?
The project management team
The stakeholders
Human resources and upper management
Both a & b
Which of these is not included in the project details?
Name of the project
The products needed
Its estimated state and end date
The client(s) involved

## Slide 71: Module Five: Review Questions
What question does ‘scope’ answer in the statement of work?
What will the project encompass?
What are our deliverables, goals, and requirements?
What is the purpose of the project?
Who is on the project management team?
Which of these statements is true of the project planning worksheet?
It remains static throughout the project.
It is a living, breathing document.
It is never complete.
It gives you several places to capture the essential information about your project.

## Slide 72: Module Five: Review Questions
How is the project planning worksheet similar to the statement of work?
They are both produced by the stakeholders.
They both must be signed off on by a number of supervisors.
In both, you may need different fields based on your project.
In both, you may need to be vague for the betterment of the project.
What is the final, formal project document?
The project planning worksheet
The project planning team
The project charter
The statement of work

## Slide 73: Module Five: Review Questions
How long should the project charter be?
It varies from a few pages to hundreds.
It varies from ten to fifteen pages.
It varies from one hundred to five hundred pages.
It is varies, but is never over one hundred pages.
Which of these would not be included in the project charter?
Estimated cost vs. budget
In house and out of house items.
Milestone descriptions and dates.
Communication plans.

## Slide 74: Module Six: Planning (I)
Those who fail to plan, plan to fail.
Anonymous
Now it’s time to plan the nuts and bolts
of your project.
When building your plan, remember:
Everything in the plan is a prediction.
The only fact that you know for certain is that your plan is definitely not 100% right.
Contingency needs to be built in to cope with the uncertainty.
Notes: Those who fail to plan, plan to fail.
Anonymous
Congratulations! With the completion of the SOW, planning worksheet, and project charter, the initiation phase is complete. Now it’s time to plan the nuts and bolts of your project. When building your plan, remember:
Everything in the plan is a prediction.
The only fact that you know for certain is that your plan is definitely not 100% right.
Contingency needs to be built in to cope with the uncertainty.

## Slide 75: Managing Expectations
Functionality
Effort (Time & Cost)
Delivery Date
Quality
Notes: Each stakeholder and each project team member will have different expectations. As the project manager, you need to manage all of them. Unmanaged expectations will cause conflict and can cause the project to fail.
Expectations fall into four main categories:
Expectations for each area should be addressed in the Statement of Work, Project Planning Worksheet, and Project Charter.
Periodically reviewing these documents is important. Key checkpoints should include:
Does everyone involved have the same understanding of the project?
Clarify responsibilities as assigned
Clarify the outcomes and time frame
Clarify the requirements and budgets
Understand the budget and schedule linkages
Communicate to everyone who is relevant
-------------------------------------
Estimated Time
10 minutes
Topic Objective
To understand the four categories of expectations and how to manage them.
Topic Summary
Expectations fall into four main categories:
Functionality
Effort (time and cost)
Delivery date
Quality
Materials Required
Worksheet Two Case Study
Module Six Questions from Worksheet Two
Planning Checklist
Print out one copy of the Worksheet Two Case Study and the Module Six Questions for each participant.
Recommended Activity
Divide participants into groups of four to six. Ask each group to identify possible expectations from stakeholders and project team members.
Delivery Tips
Teams can be divided into stakeholders and team members if you desire.
Review Questions
What are the four categories of expectations?

## Slide 76: Creating a Task List
Details
Write in the order of tasks
Be aware of micro-managing
Notes: To begin the nuts-and-bolts planning process, you must first make a list of all the tasks that are going to be done. Let’s say you are going to paint a room. Tasks might include:
Get paint samples
Choose a paint color
Remove all furniture
Take off trim
Paint trim
Apply first coat
Apply second coat
Put trim back in
Put all furniture back in
How detailed the task list becomes is up to you. We suggest writing the task list in the way that you will accomplish it. For example, if you are going to apply the first coat of paint yourself; you may want to include all steps, such as crack-filling, sanding, taping, etc. If, however, you are contracting the task out, “Apply first coat” may be the only item you need to monitor. (Your painter probably wouldn’t appreciate being micro-managed!)
-------------------------------------
Estimated Time
10 minutes
Topic Objective
To understand how to identify the work to be done in a project.
Topic Summary
To begin the nuts-and-bolts planning process, you must first make a list of all the tasks that are going to be done.
Materials Required
Flip chart paper
Markers
Worksheet Two Case Study
Planning Checklist
Print out one copy of the Worksheet Two Case Study for each participant.
Recommended Activity
Work with the group to identify a list of tasks for the case study. Tasks can be kept at a high level.
Delivery Tips
This activity can also be performed in small groups.
After the activity is over, write out a final list of tasks on flip chart paper.

## Slide 77: Estimating Time
Tm
  Probable Time
To
  Optimistic Time
Tp
  Pessimistic Time
Te
  Calculated Time (Best Estimate)
To + 4Tm + Tp
6
Te =
Notes: When building your schedule, never guess times. Gather the most reliable information possible and use a scientific formula to get the best estimate. The better your estimates, the more reliable your plan will be.
This formula is considered the standard for estimating time (Te):
To+4Tm+Tp
6
Tm= Probable Time
To= Optimistic Time
Tp=Pessimistic Time
Te=Calculated Time (Best Estimate)
First, make a table, list your tasks, and fill in the estimated time for each. (We have numbered our tasks in the example on the next page for easy identification.) Time can be listed in minutes, hours, days, weeks, months, or years. You should keep the same time scale for each task.
Next, identify what the best and worst case estimates would be. Now, for each task, plug the numbers into the formula given above. The result is the estimated time.
Task
Probable Time
Optimistic Time
Pessimistic Time
Calculated Time
Get paint samples
Choose a paint color
Remove all furniture
Take off trim
Paint trim
Apply first coat
Apply second coat
Put trim back in
Put all furniture back in
-------------------------------------
Estimated Time
10 minutes
Topic Objective
To understand how to calculate estimated times for tasks.
Topic Summary
This formula is considered the standard for estimating time (Te):
To+4Tm+Tp
6
Materials Required
Worksheet Two Case Study
Module Six questions from Worksheet Two
Planning Checklist
Print out one copy of the Worksheet Two Case Study and the Module Six questions for each participant.
Recommended Activity
Pair participants off. Have them copy the task list created in the previous topic to the worksheet. Then, have them estimate time for each task.
Stories to Share
There is also a basic three-point formula that takes the three numbers and averages them. Most project managers find the weighted formula (used here) to be more accurate.
Delivery Tips
Prepare your own worksheet while participants are doing the activity.
Review Questions
What does Tm represent?

## Slide 78: Estimating Resources
People
Material
Money
Notes: Now that the task list is complete, it’s time to decide what resources will be used to accomplish the tasks. In project management, “resources” means people, materials, and money. For now, let’s just focus on people and materials – we’ll look at money in a moment.
A common method of resource listing is to list the tasks, estimated time, and resources required, all in the same table. We have started an example here.
Task
Calculated Time
People Required
Materials Required
Get paint samples
1 hour
Me, Joe
Car
Choose a paint color
2 hours
Me, Joe
Paint Samples
Remove all furniture
1 hour
Take off trim
½ hour
Paint trim
1 hour
Apply first coat
2 hours
Apply second coat
2 hours
Put trim back in
½ hour
Put all furniture back in
1 hour
How detailed you get with your resource list is up to you. For people resources, make sure you include all people who are going to be spending their time on the project, even yourself.
-------------------------------------
Estimated Time
10 minutes
Topic Objective
To understand what the term “resources” means in project management.
Topic Summary
In project management, “resources” means people, materials, and money. For now, let’s just focus on people and materials.
Materials Required
Worksheet Two Case Study
Module Six questions from Worksheet Two
Planning Checklist
Print out one copy of the Worksheet Two Case study and the Module Six questions for each participant.
Recommended Activity
Divide participants into groups of four to six. Ask participants to list people and things that will be required to complete this project.
Review Questions
What are the three types of resources?

## Slide 79: Estimating Costs
Salary
Material
Resources
Notes: Our next step is to add cost information to our table. Make sure to include salary information for everyone, even project team members, and to include line item cost information for each material resource. If you are doing a home project (as we are here), salary information will not be necessary.
Task
Calculated Time
People Required
Estimated Cost for People
Materials Required
Estimated Cost for Resources
Get paint samples
1 hour
Sue, Joe
$0
Car
$10 (gas)
Choose a paint color
2 hours
Sue, Joe
$0
Paint Samples
$0
Remove all furniture
1 hour
Take off trim
½ hour
Paint trim
1 hour
Apply first coat
2 hours
Apply second coat
2 hours
Put trim back in
½ hour
Put all furniture back in
1 hour
-------------------------------------
Estimated Time
10 minutes
Topic Objective
To understand what project costs can encompass.
Topic Summary
Cost information should include the price for materials, as well as salaries and fees for people working on your project.
Materials Required
Flip chart paper
Markers
Worksheet Two Case Study
Planning Checklist
Print out one copy of the Worksheet Two Case Study for each participant.
Recommended Activity
In a large group, brainstorm some costs that would need to be considered for this project.
Stories to Share
This is intended to be a high-level overview of costs. Building a full project budget can be a difficult task, and is out of the scope of this course.
Delivery Tips
This activity can also be performed in small groups.

## Slide 80: Module Six: Review Questions
When building a plan, what is important to remember?
At least half of the plan is a prediction.
The only fact you know for certain is that your plan is 100% right.
There is no room for vagueness as deadlines and outcomes will not change.
Contingency needs to be built in to cope with the uncertainty.
What can unmanaged expectations cause?
Conflict
The project to succeed
Improved time management
A new statement of work to be written

## Slide 81: Module Six: Review Questions
Which of these is a main category that expectations fall into?
Communication
Product management
Delivery date
Quantity
Which of these is not a key checkpoint to include when reviewing documents?
Clarify the outcomes and time frame.
Clarify the requirements and budgets.
Understand the budget and schedule linkages.
Communicate to everyone no matter what their relevance.

## Slide 82: Module Six: Review Questions
What is a good suggestion for writing the task list?
Write the task list before the statement of work is written.
Write the task list in the way that you will accomplish it.
Write the task list as you are completing each task.
Write the task list in the same manner you would your project charter.
When building your schedule, what should you never do?
Make concrete plans
Use outside help
Guess times
Estimate deliverables

## Slide 83: Module Six: Review Questions
What does the Te in the formula used for estimating time represent?
Calculated Time
Pessimistic Time
Optimistic Time
Probable time
What is the first thing you should do when properly estimating time?
Keep the same time scale for each task.
Identify what the best and worst case estimates would be.
Plug the numbers into the formula for estimating time.
Make a table, list your tasks, and fill in the estimated time for each.

## Slide 84: Module Six: Review Questions
In project management, what does “resources” mean?
Staff room, meeting, and deliverables.
People, materials, and money.
Materials, execution, and profit.
Stakeholders, statement of work, and end product.
What is a common method of resource listing?
List the tasks, estimated time, and resources required.
List the assumptions, agreements, and estimated time required.
List the resources, materials, and profits required.
List the tasks, agreements, and materials required.

## Slide 85: Module Six: Review Questions
When building a plan, what is important to remember?
At least half of the plan is a prediction.
The only fact you know for certain is that your plan is 100% right.
There is no room for vagueness as deadlines and outcomes will not change.
Contingency needs to be built in to cope with the uncertainty.
What can unmanaged expectations cause?
Conflict
The project to succeed
Improved time management
A new statement of work to be written

## Slide 86: Module Six: Review Questions
Which of these is a main category that expectations fall into?
Communication
Product management
Delivery date
Quantity
Which of these is not a key checkpoint to include when reviewing documents?
Clarify the outcomes and time frame.
Clarify the requirements and budgets.
Understand the budget and schedule linkages.
Communicate to everyone no matter what their relevance.

## Slide 87: Module Six: Review Questions
What is a good suggestion for writing the task list?
Write the task list before the statement of work is written.
Write the task list in the way that you will accomplish it.
Write the task list as you are completing each task.
Write the task list in the same manner you would your project charter.
When building your schedule, what should you never do?
Make concrete plans
Use outside help
Guess times
Estimate deliverables

## Slide 88: Module Six: Review Questions
What does the Te in the formula used for estimating time represent?
Calculated Time
Pessimistic Time
Optimistic Time
Probable time
What is the first thing you should do when properly estimating time?
Keep the same time scale for each task.
Identify what the best and worst case estimates would be.
Plug the numbers into the formula for estimating time.
Make a table, list your tasks, and fill in the estimated time for each.

## Slide 89: Module Six: Review Questions
In project management, what does “resources” mean?
Staff room, meeting, and deliverables.
People, materials, and money.
Materials, execution, and profit.
Stakeholders, statement of work, and end product.
What is a common method of resource listing?
List the tasks, estimated time, and resources required.
List the assumptions, agreements, and estimated time required.
List the resources, materials, and profits required.
List the tasks, agreements, and materials required.

## Slide 90: Module Seven: Planning (II)
A work well begun is half ended.
Plato
The next part of the planning phase is
to bring together the nuts and bolts
information that we have gathered (the
tasks to be performed, plus the time,
resources, and costs required for each)
and to create an actual plan for
executing the project.
Notes: A work well begun is half ended.
Plato
The next part of the planning phase is to bring together the nuts and bolts information that we have gathered (the tasks to be performed, plus the time, resources, and costs required for each) and to create an actual plan for executing the project.

## Slide 91: Building the Work Breakdown Structure
Project Title
Task 1
Task 1.1
Task 1.1.1
Task 1.2
Task 2
Task 2.1
Notes: A work breakdown structure (WBS) is a graphical breakdown of all the work to be done in the project.
The WBS can be built in five easy steps.
Identify the purpose of the project and write the title at the top.
Establish the major segments of the work. Example for painting a room:
Gather materials
Prepare room
Paint room
Finish room
Break down the segments of the work into sub-components.
Gather materials
Prepare room
Paint room
Finish room
Continue breaking down the work until you reach the level where you will assign and monitor the project work. (Remember, if you are going to assign a task to someone, you may not need to break it down very far.)
Review the WBS with the stakeholders and project team to ensure all items are covered.
-------------------------------------
Estimated Time
10 minutes
Topic Objective
To understand what the Work Breakdown Structure is.
Topic Summary
A work breakdown structure (WBS) is a graphical breakdown of all the work to be done in the project.
Materials Required
List of tasks from Module Six, Creating a Task List
Sticky notes
Blank sheets of flip chart paper
Markers
Recommended Activity
Divide participants into groups of four to six. Ask each group to copy the list of tasks onto sticky notes (one task per note). Then, ask participants to build a work breakdown structure.
Stories to Share
This tool was originally developed by the United States military in the 1950’s.
Delivery Tips
If your class is small, this activity can be performed in a large group.
Review Questions
What does WBS stand for?

## Slide 92: Creating the Schedule
Perform activities simultaneously
Indicate milestones
Include deliverables
Include lag and lead time
Notes: The next task is to build the schedule. This will be your most important document during the project. It will grow and change throughout the project. Keep it up to date to make sure that you will meet your deadlines.
There are many scheduling tools available, which will be discussed in the next topic. For now, let’s look at a simple table format – an expansion of the table that we used earlier.
The first column lists the tasks that need to be performed. This list is typically organized in the order in which the tasks will be accomplished chronologically. In addition, think of how the project might be broken up into phases, to help subdivide tasks that will be performed.
The second column specifies the duration time of each task listed. This duration might be listed in terms of days, weeks, or hours, depending on the project. Next, people and equipment will be listed, followed by start and end dates and/or times.
In order to build the schedule, you will need the availability of people and machines, and sometimes material resources. This is where graphic tools can really help out.
For our room-painting project, Joe and Sue are going to do all the work. We are going to start on Friday at 5 p.m. Here is a summary of their availabilities:
Friday
Saturday
Joe
5 p.m.-10 p.m.
9 a.m.-10 a.m.
1 p.m.-5 p.m.
Sue
5 p.m.-10 p.m.
10 a.m.-noon
1 p.m.-5 p.m.
Here is an example schedule for our room-painting project.
Task
Calculated Time
People Required
Start Time and Date
End Time and Date
Get paint samples
1 hour
Sue, Joe
5 p.m. Friday
6 p.m. Friday
Choose a paint color
2 hours
Sue, Joe
6 p.m. Friday
8 p.m. Friday
Remove all furniture
1 hour
Joe
8 p.m. Friday
9 p.m. Friday
Take off trim
½ hour
Joe
9 p.m. Friday
10 p.m. Friday
Paint trim
1 hour
Sue or Joe
9 a.m. Saturday
10 a.m. Saturday
Apply first coat
2 hours
Sue or Joe
10 .am. Saturday
Noon Saturday
Apply second coat
2 hours
Sue or Joe
1 p.m. Saturday
3 p.m. Saturday
Put trim back in
½ hour
Joe
3 p.m. Saturday
3:30 p.m. Saturday
Put all furniture back in
1 hour
Joe
3:30 p.m. Saturday
4:30 p.m. Saturday
Here are some tips to make your schedule efficient, accurate, and useful.
Look for places where resources can perform activities simultaneously.
Indicate milestones in your schedule. Milestones are identifiable points in your project that require no resources or time. They are simply a key point in time. They can also help you group your project into phases. Milestones in this project might be:
  Have paint color chosen
  Have room cleaned out
  Get painting complete
  Have room put back together
If you are delivering a business project, try to include deliverables with the milestones. This way, sponsors and stakeholders have tangible results at various stages in the project, and are more likely to stay interested and committed.
Make sure to include lag and lead time in your tasks. In the painting project, for example, there is little to no time allotted for the paint to dry between coats. The project will definitely fall behind schedule.
For team projects, make a large copy of the schedule and post it where everyone can see. (You may want to choose a graphic format, discussed in the next module.)
-------------------------------------
Estimated Time
10 minutes
Topic Objective
To understand how to build a project schedule.
Topic Summary
To build a schedule, take the time required for each task and the availability of the resources. Use this to determine how long the entire project will take.
Materials Required
Worksheet Two Case Study
Module Seven activities from Worksheet Two
Planning Checklist
Print out one copy of the Worksheet Two case study and the Module Seven activities for each participant.
Recommended Activity
In pairs, have participants build the schedule for this project.
Stories to Share
We will explore more scheduling tools in the next module.
Delivery Tips
You may want to assign a portion of the WBS to each group.
Review Questions
True or False: There is only one right way to display a project schedule.

## Slide 93: Creating a Risk Management Plan
Mitigate: Reduce the probability of risk
Avoid: Take steps to avoid the risk entirely
Transfer: Transfer the responsibility for the risk to someone outside the project
Accept: This is the best approach for risks with low probability and impact ratings
Notes: The Risk Management Plan details how to approach and manage project risks. A risk management plan should be completed for any project. All project team members and stakeholders should have a meeting to complete a first draft of the plan. This ensures everyone knows what problems could crop up.
The meeting should also identify the response options for each risk. There are four common approaches:
Mitigate: Find ways to reduce the probability and impact levels of the risk.
Avoid: Take steps to avoid the risk entirely. For example, if your chosen construction company may have a worker’s strike soon, perhaps you could choose another company.
Transfer: Transfer the responsibility for the risk to someone outside the project. This will decrease your liability, but it may also decrease your level of control, too.
Accept: Accept that the risk could happen, and choose not to act. This is the best approach for risks with low probability and impact ratings.
During the project, stakeholders and team members should be encouraged to bring up new risks to the project manager. The project manager can then update the plan and communicate it to the rest of the team.
A basic risk management plan looks like this, with one row for each risk:
Risk
Date Identified
Risk Raised By
Probability Rating (/10)
Impact Rating (/10)
Response Options
-------------------------------------
Estimated Time
5 minutes
Topic Objective
To understand what a project risk is and how risks can be managed.
Topic Summary
The Risk Management Plan details how to approach and manage project risks.
Materials Required
Worksheet Two Case Study
Prepared sheet of flip chart paper
Planning Checklist
Print out one copy of the Worksheet Two case study. Prepare a sheet of flip chart paper with the risk management template shown on the next page.
Recommended Activity
In a large group, have participants identify some possible risks. Choose one or two key risks and fill out the risk management plan.
Delivery Tips
This activity can also be performed in small groups.

## Slide 94: Creating a Communication Plan
What? | Status meetings
Who? | Project team
Where? | Whirlwind Room, Fourth Floor
When? | Every Monday at 9 a.m.
Why? | To report issues encountered last week and upcoming tasks for this week
How? | In-person
Notes: Effective communication can make the difference between success and failure in any kind of project. Developing and maintaining a good communication plan will ensure that everyone involved in the project stays up to date, and that information is shared appropriately.
A basic template should include the what, who, where, when, why, and how for each communication item.
Example
What?
Status meetings
Who?
Project team
Where?
Whirlwind Room, Fourth Floor
When?
Every Monday at 9 a.m.
Why?
To report issues encountered last week and upcoming tasks for this week
How?
In-person
As you can see, the communication plan can be formal or informal, highly detailed or broadly framed, based on the needs of the project. Like the schedule, the plan should be maintained, updated, and shared throughout the project.
-------------------------------------
Estimated Time
5 minutes
Topic Objective
To understand how to ensure there is good communication within your project.
Topic Summary
A basic template should include the what, who, where, when, why, and how for each communication item.
Materials Required
Worksheet Two Case Study
Planning Checklist
Print out one copy of the Worksheet Two case study for each participant.
Recommended Activity
Divide participants into groups of eight to ten. Have each group identify some key communication points.
Stories to Share
The “When” in this template can correspond to tasks, phases, and/or risks.
Delivery Tips
This activity can also be performed in large groups.
Review Questions
Why is good communication important to a project?

## Slide 95: Module Seven: Review Questions
What is the definition of the work breakdown structure?
A graphical breakdown of all the work to be done in the project.
Team or project-based organizations.
The ability to use one's time effectively or productively, especially at work.
The structure in which people interact in large and small groups.
What is the first step of the work breakdown structure?
Identify the purpose of the project and write the title at the top.
Review the WBS with the stakeholders and project team to ensure all items are covered.
Establish the major segments of the work.
Break down the segments of the work into sub-components.

## Slide 96: Module Seven: Review Questions
After breaking down the segments of the work into sub-components, what is the next step?
Review the WBS with the stakeholders and project team to ensure all items are covered.
Continue breaking down the work until you reach the level where you will assign and monitor the project work.
Establish the major segments of the work.
Identify the purpose of the project and write the title at the top.
Which of these statements is not true about the schedule?
The schedule is the most important document during the project.
Graphic tools can really help out when building the schedule.
You must keep the schedule up to date to make sure that you will meet your deadlines.
The schedule is the only document that will not grow and change throughout the project.

## Slide 97: Module Seven: Review Questions
What might you need in order to build the schedule?
The availability of people
The availability of machines
Material resources
All of the above
Which of these is a helpful tip to make your schedule accurate, available and useful?
Look for places where resources can perform activities separately.
Identify milestone points in your project that require resources or time.
If you are delivering a business project, try to include deliverables with the milestones.
Make sure to exclude lag and lead time in your tasks.

## Slide 98: Module Seven: Review Questions
In team projects, which members of your team should have access to the schedule?
Only the project manager
Your team leads
The lower-level employees
Everyone
What is not a common approach when identifying responses options to risks?
Mitigate
Permit
Transfer
Accept

## Slide 99: Module Seven: Review Questions
During the project, what should team members and stakeholders be encouraged to do?
Transfer the blame for a risk to someone outside the team.
Update the plan and communicate it to the rest of the team.
Bring up new risks to the project manager.
Create new risks to test and prepare the team.
Which plan ensures that everyone involved in the project stays up to date, and that information is shared appropriately?
Risk management plan
Communication plan
Project charter
Schedule

## Slide 100: Module Seven: Review Questions
What is the definition of the work breakdown structure?
A graphical breakdown of all the work to be done in the project.
Team or project-based organizations.
The ability to use one's time effectively or productively, especially at work.
The structure in which people interact in large and small groups.
What is the first step of the work breakdown structure?
Identify the purpose of the project and write the title at the top.
Review the WBS with the stakeholders and project team to ensure all items are covered.
Establish the major segments of the work.
Break down the segments of the work into sub-components.

## Slide 101: Module Seven: Review Questions
After breaking down the segments of the work into sub-components, what is the next step?
Review the WBS with the stakeholders and project team to ensure all items are covered.
Continue breaking down the work until you reach the level where you will assign and monitor the project work.
Establish the major segments of the work.
Identify the purpose of the project and write the title at the top.
Which of these statements is not true about the schedule?
The schedule is the most important document during the project.
Graphic tools can really help out when building the schedule.
You must keep the schedule up to date to make sure that you will meet your deadlines.
The schedule is the only document that will not grow and change throughout the project.

## Slide 102: Module Seven: Review Questions
What might you need in order to build the schedule?
The availability of people
The availability of machines
Material resources
All of the above
Which of these is a helpful tip to make your schedule accurate, available and useful?
Look for places where resources can perform activities separately.
Identify milestone points in your project that require resources or time.
If you are delivering a business project, try to include deliverables with the milestones.
Make sure to exclude lag and lead time in your tasks.

## Slide 103: Module Seven: Review Questions
In team projects, which members of your team should have access to the schedule?
Only the project manager
Your team leads
The lower-level employees
Everyone
What is not a common approach when identifying responses options to risks?
Mitigate
Permit
Transfer
Accept

## Slide 104: Module Seven: Review Questions
During the project, what should team members and stakeholders be encouraged to do?
Transfer the blame for a risk to someone outside the team.
Update the plan and communicate it to the rest of the team.
Bring up new risks to the project manager.
Create new risks to test and prepare the team.
Which plan ensures that everyone involved in the project stays up to date, and that information is shared appropriately?
Risk management plan
Communication plan
Project charter
Schedule

## Slide 105: Module Eight: Planning Tools
Good fortune is what happens when opportunity meets with planning.
Thomas Edison
In the last module, we looked at how to build a schedule in table format. This format will work well for small projects. However, for more complex projects, you will need additional tools. This module will explore four of the most popular tools, including graphical methods and Microsoft Project.
Notes: Gantt charts have become a common technique for representing the phases and activities of a project work breakdown structure, as they can be understood by a wide audience.
A Gantt chart is a type of bar chart that illustrates a project schedule. Gantt charts illustrate the start and finish dates of each task, as well as task dependencies and links. Gantt charts can be easily customized to show resources, costs, and other important information. They can also be color-coded for different task phases or responsibilities.
Example
-------------------------------------
Estimated Time
10 minutes
Topic Objective
To understand what a Gantt chart is and what it is used for.
Topic Summary
A Gantt chart is a type of bar chart that illustrates a project schedule.
Materials Required
Example Gantt chart (shown on the next page)
Planning Checklist
Make sure you have the PowerPoint slides for this course. Or, you can blow up the provided diagram and show it on overhead or flip chart.
Recommended Activity
Review the sample Gantt chart with participants.
Stories to Share
The Gantt chart was developed by Henry Gantt in the 1920’s. One of the first projects that it was used on was the construction of the Hoover Dam.
Delivery Tips
Make sure that participants know that this is a very simple example. Part of the power of Gantt charts is that they can be easily customized.
Although our example was created with Microsoft Project, Gantt charts can be drawn by hand.
Review Questions
What type of chart is a Gantt chart?

## Slide 106: The Gantt Chart
Notes: Gantt charts have become a common technique for representing the phases and activities of a project work breakdown structure, as they can be understood by a wide audience.
A Gantt chart is a type of bar chart that illustrates a project schedule. Gantt charts illustrate the start and finish dates of each task, as well as task dependencies and links. Gantt charts can be easily customized to show resources, costs, and other important information. They can also be color-coded for different task phases or responsibilities.
Example
-------------------------------------
Estimated Time
10 minutes
Topic Objective
To understand what a Gantt chart is and what it is used for.
Topic Summary
A Gantt chart is a type of bar chart that illustrates a project schedule.
Materials Required
Example Gantt chart (shown on the next page)
Planning Checklist
Make sure you have the PowerPoint slides for this course. Or, you can blow up the provided diagram and show it on overhead or flip chart.
Recommended Activity
Review the sample Gantt chart with participants.
Stories to Share
The Gantt chart was developed by Henry Gantt in the 1920’s. One of the first projects that it was used on was the construction of the Hoover Dam.
Delivery Tips
Make sure that participants know that this is a very simple example. Part of the power of Gantt charts is that they can be easily customized.
Although our example was created with Microsoft Project, Gantt charts can be drawn by hand.
Review Questions
What type of chart is a Gantt chart?

## Slide 107: The Network Diagram
Notes: A network diagram is another way of showing the path of tasks in the project. Tasks are each placed in a box and each box is placed in chronological order. Arrows are drawn from task to task, indicating the logical progression of work. Boxes can be customized to contain any information you like, including start and finish dates, task length, cost, resources, and more. Boxes can also be color-coded based on the phase of the project; resource required, team assignment, etc.
Here is an example of a network diagram from Microsoft Project. (We have scheduled the “Remove furniture” and “Take off trim” tasks to happen at the same time for demonstration purposes.)
We recommend building the network diagram as a team using these steps.
Write all steps out on sticky notes.
Tape a large piece of paper to the wall.
Place sticky notes in order.
Once you think you have the right order, check to make sure lag and lead time is allowed for. Also look for ways that work can be completed simultaneously.
Draw arrows to indicate task links. Color-code the boxes if desired.
Post the diagram in a central location. Make a copy for reference, and keep the original drawing updated as the project progresses.
The network diagram will also help you identify the critical path: the shortest path through the project. This will help if an element of the triple constraint changes and you must alter your plan.
-------------------------------------
Estimated Time
10 minutes
Topic Objective
To understand what a network diagram is and what it is used for.
Topic Summary
A network diagram is another way of showing the path of tasks in the project.
Materials Required
Example network diagram, provided on the next page
Planning Checklist
Make sure you have the PowerPoint slides for this course. Or, you can blow up the provided diagram and show it on overhead or flip chart.
Recommended Activity
Review the sample network diagram with participants.
Stories to Share
The Network Diagram was also originally developed by the United States military.
Delivery Tips
Emphasize that the network diagram can be customized.
Although our sample diagram was created with Microsoft Project, network diagrams can be drawn by hand.
Review Questions
What is the first step to creating a network diagram?

## Slide 108: Using a RACI Chart
R
  Responsible for execution
A
  Approver
Example | Sue | Bob | Joe | Jane
Build widget plan | A | R | I | I
Build widget | R | A | C | I
Ship widget to customers | I | I | I | R
C
  Consult
I
  Keep informed
Notes: A RACI chart is an excellent way to outline who is responsible for what during the project. To start, create a chart with tasks listed on the left hand side, and resources listed across the top. Now, put the appropriate letter in each cell:
R: Responsible for execution
A: Approver
C: Consult
I: Keep informed
Example
Sue
Bob
Joe
Jane
Build widget plan
A
R
I
I
Build widget
R
A
C
I
Ship widget to customers
I
I
I
R
-------------------------------------
Estimated Time
5 minutes
Topic Objective
To understand what a RACI chart is and when to use it.
Topic Summary
A RACI chart, also known as a responsibility matrix, outlines who is responsible for what during the project.
Materials Required
Example RACI chart, provided on the next page
Planning Checklist
Make sure you have the PowerPoint slides for this course. Or, you can blow up the provided chart and show it on overhead or flip chart.
Recommended Activity
Review the sample RACI chart with participants.
Stories to Share
Some project managers add an E to the legend, so that the R stands for responsible (i.e., the project sponsor), while the E indicates who must actually perform the task.
Review Questions
What does each letter of RACI stand for?

## Slide 109: Going the Extra Mile: Microsoft Project
Microsoft Project is just a tool
Understand how it calculates numbers
Every project requires different tools
Notes: Throughout the course, we have made some references to using computer software to manage projects. We have even included some diagrams from Microsoft Project, a popular project management application.
Applications like Microsoft Project are extremely useful for project managers and their teams. Microsoft Project, as an example, stores information about resources, schedules, tasks, budgets, and more; generates reports on the fly; allows you to enter and view information in numerous ways; and even allows you to collaborate with other team members.
We urge everyone, particularly new project managers, to remember that Microsoft Project is just a tool. In order to make the best use of it, you must understand how it calculates numbers and generates diagrams. Once you have a solid understanding of basic project management concepts, feel free to take the time to learn about project management software if you desire.
Remember, too, that every project requires different tools. For small projects, you may not need the sophisticated features of a software program. If you choose to grow your project management skills, however, and take on larger projects, you will appreciate the extra tools available in these applications.
-------------------------------------
Estimated Time
5 minutes
Topic Objective
To understand what Microsoft Project is and when to use it.
Topic Summary
Microsoft Project is one of the most popular project management software applications.
Recommended Activity
In a large group, discuss the following questions:
What are the advantages to using Microsoft Project? What are the disadvantages?
Is Microsoft Project used in your organization? If so, how?
Have you used Microsoft Project? If so, what have your experiences been like?
Stories to Share
Microsoft Project was first released in 1984.
Delivery Tips
If possible, have a laptop with Microsoft Project installed and a sample project set up for participants to view.
Review Questions
True or False: All projects should be set up in Microsoft Project.

## Slide 110: Module Eight: Review Questions
Which of these statements is not true of the Gantt chart?
A Gantt chart is a type of bar chart that illustrates a project schedule.
Gantt charts can be easily customized to show resources, costs, and other important information.
Gantt charts illustrate the start and finish dates of each task, as well as task dependencies and links.
They have become a common technique for representing the phases and activities of a project work breakdown structure, as they can be understood by a small audience.
Which of these is an additional benefit of using the Gantt chart?
It helps you assign tasks to several other project manager’s team.
Arrows can be drawn from task to task, indicating the logical progression of work.
They can be color-coded for different task phases or responsibilities.
They can post the diagram in a central location.

## Slide 111: Module Eight: Review Questions
When building the network diagram as a team, what is the first step?
Write all steps out on sticky notes
Place sticky notes in order
Tape a large sheet to the wall
Draw arrows to indicate task links
How will using the network diagram to identify a critical path help?
It will help if you need to assign tasks to another project manager’s team.
It will help if an element of the triple constraint changes and you must alter your plan.
It will help if a task in the statement of work needs updating.
It will help if you need to keep all tasks and responsibilities the same.

## Slide 112: Module Eight: Review Questions
Which planning tool will be best to use for outlining who is responsible for what during the project?
The RACI Char
The Network Diagram.
The Gantt Chart
The Microsoft Project
How would you start to make a RACI chart?
Customize each cell to show resources, costs, and other important information.
Tasks are each placed in a box and each box is placed in chronological order.
Create a chart with tasks and put each task in the appropriate cell.
Create a chart with tasks listed on the left hand side and resources listed across the top.

## Slide 113: Module Eight: Review Questions
What does the “I” in RACI stand for?
Keep individualized
Keep informed
Include
Improvise
Which of these describes the Microsoft Project?
A program that allows the user to use the Gantt chart, the Network Diagram, and the RACI chart all at once
A template used by the RACI chart
A popular project management application
A little-known project management organizer

## Slide 114: Module Eight: Review Questions
Which of these statements is not true of Microsoft Project?
Microsoft Project stores information about resources, schedules, tasks, budgets, and more.
Microsoft Project allows you to collaborate with other team members.
Microsoft Project is extremely useful for project managers, not their teams as a whole.
Microsoft Project allows you to enter and view information in numerous ways.
When is it possible that you would not need the sophisticated features of a software program?
With large audiences
With startup companies
When more than one team is working together
With small projects

## Slide 115: Module Eight: Review Questions
Which of these statements is not true of the Gantt chart?
A Gantt chart is a type of bar chart that illustrates a project schedule.
Gantt charts can be easily customized to show resources, costs, and other important information.
Gantt charts illustrate the start and finish dates of each task, as well as task dependencies and links.
They have become a common technique for representing the phases and activities of a project work breakdown structure, as they can be understood by a small audience.
Which of these is an additional benefit of using the Gantt chart?
It helps you assign tasks to several other project manager’s team.
Arrows can be drawn from task to task, indicating the logical progression of work.
They can be color-coded for different task phases or responsibilities.
They can post the diagram in a central location.

## Slide 116: Module Eight: Review Questions
When building the network diagram as a team, what is the first step?
Write all steps out on sticky notes
Place sticky notes in order
Tape a large sheet to the wall
Draw arrows to indicate task links
How will using the network diagram to identify a critical path help?
It will help if you need to assign tasks to another project manager’s team.
It will help if an element of the triple constraint changes and you must alter your plan.
It will help if a task in the statement of work needs updating.
It will help if you need to keep all tasks and responsibilities the same.

## Slide 117: Module Eight: Review Questions
Which planning tool will be best to use for outlining who is responsible for what during the project?
The RACI Char
The Network Diagram.
The Gantt Chart
The Microsoft Project
How would you start to make a RACI chart?
Customize each cell to show resources, costs, and other important information.
Tasks are each placed in a box and each box is placed in chronological order.
Create a chart with tasks and put each task in the appropriate cell.
Create a chart with tasks listed on the left hand side and resources listed across the top.

## Slide 118: Module Eight: Review Questions
What does the “I” in RACI stand for?
Keep individualized
Keep informed
Include
Improvise
Which of these describes the Microsoft Project?
A program that allows the user to use the Gantt chart, the Network Diagram, and the RACI chart all at once
A template used by the RACI chart
A popular project management application
A little-known project management organizer

## Slide 119: Module Eight: Review Questions
Which of these statements is not true of Microsoft Project?
Microsoft Project stores information about resources, schedules, tasks, budgets, and more.
Microsoft Project allows you to collaborate with other team members.
Microsoft Project is extremely useful for project managers, not their teams as a whole.
Microsoft Project allows you to enter and view information in numerous ways.
When is it possible that you would not need the sophisticated features of a software program?
With large audiences
With startup companies
When more than one team is working together
With small projects

## Slide 120: Module Nine: Executing the Project
You can only elevate individual performance by elevating that of the entire system.
W. Edwards Deming
We have spent a lot of time talking about what the project will do and making plans for how to do it. Finally, it is time to get to work and put our plans into action.
Notes: You can only elevate individual performance by elevating that of the entire system.
W. Edwards Deming
We have spent a lot of time talking about what the project will do and making plans for how to do it. Finally, it is time to get to work and put our plans into action.

## Slide 121: Establishing Baselines
Formal end of the planning phase
Original plan
Measuring stick
Communicated to all stakeholders
Notes: There is actually one final task to complete before we can start work on our project. Establishing the baseline indicates the formal end of the planning phase and the beginning of project execution and control.
The baseline is your original plan, containing the original scope, cost, and time. This gives you a measuring stick throughout the project. For example, let’s say that your baseline budget was $20,000. If, after the first task, you have spent $15,000, you know you’re in trouble. You can then evaluate the situation and prepare an action plan – hopefully before things get too out of hand.
The baseline should be communicated to all stakeholders and the project team. Scope and resources can be outlined in text format. Cost and time can be displayed as a graph. Or, you can use a graphic scheduling tool (like a Gantt chart or network diagram) to display the original plan and track where you are. (More on that in a moment!)
-------------------------------------
Estimated Time
10 minutes
Topic Objective
To understand what a baseline is and its use in project management.
Topic Summary
Establishing the baseline indicates the formal end of the planning phase and the beginning of project execution and control.
The baseline is your original plan, containing the original scope, cost, and time. This gives you a measuring stick throughout the project.
Materials Required
List of categories
Planning Checklist
Prepare a list of categories before the workshop, or use the list below.
Height
Age
Birth month
Number of pets
Number of bones broken
Number of pieces of jewelry they are wearing
Number of projects they have managed or been part of
Number of siblings
Recommended Activity
After delivering the content for this module, engage participants in a quick energizer.
Divide participants into groups of ten to twelve. Explain that you are going to call out a category and they must line themselves up by those criteria. If you like, you can keep score or assign points.
Keep this activity quick and light.
Delivery Tips
If your group is smaller than twenty, do not split the groups up.

## Slide 122: Monitoring Project Progress
Status meetings
Regular status reports
Hands-on observation
Notes: As the project manager, it is your responsibility to monitor all the parts of your project to make sure they are continuing as planned. If issues arise, it is your responsibility to resolve them, or to escalate them to someone who can resolve them.
Some popular, effective methods of tracking project progress include:
Regular status meetings
Regular status reports
Hands-on observation
Recording data manually or electronically and generating reports (for example, spending to date versus total budget)
Your visual scheduling tools can also help you record project progress and communicate it to your team.
As tasks are completed, they can be crossed off the Gantt chart and/or the network diagram.
If new resources need to be added, they can be added to network diagram boxes.
If tasks need to be re-scheduled, they can be moved around on the network diagram.
Risks, accomplishments, and lessons learned can be posted next to tasks.
-------------------------------------
Estimated Time
10 minutes
Topic Objective
To understand how to monitor project progress.
Topic Summary
As the project manager, it is your responsibility to monitor all the parts of your project to make sure they are continuing as planned. You can use a variety of tools to do this.
Materials Required
Worksheet Two Case Study
Planning Checklist
Print out one copy of the Worksheet Two Case Study for each participant.
Recommended Activity
In groups of four to six, have participants identify what project monitoring tools would be most appropriate for the project at Super Shovels.
Review Questions
True or False: The project manager is responsible for fixing all project issues themselves.

## Slide 123: Triple Constraint Reduction Methods
Crashing: Reduce the schedule without changing the budget
Fast-Tracking: Where lag/lead time can be reduced or eliminated.
De-scoping: Removes items from the project scope to free up time and/or money.
Notes: Be forewarned: after all of your planning, it is very likely that one element of the triple constraint will change. Perhaps a team member has left the organization, the budget has been cut, or new technical requirements need to be met.
When approached with scope changes, don’t panic! There are three established methods that you can use to decide how to alter the course of the project.
Crashing: Reduce the schedule without changing the budget, or vice-versa (depending on project needs). This can be done by using cheaper resources, or by re-evaluating time estimates.
Fast-Tracking: Can be done with the schedule only. Looks at the schedule to see which tasks (if any) can be completed concurrently, and where lag/lead time can be reduced or eliminated.
De-scoping: Removes items from the project scope to free up time and/or money.
Make sure that you truly look at the big picture, and include short and long term benefits and consequences in your decision-making process.
Once you have performed careful analysis, gather documentation to back up your decision, clear the decision with the appropriate stakeholders, change the project plan accordingly, and communicate the plan change to everyone involved.
-------------------------------------
Estimated Time
10 minutes
Topic Objective
To understand how to adjust your project plans if a triple constraint element is changed.
Topic Summary
There are three established methods that you can use to decide how to alter the course of the project.
Crashing
Fast-tracking
De-scoping
Materials Required
Flip chart paper
Markers
Planning Checklist
Review the scenarios below before the workshop and come up with some ideas of your own.
Recommended Activity
Revisit the following scenarios with the group. Explore which reduction method would be appropriate for each scenario.
Budget is reduced by 25%
Building needs to be completed three months earlier
Product must have 99% purity instead of 95%
Need to renovate three office buildings instead of one
Delivery Tips
There are no “right” answers for this activity. The objective is to have participants see how changes can have a ripple effect.
Review Questions
Name one of the triple constraints.

## Slide 124: Module Nine: Review Questions
What indicates the formal end of the planning phase and the beginning of project execution and control?
Establishing the baseline
Maintaining and controlling
Initiating
Resolving risk
Who should the baseline be communicated to?
The project team and those working on the budget.
All stakeholders and the project team.
All stakeholders and direct supervisors.
The project team and direct supervisors.

## Slide 125: Module Nine: Review Questions
When establishing baselines, what can be outlined in text format?
The baseline
Cost and time
Scope and resources
Both a & b
If an issue arises, what is the responsibility of the project manager?
To resolve the issues
To escalate the issues to someone who can resolve them
To ensure that issues do not arise in the first place
Both a & b

## Slide 126: Module Nine: Review Questions
Which of these is not a popular, effective method of tracking project progress?
Regular status meetings
Hands-off observation
Recording data manually or electronically and generating reports
Regular status reports
Which of these is a good suggestion when using your visual scheduling tools?
Risks, accomplishments, and lessons learned can be posted only in a Gantt Chart.
If tasks need to be re-scheduled, they cannot be moved around on the network diagram.
As tasks are completed, they can be crossed off the RACI chart.
If new resources need to be added, they can be added to network diagram boxes.

## Slide 127: Module Nine: Review Questions
After all your planning, what is very likely to change?
One element of the triple constraint
The guidance of your shareholders
One of the members of your project management team
The deliverables of the project
Which of these is not an established method that you can use to decide how to alter the course of the project?
Projecting
Crashing
Fast-tracking
De-scoping

## Slide 128: Module Nine: Review Questions
When faced with scope changes, how can you reduce the schedule without changing the budget (or vice versa)?
This can be done by removing items from the project scope to free up money
This can be done by removing items from the project scope to free up time
This can be done by using cheaper resources, or by re-evaluating time estimates
This can be done with the schedule only
When using triple constraint reduction methods, what is important to remember?
Include short and long term benefits and consequences in your decision-making process
Don’t panic
Make sure that you truly look at the big picture
All of the above

## Slide 129: Module Nine: Review Questions
What indicates the formal end of the planning phase and the beginning of project execution and control?
Establishing the baseline
Maintaining and controlling
Initiating
Resolving risk
Who should the baseline be communicated to?
The project team and those working on the budget.
All stakeholders and the project team.
All stakeholders and direct supervisors.
The project team and direct supervisors.

## Slide 130: Module Nine: Review Questions
When establishing baselines, what can be outlined in text format?
The baseline
Cost and time
Scope and resources
Both a & b
If an issue arises, what is the responsibility of the project manager?
To resolve the issues
To escalate the issues to someone who can resolve them
To ensure that issues do not arise in the first place
Both a & b

## Slide 131: Module Nine: Review Questions
Which of these is not a popular, effective method of tracking project progress?
Regular status meetings
Hands-off observation
Recording data manually or electronically and generating reports
Regular status reports
Which of these is a good suggestion when using your visual scheduling tools?
Risks, accomplishments, and lessons learned can be posted only in a Gantt Chart.
If tasks need to be re-scheduled, they cannot be moved around on the network diagram.
As tasks are completed, they can be crossed off the RACI chart.
If new resources need to be added, they can be added to network diagram boxes.

## Slide 132: Module Nine: Review Questions
After all your planning, what is very likely to change?
One element of the triple constraint
The guidance of your shareholders
One of the members of your project management team
The deliverables of the project
Which of these is not an established method that you can use to decide how to alter the course of the project?
Projecting
Crashing
Fast-tracking
De-scoping

## Slide 133: Module Nine: Review Questions
When faced with scope changes, how can you reduce the schedule without changing the budget (or vice versa)?
This can be done by removing items from the project scope to free up money
This can be done by removing items from the project scope to free up time
This can be done by using cheaper resources, or by re-evaluating time estimates
This can be done with the schedule only
When using triple constraint reduction methods, what is important to remember?
Include short and long term benefits and consequences in your decision-making process
Don’t panic
Make sure that you truly look at the big picture
All of the above

## Slide 134: Module Ten: Maintaining and Controlling the Project
Trying is just a noisy way of saying no progress.
Warren Bennis
The fourth phase of project
management is maintaining and
controlling. Although it is part of the
execution phase, it is so important that
the PMBOK separates it out into its
own set of activities. This module will
give you some key tools for keeping
your project on track.
Notes: Trying is just a noisy way of saying no progress.
Warren Bennis
The fourth phase of project management is maintaining and controlling. Although it is part of the execution phase, it is so important that the PMBOK separates it out into its own set of activities. This module will give you some key tools for keeping your project on track.

## Slide 135: Making the Most of Status Updates
Tasks planned for the previous week
Tasks completed in the previous week
Tasks planned for the following week
Issues and risks identified
Notes: Regular, mandatory status meetings for all project team members should be a part of any project. These meetings will give team members a chance to connect, discuss issues, and solve problems. It will also give you the opportunity to coach team members and make sure you’re on top of what everyone is doing.
Status meetings should be tied in with status reports. We recommend that both items be completed weekly or bi-weekly, depending on your project. Also, remember that meetings and reports can be brief or detailed – it all depends on what level of control you need and how big the project is.
We recommend a Friday-Monday schedule, where reports are submitted on Friday (before the end of the day) and status meetings are held on Monday. If a holiday happens to occur, reports could be submitted on the Thursday, and meetings could take place on the Tuesday.
Status reports should contain the following items:
Team member name
Status report date
Tasks planned for the previous week
Tasks completed in the previous week
Tasks planned for the following week
Issues and risks identified (highlight those that require project manager attention)
Status meetings, then, are a review of tasks that each member completed for the previous week, what they have planned for the upcoming week, and what issues they have encountered or predict.
Again, status reports and meetings should be customized for your projects’ needs. Team members should also know that issues should be reported to the project manager as they arise.
-------------------------------------
Estimated Time
10 minutes
Topic Objective
To understand how to organize status reports and update meetings.
Topic Summary
Regular, mandatory status meetings for all project team members should be a part of any project. Status meetings should be tied in with status reports.
Materials Required
Flip chart paper
Markers
Recommended Activity
In a large group, create a do’s and don’ts list for status meetings.
Delivery Tips
If your group is larger than twenty, you may want to perform this activity in smaller groups.

## Slide 136: Managing Change
Change Request Number: | Change Requested On:
Change Requested By: | Change Submitted By:
Change Details: | Tasks Affected:
Approved or Rejected? | By:
Notes: Change management is another way of controlling your project. This process ensures that any changes, whether they are to the objectives, requirements, tasks, or design of a particular component, are approved by the project team.
At the beginning of the project, all stakeholders and team members must agree not to make any changes to the project plan or to the design of its components, and to instead follow a change management process. Then, when a change is required, a change management form is completed.
Example
Change Request Number:
Change Requested On:
Change Requested By:
Change Submitted By:
Change Details:
Tasks Affected:
Approved or Rejected?
By:
Then, the form is submitted to the project manager. The change is reviewed and a decision is made. In small projects, the review process may be done by the project manager. For larger projects, the project team or even a separate task force (typically called the Change Control Board, or CCB) is involved.
-------------------------------------
Estimated Time
10 minutes
Topic Objective
To become familiar with a basic change management process.
Topic Summary
At the beginning of the project, all stakeholders and team members must agree not to make any changes to the project plan or to the design of its components, and to instead follow a change management process. Then, when a change is required, a change management request is completed. A decision is then made by the project manager.
Materials Required
Worksheet Two Case Study
Module Ten questions from Worksheet Two
Planning Checklist
Print out one copy of the Worksheet Two Case Study and the Module Ten questions for each participant.
Recommended Activity
Divide participants into groups of four to six. Ask each group to answer the worksheet questions.
Delivery Tips
You can also have a large group discussion, and use the worksheet questions as a guide.

## Slide 137: Monitoring Risks
Be proactive
Keep an eye out for assumptions
Keep a record of actions
Notes: Remember the risk management plan that we built during the planning phase? Make sure it doesn’t stay on a shelf. Continue to monitor and add to it.
Here are some additional tips for making sure risks don’t ruin your project:
Be proactive. Have meetings with stakeholders and outside parties to ensure your risk assessment is accurate and that your action plan (if you have one) is valid.
Keep an eye out for assumptions. Make sure that they continue to hold true. Identify what could happen if those assumptions are unfulfilled.
Keep a record of what actions you take to mitigate risks.
-------------------------------------
Estimated Time
10 minutes
Topic Objective
To understand how to monitor risks during a project.
Topic Summary
During the execution of the project, you must continue to monitor risks and add to the risk management plan. (See Module Seven for more information.)
Materials Required
Worksheet Two Case Study
Planning Checklist
Print out one copy of the Worksheet Two case study for each participant.
Recommended Activity
In a large group, discuss what new risks might arise during our case study project.
Delivery Tips
This activity can also be performed in small groups.
Review Questions
Name one activity that you can perform to monitor risks.

## Slide 138: Module Ten: Review Questions
Which is the fourth phase of project management?
Planning
Maintaining and controlling
Preparing and executing
Initiating
How often is it recommended that status meetings and status updates be completed?
Weekly or bi-weekly
Monthly or bi-monthly
Every quarter, tied in with quarterly reports
Daily

## Slide 139: Module Ten: Review Questions
In a Friday-Monday schedule, if a holiday occurs on a Friday, when it recommended that status updates be submitted?
Thursday
Friday, even with the holiday
The following Monday
Wednesday
Which of these is not an item that should be contained within the status report?
Issues and risks identified
Status report date
Tasks planned for the previous week
Tasks planned for the following months

## Slide 140: Module Ten: Review Questions
What is a good rule of thumb for status reports and meetings?
Status meetings should be kept separate from status reports whenever possible.
Status meetings and reports should be kept brief.
Status meetings and reports should be kept intricately detailed.
Status meetings and reports should be customized for your projects’ needs.
What process assures that all changes are approved by the project team?
Status meetings and reports
Risk management
Change management
Project management team changes

## Slide 141: Module Ten: Review Questions
Who is the change management form submitted to?
Human resources
The project manager
The project management team
The stakeholders
For larger projects, who can be involved in managing change?
The project manager
The project management team
A separate task force
All of the above

## Slide 142: Module Ten: Review Questions
Which plan used during the planning phase can also be used in the maintaining and controlling phase?
Change management plan
Risk management plan
Status reports and updates
Communication plan
Which of these is not a helpful tip when using a risk management plan?
Have meetings with stakeholders and outside parties to ensure your risk assessment is accurate.
Keep a record of what actions you take to mitigate risks.
Be reactive when it comes to maintaining and controlling with stakeholders and outside parties.
Identify what could happen if assumptions are unfulfilled.

## Slide 143: Module Ten: Review Questions
Which is the fourth phase of project management?
Planning
Maintaining and controlling
Preparing and executing
Initiating
How often is it recommended that status meetings and status updates be completed?
Weekly or bi-weekly
Monthly or bi-monthly
Every quarter, tied in with quarterly reports
Daily

## Slide 144: Module Ten: Review Questions
In a Friday-Monday schedule, if a holiday occurs on a Friday, when it recommended that status updates be submitted?
Thursday
Friday, even with the holiday
The following Monday
Wednesday
Which of these is not an item that should be contained within the status report?
Issues and risks identified
Status report date
Tasks planned for the previous week
Tasks planned for the following months

## Slide 145: Module Ten: Review Questions
What is a good rule of thumb for status reports and meetings?
Status meetings should be kept separate from status reports whenever possible.
Status meetings and reports should be kept brief.
Status meetings and reports should be kept intricately detailed.
Status meetings and reports should be customized for your projects’ needs.
What process assures that all changes are approved by the project team?
Status meetings and reports
Risk management
Change management
Project management team changes

## Slide 146: Module Ten: Review Questions
Who is the change management form submitted to?
Human resources
The project manager
The project management team
The stakeholders
For larger projects, who can be involved in managing change?
The project manager
The project management team
A separate task force
All of the above

## Slide 147: Module Ten: Review Questions
Which plan used during the planning phase can also be used in the maintaining and controlling phase?
Change management plan
Risk management plan
Status reports and updates
Communication plan
Which of these is not a helpful tip when using a risk management plan?
Have meetings with stakeholders and outside parties to ensure your risk assessment is accurate.
Keep a record of what actions you take to mitigate risks.
Be reactive when it comes to maintaining and controlling with stakeholders and outside parties.
Identify what could happen if assumptions are unfulfilled.

## Slide 148: Module Eleven: Closing Out
The real problem is what to do with problem solvers after the problem is solved.
Gay Talese
You’ve reached the point where all the
tasks in your project plan have been
checked off: the widget is built, the
advertisements are on TV, and boxes
are being shipped to customers. Before
you consider the project complete,
however, there are a few more things
to be done.
Notes: The real problem is what to do with problem solvers after the problem is solved.
Gay Talese
You’ve reached the point where all the tasks in your project plan have been checked off: the widget is built, the advertisements are on TV, and boxes are being shipped to customers. Before you consider the project complete, however, there are a few more things to be done.

## Slide 149: Preparing for Closeout
Closure of a project can be difficult
Reviewing their performance
Help team members get through this tough time
Notes: As your project winds down, you may find team morale dropping, or anxiety increasing. Closure of a project can be difficult, particularly if the project has been long and/or difficult, or if team members will not be working together afterward.
To help team members get through this tough time, make sure they know what they will be working on after the project. Make sure they know who will be reviewing their performance. (If it is not you, let them know that you will pass on information about their performance to their regular supervisor. This expectation should have been set at the beginning of the project, too.) Encourage team members to come to you with questions.
-------------------------------------
Estimated Time
5 minutes
Topic Objective
To understand how to ensure a smooth transition for team members.
Topic Summary
As your project winds down, you may find team morale dropping, or anxiety increasing. Closure of a project can be difficult, particularly if the project has been long and/or difficult, or if team members will not be working together afterward.
Materials Required
Worksheet Two Case Study
Planning Checklist
Print out one copy of the Worksheet Two Case Study for each participant.
Recommended Activity
In a large group, brainstorm what closing activities might be required for this project.
Stories to Share
Sometimes, the closure of a project can represent the grieving process. For some people, it is a very serious time in their professional lives.
Delivery Tips
A ribbon-cutting ceremony to open the new office building could be one idea.

## Slide 150: Celebrating Successes
Take time to celebrate
Recognize each person for their contributions
Have a close-out meeting
Notes: After the project, take time to celebrate the things that the project team did well. Try to recognize each person for their contributions and accomplishments.
Team celebrations, of course, are also an important part of project close-out. It is a great idea to have a team party. Another excellent idea is to have a close-out meeting with stakeholders, team members, and other interested parties. This provides an opportunity to review the project’s accomplishments and challenges – and it ties in with our next topic.
-------------------------------------
Estimated Time
10 minutes
Topic Objective
To understand the important of having a celebration at the end of the project.
Topic Summary
After the project, take time to celebrate the things that the project team did well. Team celebrations, of course, are also an important part of project close-out.
Materials Required
Index cards
Markers
Craft supplies, such as glue, sparkles, cut-outs, etc. (if desired)
Planning Checklist
Have plenty of supplies on hand for this activity.
Recommended Activity
Place a stack of index cards and supplies in the middle of each table.
Explain to participants that recognition is an important part of our everyday lives that many people neglect. It is even more important when you are a project manager.
Ask participants to take a moment to take a pile of index cards and to write a compliment for each individual in the class on that card.
This is an easy, inexpensive way of recognizing your team members. It is also a good way to build team morale, particularly if team members are having a hard time getting along.
Stories to Share
Of course, celebrations should take place throughout the project. One easy way to do this is to make recognition part of your status meetings.
Delivery Tips
If your group is so large that all members have not had a chance to interact, divide the class into smaller groups, or limit the number of cards that each person must prepare.

## Slide 151: Learning from Project Challenges
Ensures everyone is aware of the challenges encountered
Effort put into the task is not wasted
Apply these lessons to future projects
Lessons learned should be documented
Notes: No project will go perfectly. There will always be a risk you didn’t anticipate, tasks that run longer than they should have, project team members that didn’t perform as you expected… If it can happen, it probably will!
Meeting with team members and stakeholders to identify lessons learned throughout the project is a valuable exercise for several reasons.
It ensures everyone is aware of the challenges encountered and what was done to resolve them.
If something is learned from a mistake or failed endeavor, then the effort put into the task is not entirely wasted.
Participants can apply these lessons to future projects and be more successful.
Lessons learned should be documented and included with final project documentation.
-------------------------------------
Estimated Time
5 minutes
Topic Objective
To understand how to identify lessons learned throughout the project.
Topic Summary
No project will go perfectly. Meeting with team members and stakeholders to identify lessons learned throughout the project is a valuable exercise.
Materials Required
Flip chart paper
Markers
Recommended Activity
In a large group, discuss what participants learned during the workshop.
Stories to Share
This activity is important for all projects, no matter what their size.
Delivery Tips
This activity can also be performed in small groups.
Review Questions
Why is it important to document lessons learned?

## Slide 152: Scope Verification
Were all needs met?
Were all deliverables met?
Are the stakeholders happy with the results?
Notes: Another important part of project closeout is scope verification. This is where stakeholders and team members meet to determine whether or not the project did what it set out to do.
This checklist can be used as a guide for scope verification.
Were all needs met? Were any wants met?
Were all SMART objectives achieved?
Were all deliverables met?
Are the stakeholders happy with the results? Are team members happy?
If the project team realizes that an important deliverable has been missed, there are two options.
Return to the planning phase and create a plan for completing the missed tasks.
Choose to leave this item as unmet and create a separate project for it.
-------------------------------------
Estimated Time
5 minutes
Topic Objective
To understand how to verify that your project did what it set out to do.
Topic Summary
This checklist can be used as a guide for scope verification.
Were all needs met? Were any wants met?
Were all SMART objectives achieved?
Were all deliverables met?
Are the stakeholders happy with the results? Are team members happy?
Materials Required
List of workshop objectives
Planning Checklist
Have the workshop objectives available on PowerPoint or on flip chart paper.
Recommended Activity
Go through the list of objectives and see if we learned everything we set out to do. This is a type of scope verification.
Delivery Tips
If any items were not covered in sufficient depth, be prepared to offer alternate resources.
Review Questions
What should the team do if they realize they forgot to do something?

## Slide 153: A Final To-Do List
Dispose of or return materials
Ensure all payments have been made and paperwork submitted
Pass on appropriate project information
Notes: In addition to scope verification and lessons learned, the following tasks should also be completed during closeout:
Pass on appropriate project information (training documentation, blueprints, troubleshooting information, etc.) to the appropriate people.
Ensure all payments have been made and paperwork submitted.
Dispose of or return materials.
All project documents, both electronic and paper, should be completed and compiled. Make sure to include the original document, the final document, and any revised versions. Key documents include:
Statement of work
Project charter
Project planning worksheet
Project schedule and related documents
Risk management plan
Communication plan
Change management requests
Team member evaluations
Lessons learned
Meeting minutes
Status reports
-------------------------------------
Estimated Time
5 minutes
Topic Objective
To ensure participants understand what activities need to be completed before the project can be considered finished.
Topic Summary
In addition to scope verification and lessons learned, there are some additional tasks that should be completed during closeout.
Materials Required
Action plans
Planning Checklist
Print out one action plan per participant.
Recommended Activity
Ask participants to create their own to-do list for after the workshop.
Delivery Tips
If participants are familiar enough with each other, it can be useful to have participants choose a buddy for follow-up after the workshop. Or, participants can identify someone back at the workplace to help them achieve their goals.

## Slide 154: Module Eleven: Review Questions
As your project winds down, what may you find happening?
Team morale dropping
Anxiety increasing
Closing of the project becoming difficult
All of the above
Which of these is a helpful way to help co-workers get through the closing of a project?
Make sure they know what they will be working on after the project.
Pass on comments about their work performance to their co-workers.
Try not to discuss performance review as this will only increase the difficulty.
Encourage team members to go to their human resources department with questions.

## Slide 155: Module Eleven: Review Questions
After the project, what should you take time to celebrate?
The anxiety your co-workers are experiencing.
The things the project team did well.
The risks and issues that were not avoided.
The relief the end of the project brings.
What is an important part of project close-out?
Status updates and reports
Risk management planning
A team celebration
Quickly focusing on the next project

## Slide 156: Module Eleven: Review Questions
Which of these statements is true about learning from project challenges?
Some projects go perfectly, and it’s important to learn what went wrong to get it perfect next time.
No project goes perfectly. If it can happen, it probably will!
There are always risks that you didn’t anticipate, but there are never tasks that run longer than they should have.
The best projects do not have challenges.
Which of these is not a good reason why meeting with team members and stakeholders to identify lessons learned is a valuable experience?
Participants can apply these lessons to future projects and be more successful.
It ensures everyone is aware of the challenges encountered and what was done to resolve them.
Lessons learned should be kept between the project manager and his team.
If something is learned from a mistake or failed endeavor, then the effort put into the task is not entirely wasted.

## Slide 157: Module Eleven: Review Questions
At which point in the project do stakeholders and team members meet to determine whether or not the project did what it set out to do?
Risk management plan.
When learning from project challenges.
Scope verification.
Celebrating successes.
Which of these questions can be used as a guide for scope verification?
Who else should we involve in this? Who might be affected?
What is a step in creating a network diagram?
What do we want the project to accomplish?
Were all needs met? Were any wants met?

## Slide 158: Module Eleven: Review Questions
If the project team realizes that an important deliverable has been missed, what is a good option?
Return to the planning phase and create a plan for completing the missed tasks.
Choose to leave the item at met as it is the end of the project.
Do whatever is necessary to ensure that stakeholders are happy on the return of their investment.
Apply lessons learned to future projects in order to be successful.
Which of these tasks is not completed during closeout?
Dispose of or return materials.
Complete a change management form at the end of the project.
Ensure all payments have been made and paperwork submitted.
Pass on appropriate project information to the appropriate people.

## Slide 159: Module Eleven: Review Questions
As your project winds down, what may you find happening?
Team morale dropping
Anxiety increasing
Closing of the project becoming difficult
All of the above
Which of these is a helpful way to help co-workers get through the closing of a project?
Make sure they know what they will be working on after the project.
Pass on comments about their work performance to their co-workers.
Try not to discuss performance review as this will only increase the difficulty.
Encourage team members to go to their human resources department with questions.

## Slide 160: Module Eleven: Review Questions
After the project, what should you take time to celebrate?
The anxiety your co-workers are experiencing.
The things the project team did well.
The risks and issues that were not avoided.
The relief the end of the project brings.
What is an important part of project close-out?
Status updates and reports
Risk management planning
A team celebration
Quickly focusing on the next project

## Slide 161: Module Eleven: Review Questions
Which of these statements is true about learning from project challenges?
Some projects go perfectly, and it’s important to learn what went wrong to get it perfect next time.
No project goes perfectly. If it can happen, it probably will!
There are always risks that you didn’t anticipate, but there are never tasks that run longer than they should have.
The best projects do not have challenges.
Which of these is not a good reason why meeting with team members and stakeholders to identify lessons learned is a valuable experience?
Participants can apply these lessons to future projects and be more successful.
It ensures everyone is aware of the challenges encountered and what was done to resolve them.
Lessons learned should be kept between the project manager and his team.
If something is learned from a mistake or failed endeavor, then the effort put into the task is not entirely wasted.

## Slide 162: Module Eleven: Review Questions
At which point in the project do stakeholders and team members meet to determine whether or not the project did what it set out to do?
Risk management plan.
When learning from project challenges.
Scope verification.
Celebrating successes.
Which of these questions can be used as a guide for scope verification?
Who else should we involve in this? Who might be affected?
What is a step in creating a network diagram?
What do we want the project to accomplish?
Were all needs met? Were any wants met?

## Slide 163: Module Eleven: Review Questions
If the project team realizes that an important deliverable has been missed, what is a good option?
Return to the planning phase and create a plan for completing the missed tasks.
Choose to leave the item at met as it is the end of the project.
Do whatever is necessary to ensure that stakeholders are happy on the return of their investment.
Apply lessons learned to future projects in order to be successful.
Which of these tasks is not completed during closeout?
Dispose of or return materials.
Complete a change management form at the end of the project.
Ensure all payments have been made and paperwork submitted.
Pass on appropriate project information to the appropriate people.

## Slide 164: Module Twelve: Wrapping Up
This feeling, finally, that we may change things - this is at the centre of everything we are. Lose that... lose everything.
Sir David Hare
Although this workshop is coming to a close, we hope that your journey to improve your Project Management skills is just beginning. Please take a moment to review and update your action plan. This will be a key tool to guide your progress in the days, weeks, months, and years to come. We wish you the best of luck on the rest of your travels!
Notes: Although this workshop is coming to a close, we hope that your journey to improve your project management skills is just beginning. Please take a moment to review and update your action plan. This will be a key tool to guide your progress in the days, weeks, months, and years to come. We wish you the best of luck on the rest of your travels!

## Slide 165: Words from the Wise
Yogi Berra
  In theory there is no difference between theory and practice. In practice there is.
Dwight Eisenhower
  Plans are nothing; planning is everything.
Jonas Salk:
  The reward for work well done is the opportunity to do more.
Notes: Yogi Berra: In theory there is no difference between theory and practice. In practice there is.
Dwight Eisenhower: Plans are nothing; planning is everything.
Jonas Salk: The reward for work well done is the opportunity to do more.

## Slide 166: Conclusion
Recap and Reflection Wrap-up
ISD to Update
Notes: Slide Time: :30
SAY
Remember the handout which is available to remind you of some of things we spoke about and discussed together today.
In this session we covered how to:
Identify the self and different aspects of the self: the physical, emotional, mental, and spiritual.
Learn from introspection and the nature and value of emotions
Learn how to appreciate yourself and others to improve effectiveness and
Gain insight of limitations of self-awareness
Transition: Click next slide.

## Slide 167: What of your original response would have changed if you knew the insights provided today?
Revisiting Your Responses
BECAME ANGRY
BECAME STRESSED OUT
FOCUSED ON SOMETHING ELSE
REDIRECED THOUGHTS / ACTIONS
FELT OR GOT SICK
IGNORED IT
ISD to Update
Think of a recent situation where you felt anxious, frustrated, disappointed, or any other unpleasant emotion.
How did you address it?
Next Steps in Success
Apply What You’ve Learned
Your next step is to complete the On-the-Job section of the XXXX Career Development topic.
Notes: Slide Time: 3:00
FACILITATOR NOTEs & Tips For Slide
Call on participants and discuss their answers. Start a verbal dialog. Don’t forget to check/repeat some of the responses provided in chat.
Use participant names and thank them for responding and sharing.
Remind participants of the workshop hand out provided earlier in today’s session. Provide WebEx File for those that request it because they came in late.
Use the handout to conduct a brief review of the session.
SAY
Remember this question at the beginning of our session?
ASK
What of your original answer would have changed if you knew the insights provided today?
USE THE HAND RAISE ICON or USE THE CHAT BOX TO share your ANSWER.
ASK
Which area will you reflect on and why?
USE THE CHAT BOX TO PROVIDE YOUR ANSWER.
FACILITATOR NOTEs: Remember to clear icons before moving on.
Transition: Click next slide.

## Slide 168: Survey
Learn – Apply – Practice – Evaluate
Which insights of leadership and influence from today’s session will you apply immediately?
ISD to Update
Thank you!
[Time: 1/2 minute]
Instructions: Thank participants for their time and active participation.
Notes: Slide Time: Till the close of workshop
FACILITATOR NOTEs & Tips For Slide
Provide Survey Link in the Chat box.
Call on participants and discuss their answers. Start a verbal dialog. Don’t forget to check/repeat some of the responses provided in chat.
Use participant names and thank them for responding and sharing.
Please remain in the training room until most participants have left the session.
FACILITATOR/PRODUCER NOTES: REQUEST #3: please capture information discussion points.
SAY
I am providing you at this time a brief survey, and will place the link in the Chat window. Please click on it and provide your learning experience with us!
ASK
Let me ask you while some of you have completed the survey, which insights of from today’s session will you apply immediately and why?
Feel free to USE THE HAND RAISE ICON or USE THE CHAT BOX TO share your ANSWER.
SAY
We covered a lot today and encourage you to take what YOU learned today and challenge you to apply and practice this information.
I want to thank you for attending the Leadership and Influence workshop!
I hope you enjoyed todays session and look forward to seeing many of you again in our other workshops!
Have a wonderful rest of the day!

## Slide 169: Recap and Reflect
ISD to Update
Notes: Slide Time: 2:00
FACILITATOR NOTEs & Tips For Slide
Call on participants and discuss their answers. Start a verbal dialog. Don’t forget to check/repeat some of the responses provided in chat.
Use participant names and thank them for responding and sharing.
Remind participants of the workshop hand out provided earlier in today’s session. Provide WebEx File for those that request it because they came in late.
Use the handout to conduct a brief review of the session.
SAY
Remember the handout which is available to remind you of some of things we spoke about and discussed together today.
In this session we covered how to:
Identify the self and different aspects of the self: the physical, emotional, mental, and spiritual.
Learn from introspection and the nature and value of emotions
Learn how to appreciate yourself and others to improve effectiveness and
Gain insight of limitations of self-awareness
ASK
Which area will you reflect on and why?
USE THE CHAT BOX TO PROVIDE YOUR ANSWER.
FACILITATOR NOTEs: Remember to clear icons before moving on.
Transition: Click next slide.

## Slide 170: Revisiting Your Answer
Think of a recent situation where you felt anxious, frustrated, disappointed, or any other unpleasant emotion.
How did you address it?
BECAME ANGRY
BECAME STRESSED OUT
FOCUSED ON SOMETHING ELSE
REDIRECED THOUGHTS / ACTIONS
FELT OR GOT SICK
What of your original answer would have changed if you knew the insights provided today?
IGNORED IT
Facilitator/Producer Notes: REQUEST #2.
THIS SLIDE: Capture discussion notes of what people are saying/typing for the reason why & expectation they are taking the course.
Email all request from this training session to learn@aim2train.com after course delivery with the following:
EMAIL SUBECT LINE: FEEDBACK – COURSE NAME
IN BODY OF EMAIL:
The Course Name:
Class Date & Time Delivered:
Your Name (Facilitator):
Request #: The discussion answers to the question(s):
Request #: The discussion answers to the question(s):
Request #: The discussion answers to the question(s):
ISD to Update
Notes: Slide Time: 3:00
FACILITATOR NOTEs & Tips For Slide
Call on participants and discuss their answers. Start a verbal dialog. Don’t forget to check/repeat some of the responses provided in chat.
Use participant names and thank them for responding and sharing.
FACILITATOR/PRODUCER NOTES: REQUEST #2: please capture information discussion points.
SAY
Remember this question at the beginning of our session?
ASK
What of your original answer would have changed if you knew the insights provided today?
USE THE HAND RAISE ICON or USE THE CHAT BOX TO share your ANSWER.
FACILITATOR NOTEs: Remember to clear icons before moving on.
Transition: Click next slide.

## Slide 171
Learn – Apply – Practice – Evaluate
Which insights of leadership and influence from today’s session will you apply immediately?
Facilitator/Producer Notes: REQUEST #3.
Email all request from this training session to learn@aim2train.com after course delivery with the following:
EMAIL SUBECT LINE: FEEDBACK – COURSE NAME
IN BODY OF EMAIL:
The Course Name:
Class Date & Time Delivered:
Your Name (Facilitator):
Request #: The discussion answers to the question(s):
Request #: The discussion answers to the question(s):
Request #: The discussion answers to the question(s):
ISD to Update
Update Image
Notes: Slide Time: Till the close of workshop
FACILITATOR NOTEs & Tips For Slide
Provide Survey Link in the Chat box.
Call on participants and discuss their answers. Start a verbal dialog. Don’t forget to check/repeat some of the responses provided in chat.
Use participant names and thank them for responding and sharing.
Please remain in the training room until most participants have left the session.
FACILITATOR/PRODUCER NOTES: REQUEST #3: please capture information discussion points.
SAY
I am providing you at this time a brief survey, and will place the link in the Chat window. Please click on it and provide your learning experience with us!
ASK
Let me ask you while some of you have completed the survey, which insights of from today’s session will you apply immediately and why?
Feel free to USE THE HAND RAISE ICON or USE THE CHAT BOX TO share your ANSWER.
SAY
We covered a lot today and encourage you to take what YOU learned today and challenge you to apply and practice this information.
I want to thank you for attending the Leadership and Influence workshop!
I hope you enjoyed todays session and look forward to seeing many of you again in our other workshops!
Have a wonderful rest of the day!