## Slide 1
Project Management
Corporate Training Materials

## Slide 2: Module One: Getting Started
In the past few decades, organizations have discovered something incredible: principles that have been used to create enormous successes in large projects can be applied to projects of any size to create amazing success. As a result, many employees are expected to understand project management techniques and how to apply them to projects of any size.
It must be considered that there is nothing more difficult to carry out nor more doubtful of success nor more dangerous to handle than to initiate a new order of things.
Machiavelli
Notes: Welcome to the Project Management workshop. In the past few decades, organizations have discovered something incredible: principles that have been used to create enormous successes in large projects can be applied to projects of any size to create amazing success. As a result, many employees are expected to understand project management techniques and how to apply them to projects of any size.
This workshop will give participants an overview of the entire project management process, as well as key project management tools that they can use every day.

## Slide 3: Workshop Objectives
Define projects
Project needs assessment
Project schedule
Planning tools
Notes: • Define projects, project management, and project managers
• Identify the importance of the PMBOK and PMI
• Identify the five process groups and nine knowledge areas as defined by the PMI
• Describe the triple constraint
• Perform a project needs assessment and write goals, requirements, and deliverables
• Create key project documents, including the statement of work, project planning worksheet, and project charter
• Build a project schedule by estimating time, costs, and resources
• Understand and use the work breakdown structure
• Create project planning documents, such as a schedule, risk management plan, and communication plan
• Use planning tools, including the Gantt chart, network diagram, and RACI chart
• Establish and use baselines
• Monitor and maintain the project
• Perform basic management tasks, including leading status meetings and ensuring all documents are complete at the end of the project

## Slide 4: Module Two: Key Concepts (I)
Before we get started, let’s make sure we all understand just what we mean by a project and by project management. We’ll also look at what a project manager’s role is.
Do not repeat the tactics which have gained you one victory, but let your methods be regulated by the infinite variety of circumstances.
Sun Tzu
Notes: Before we get started, let’s make sure we all understand just what we mean by a project and by project management. We’ll also look at what a project manager’s role is.

## Slide 5: What is a Project?
Limited endeavor
Start and end date
Clear goals
Defined responsibility
Notes: A project is a limited endeavor (meaning it has specific start and finish dates) that is undertaken to meet particular goals and objectives. Projects are different than processes or everyday operations, which are repetitive, permanent, or semi-permanent functional work taken on to produce products or services.
All successful projects share the following characteristics:
Clear goals
Defined ownership/responsibility
Timeline
Dedicated team
Defined methodology
Controlled execution
Completion evaluated based on original plan
Linked to business objectives
Supported by an organization’s management team

## Slide 6: What is a Project Management?
Planning and organizing
Managing resources
Within budget
Notes: Project management is the combined art and science of planning, organizing, and managing resources to get a particular project done on time, within budget, and with the results that the organization set out to achieve.
There are many types of project management designed for different scenarios and different industries. This workshop will focus on the traditional method, used by the Project Management Institute, which follows five process groups. (See Module Three for more information.)

## Slide 7: What is Project Manager?
Responsible and accountable
Setting objectives
Balance wants and needs
Notes: A project manager is the person responsible and accountable for accomplishing the stated project objectives. Key project management responsibilities include creating clear and attainable project objectives, building the project requirements, and managing the triple constraint for projects.
The project manager is often required to perform a juggling act, balancing what the customer wants, and needs with what the team can provide in a particular time frame and with a particular budget. A successful project manager has a hodgepodge of skills and continues learning.
Key skills include:
• Leadership
• Negotiation
• Influence and persuasion
• Project management
• Communication
• Time management
• Stress and anger management
Although you do need project management skills to be a project manager, you don’t need to be a project manager to use project management skills. You will find uses for most of the tools that we discuss today in your day-to-day life, both personal and professional.

## Slide 8: Module Two: Review Questions
What is the definition of a project?
A planned series of future events, items, or performances.
A meeting of people face to face, especially for consultation.
A limited endeavor that is undertaken to meet particular goals and objectives.
An assembly of people, especially the members of a society or committee, for discussion or entertainment.
What is an example of a characteristic of a successful project?
Defined ownership and responsibility
Vague goals
A timeline that changes frequently
Methodology that is “plan-as-you-go”

## Slide 9: Module Two: Review Questions
What is not an example of a characteristic of a successful project?
Ambiguous communication
Dedicated team
Completion evaluated based on original plan
Supported by an organization’s management team
What can be defined as “the combined art and science of planning, organizing, and managing resources to get a particular project done on time, within budget, and with the results that the organization set out to achieve”?
Meeting planning
Project planning
Office management
Project management

## Slide 10: Module Two: Review Questions
Which of these statements is true of project management?
Project management involves repetitive, permanent, or semi-permanent functional activities to produce products or services.
Project management is just like meeting management, involving a chairperson, minute taker, and attendee participation.
There are many types of project management designed for different scenarios and different industries.
There is only one trusted method for project management, and that method is the traditional method.
What is the definition of a project manager?
The profession involving office supervisory positions.
The person responsible and accountable for accomplishing the stated project objectives.
The person ultimately responsible for the day-to-day operations or an organization.
The person who presides over a meeting, committee, or board.

## Slide 11: Module Two: Review Questions
What is not an example of a key project management responsibility?
Organizing the office before the project begins
Deconstructing the project requirements
Managing the triple constraint for projects
All of the above
What job is the project manager often required to do?
Balancing what the customer wants, and needs with what the team can provide in a particular time frame and with a particular budget.
Focusing on consistent and permanent projects that the company needs on a rolling basis.
Giving a brief explanation of the purpose of the meeting and an idea of what you are looking for in terms of topics.
Maintains focus while writing down information during the project’s many meetings.

## Slide 12: Module Two: Review Questions
Which of these is not a key skill of a project manager?
Excellent at taking orders from the team
Negotiation
Leadership
Stress and anger management
Which of these statement is true of project management?
A successful project manager has a basic skill set and is focused on application of these skills, not on learning new ones.
A project manager is the person who delegates responsibility for accomplishing the stated project objectives.
There is only one type of project management, designed for specific scenarios and specific industries.
One can find uses for most of the project management tools that are discussed in day-to-day life, both personal and professional.

## Slide 13: Module Two: Review Questions
What is the definition of a project?
A planned series of future events, items, or performances.
A meeting of people face to face, especially for consultation.
A limited endeavor that is undertaken to meet particular goals and objectives.
An assembly of people, especially the members of a society or committee, for discussion or entertainment.
What is an example of a characteristic of a successful project?
Defined ownership and responsibility
Vague goals
A timeline that changes frequently
Methodology that is “plan-as-you-go”

## Slide 14: Module Two: Review Questions
What is not an example of a characteristic of a successful project?
Ambiguous communication
Dedicated team
Completion evaluated based on original plan
Supported by an organization’s management team
What can be defined as “the combined art and science of planning, organizing, and managing resources to get a particular project done on time, within budget, and with the results that the organization set out to achieve”?
Meeting planning
Project planning
Office management
Project management

## Slide 15: Module Two: Review Questions
Which of these statements is true of project management?
Project management involves repetitive, permanent, or semi-permanent functional activities to produce products or services.
Project management is just like meeting management, involving a chairperson, minute taker, and attendee participation.
There are many types of project management designed for different scenarios and different industries.
There is only one trusted method for project management, and that method is the traditional method.
What is the definition of a project manager?
The profession involving office supervisory positions.
The person responsible and accountable for accomplishing the stated project objectives.
The person ultimately responsible for the day-to-day operations or an organization.
The person who presides over a meeting, committee, or board.

## Slide 16: Module Two: Review Questions
What is not an example of a key project management responsibility?
Organizing the office before the project begins
Deconstructing the project requirements
Managing the triple constraint for projects
All of the above
What job is the project manager often required to do?
Balancing what the customer wants, and needs with what the team can provide in a particular time frame and with a particular budget.
Focusing on consistent and permanent projects that the company needs on a rolling basis.
Giving a brief explanation of the purpose of the meeting and an idea of what you are looking for in terms of topics.
Maintains focus while writing down information during the project’s many meetings.

## Slide 17: Module Two: Review Questions
Which of these is not a key skill of a project manager?
Excellent at taking orders from the team
Negotiation
Leadership
Stress and anger management
Which of these statement is true of project management?
A successful project manager has a basic skill set and is focused on application of these skills, not on learning new ones.
A project manager is the person who delegates responsibility for accomplishing the stated project objectives.
There is only one type of project management, designed for specific scenarios and specific industries.
One can find uses for most of the project management tools that are discussed in day-to-day life, both personal and professional.

## Slide 18: Module Three: Key Concepts (II)
This module will look at the Project
Management Institute, a global project
management group that publishes and
promotes project management
standards, and its core ideas.
Life is a do-it-yourself project.
Napoleon Hill
Notes: Now that we understand what we mean by projects, project management, and project managers, let’s look at some of the other concepts related to projects. This module will look at the Project Management Institute, a global project management group that publishes and promotes project management standards, and its core ideas.

## Slide 19: The Project Management Institute (PMI)
PMBOK
Project management standards
Techniques
Notes: The Project Management Institute is a global association for the project management profession. Since being founded in 1969, they have been at the forefront of working with businesses to create project management standards and techniques that work.
Their core ideas include:
The Project Management Body of Knowledge( PMBOK), which we will discuss in a moment
Five process groups, which outline the path a project should take
Nine knowledge areas, which outline various parts of each process group
The triple constraint, which illustrates how a project is balanced

## Slide 20: The Project Management Body Of Knowledge (PMBOK)
Processes and knowledge
Best practices
Standards
Notes: The Project Management Body of Knowledge (PMBOK) is the PMI bible. It includes a detailed overview of the processes and knowledge areas promoted by the PMI as best practice within the project management discipline.
This global standard allows consistent procedures, methods, and processes to be applied to any project and measured equally, no matter what the actual project is about.
The guide is built around five process groups and ten knowledge areas.

## Slide 21: The Five Process Groups
Initiating
Monitoring and Controlling
Closing
Planning
Executing
Notes: These processes form the core structure of any project. Although they are illustrated here as a continuous process, they can overlap and interact throughout a project.
Processes are described in terms of:
Inputs (documents, plans, designs, etc.)
Tools and Techniques (mechanisms applied to inputs)
Outputs (documents, products, etc.)

## Slide 22: The Ten Knowledge Areas
Integration
Procurement
Scope
Risk
Time
Quality and Stakeholder
Communications
Cost
Human Resources
Notes: The PMBOK guide focuses on ten knowledge areas that are crucial to the project management processes. The areas are:
Integration Management
Procurement Management
Scope Management
Risk Management
Time Management
Communications Management
Cost Management
Human Resources Management
Quality Management
Stakeholder Management
Each knowledge area contains some or all of the project management processes. For example, Project Procurement Management includes:
Plan Procurement Management
Conduct Procurements
Control Procurements
Close Procurements

## Slide 23: The Triple Constraint
Schedule
(Time)
Scope
Quality
Customer Satisfaction
Budget (Cost)
Resources
Risk
Notes: The Triple Constraint illustrates the balance of the project’s scope, schedule (time), and budget (cost). During the planning phase of a project, the project management team defines the project scope, schedule (time), and budget (cost)of a project. As the process continues, the project managers discover that there may be changes or adjustments to be made in one of these areas. When this happens, the other factors of the triple constraint are likely to be affected as well.
For example, if the budget (cost) increases, it is logical to assume that the scope and schedule (time) will increase as well. The same thing happens if the budget (cost) decreases; the scope and schedule (time) will decrease too.
It is the job of the project manager, and sometimes the project team, to identify how a change to a single element will change the other elements.

## Slide 24: Module Three: Review Questions
What is the Global Project Institute?
The process of international integration arising from the interchange of world views, products, ideas, and other aspects of culture.
A global association for the project management profession.
The combined art and science of planning, organizing, and managing resources to get a particular project done on time, within budget, and with the results that the organization set out to achieve.
A society or organization having a particular object or common factor, especially a scientific, educational, or social one.
What is included in the Global Project Institute’s core ideas?
The Project Management Body of Management ( PMBOM).
Five process groups, which outline the path a project should take.
Seven knowledge areas, which outline various parts of each process group.
The double constraint, which illustrates how a project is balanced.

## Slide 25: Module Three: Review Questions
Which of these forms the core structure of any project?
The Five Process Groups
The Five Management Groups
The Four Process Groups
The Four Management Groups
Which of these is a term that could describe the processes?
Means
Products
Amounts
Inputs

## Slide 26: Module Three: Review Questions
How many knowledge areas are crucial to the project management processes?
Thirteen
Ten
Nine
Three
What is not a knowledge area the PMBOK focuses on?
Integration
Settlement
Scope
Procurement

## Slide 27: Module Three: Review Questions
Which of these does Project Procurement Management include?
Elements
Predictions
Human Resources
Contract Administration
What illustrates the balance of the project’s scope, schedule (time), quality, and cost?
The triple constraint
The double constraint
Solicitation Planning
Procurement Planning

## Slide 28: Module Three: Review Questions
During the planning phase of a project, who defines the scope, time, cost, and quality?
Human resources
Solicitation team
Planning resources
Project Management Team
What is the job of the project manager?
To take on long term, permanent projects that are managed on an ongoing basis.
To balance day-to-day office management with project planning.
To identify how a change to a single element will change the other elements.
To procure funds for the projects that are being managed.

## Slide 29: Module Three: Review Questions
What is the Global Project Institute?
The process of international integration arising from the interchange of world views, products, ideas, and other aspects of culture.
A global association for the project management profession.
The combined art and science of planning, organizing, and managing resources to get a particular project done on time, within budget, and with the results that the organization set out to achieve.
A society or organization having a particular object or common factor, especially a scientific, educational, or social one.
What is included in the Global Project Institute’s core ideas?
The Project Management Body of Management ( PMBOM).
Five process groups, which outline the path a project should take.
Seven knowledge areas, which outline various parts of each process group.
The double constraint, which illustrates how a project is balanced.

## Slide 30: Module Three: Review Questions
Which of these forms the core structure of any project?
The Five Process Groups
The Five Management Groups
The Four Process Groups
The Four Management Groups
Which of these is a term that could describe the processes?
Means
Products
Amounts
Inputs

## Slide 31: Module Three: Review Questions
How many knowledge areas are crucial to the project management processes?
Thirteen
Ten
Nine
Three
What is not a knowledge area the PMBOK focuses on?
Integration
Settlement
Scope
Procurement

## Slide 32: Module Three: Review Questions
Which of these does Project Procurement Management include?
Elements
Predictions
Human Resources
Contract Administration
What illustrates the balance of the project’s scope, schedule (time), quality, and cost?
The triple constraint
The double constraint
Solicitation Planning
Procurement Planning

## Slide 33: Module Three: Review Questions
During the planning phase of a project, who defines the scope, time, cost, and quality?
Human resources
Solicitation team
Planning resources
Project Management Team
What is the job of the project manager?
To take on long term, permanent projects that are managed on an ongoing basis.
To balance day-to-day office management with project planning.
To identify how a change to a single element will change the other elements.
To procure funds for the projects that are being managed.

## Slide 34: Module Four: Initiation (I)
The first phase of project management
is initiation.
This module will explore the first part
of that process: identifying what
success will look like for your particular
project.
No sensible decision can be made without taking into account not only the world as it is, but the world as it will be.
Isaac Asimov
Notes: The first phase of project management is initiation. This is where the project starts to take shape. Stakeholders and team member’s work together to identify wants and needs, and then the project team creates a plan to accomplish the objectives with the time and budget available. This module will explore the first part of that process: identifying what success will look like for your particular project.

## Slide 35: Identifying Your Stakeholders
Has an interest
Feedback
Guidance
Who might be affected?
Notes: A stakeholder is someone who has an interest in the development and/or outcome in the project. This person is usually only involved at key project gateways, such as project initiation and evaluation. Their main role is to provide feedback and guidance.
When you are identifying stakeholders, think outside the box. Ask other members of the team and the organization, “Who else should we involve in this? Who might be affected?”
If it turns out you missed a stakeholder, ask them for their feedback. You may not be able to change the project’s course at that point, but you may receive valuable information on possible opportunities or potential issues.

## Slide 36: Assessing Needs and Wants
Decide which items are necessary (needs)
“nice to haves” (wants)
Prioritize the needs
Notes: When stakeholders and other project members begin identifying the goals of the project, encourage them to list any and all possibilities. If the sky is the limit, what would they want the project to accomplish?
Then, they should decide which items are necessary for the project’s success (needs), and which are “nice to haves” (wants). If the list is lengthy, wants and needs can be prioritized to help the project team identify the most important tasks. (Remember, this is not a final list, just brainstorming to kick things off.)
To wow your stakeholders, keep this list on hand during the project. Keep an eye out for ways to incorporate wants and maximize their value.

## Slide 37: Setting a SMART Project Goal
Specific
Measurable
Relevant
Timed
Agreed Upon
Notes: Each project should have a goal statement. SMART is a convenient acronym for the set of criteria that a goal must have in order for it to be realized by the goal achiever.
• Specific: In order for the project team to achieve a goal, stakeholders must be very clear about what they want. As Jack Canfield says, “Vague goals produce vague results.”
• Measurable: It’s crucial that you are able to track your progress towards your goal. That’s why all goals need some form of objective measuring system so that you can stay on track and become motivated when you enjoy the sweet taste of quantifiable progress.
• Agreed Upon: All team members and stakeholders must agree on the goal.
• Relevant: The goal must be relevant to the business’ purpose.
• Timed: In order for a project to be considered a project, it must have a specific start and end date.
Some examples of good project goals:
• To upgrade the existing sales system to EasySell 5.1 by January 1, 2015.
• To begin production of a new widget by September 1, 2016.
• To build a new 5,000 square foot office facility and have all staff relocated to it by December 31, 2015.

## Slide 38: Creating Requirements and Deliverables
What a project must do in order for it to be considered successful
Define what people can expect to hold in their hands after the project is complete
Notes: Now that we have some idea of what we want our project to accomplish, we can begin setting requirements. Requirements outline exactly what a project must do in order for it to be considered successful. Remember, good requirements are highly specific. Although they are particularly useful in IT projects, they should be used for any project that you want to succeed.
For example, let’s say one goal for our project is this: “To reduce the time to process inbound orders to 15 minutes by January 1, 2015.” A corresponding project requirement could be, “Implement version 5.0 of Superior Records Processing on all 14 customer service representative stations.”
As part of this, you should then be able to create your deliverables. These define what people can expect to hold in their hands after the project is complete. These deliverables will help you set clear expectations at the beginning of your project, and maintain a clear idea of what you are doing as you execute the project.

## Slide 39: Module Four: Review Questions
What is the first phase of project management?
Foundation
Prophase
Initiation
Induction
What is the definition of a stakeholder?
The supervisor who must take responsibility for and is accountable for the success or failure of their particular operation.
Someone who has an interest in the development and/or outcome in the project.
Someone who competes against or fights another in a contest, game, or argument; a rival or adversary.
A person who supervises a person or an activity.

## Slide 40: Module Four: Review Questions
If it turns out that you missed a stakeholder, why should you ask them for their feedback?
You may receive valuable information on possible opportunities or potential issues.
You will be able to change the project’s course at that point.
You will be able to initiate other projects in the future with this person.
You will save the company on time and cost.
When stakeholders and other project members begin identifying the goals of the project, what is the first step should you take?
Work on creating your deliverables.
Get all team members and stakeholders to agree on the goals.
Assemble an outside team to list any and all possibilities.
Encourage them to list any and all possibilities.

## Slide 41: Module Four: Review Questions
What does the “M” in the SMART acronym stand for?
Meaningful
Measurable
Money-making
Matter-of-fact
According to Jack Canfield, what do vague goals produce?
Specific goals
Clear planning
Vague results
Vague stakeholders

## Slide 42: Module Four: Review Questions
In order for a project to be considered a project what does it need?
A transitory name and title
Extra funding to prepare for possible emergencies
A specific start and end date
A vague purpose and results
What is not an example of a good project goal?
To upgrade the existing sales system to EasySell 5.1 by January 1, 2010.
To begin production of a new widget by September 1, 2011.
To build a new 5,000 square foot office facility and have all staff relocated to it by December 31, 2010.
To design a new data entry system to a future buyer at a time to be determined.

## Slide 43: Module Four: Review Questions
Which of these statements is true about setting requirements?
Requirements outline exactly what a project must do in order for it to be considered successful.
Good requirements are at least somewhat specific.
They should not be used for just any project, but are particularly useful in IT projects.
When it comes to requirements it is best to be vague in order to not miss important deadlines.
Which of these describes deliverable?
They define what people can expect to hold in their hands after the project is complete.
They define the goals set by the project management team.
They help you set clear expectations at the end of your project.
They maintain a clear idea of what the stakeholders should be executing.

## Slide 44: Module Four: Review Questions
What is the first phase of project management?
Foundation
Prophase
Initiation
Induction
What is the definition of a stakeholder?
The supervisor who must take responsibility for and is accountable for the success or failure of their particular operation.
Someone who has an interest in the development and/or outcome in the project.
Someone who competes against or fights another in a contest, game, or argument; a rival or adversary.
A person who supervises a person or an activity.

## Slide 45: Module Four: Review Questions
If it turns out that you missed a stakeholder, why should you ask them for their feedback?
You may receive valuable information on possible opportunities or potential issues.
You will be able to change the project’s course at that point.
You will be able to initiate other projects in the future with this person.
You will save the company on time and cost.
When stakeholders and other project members begin identifying the goals of the project, what is the first step should you take?
Work on creating your deliverables.
Get all team members and stakeholders to agree on the goals.
Assemble an outside team to list any and all possibilities.
Encourage them to list any and all possibilities.

## Slide 46: Module Four: Review Questions
What does the “M” in the SMART acronym stand for?
Meaningful
Measurable
Money-making
Matter-of-fact
According to Jack Canfield, what do vague goals produce?
Specific goals
Clear planning
Vague results
Vague stakeholders

## Slide 47: Module Four: Review Questions
In order for a project to be considered a project what does it need?
A transitory name and title
Extra funding to prepare for possible emergencies
A specific start and end date
A vague purpose and results
What is not an example of a good project goal?
To upgrade the existing sales system to EasySell 5.1 by January 1, 2010.
To begin production of a new widget by September 1, 2011.
To build a new 5,000 square foot office facility and have all staff relocated to it by December 31, 2010.
To design a new data entry system to a future buyer at a time to be determined.

## Slide 48: Module Four: Review Questions
Which of these statements is true about setting requirements?
Requirements outline exactly what a project must do in order for it to be considered successful.
Good requirements are at least somewhat specific.
They should not be used for just any project, but are particularly useful in IT projects.
When it comes to requirements it is best to be vague in order to not miss important deadlines.
Which of these describes deliverable?
They define what people can expect to hold in their hands after the project is complete.
They define the goals set by the project management team.
They help you set clear expectations at the end of your project.
They maintain a clear idea of what the stakeholders should be executing.

## Slide 49: Module Five: Initiation (II)
This module will look at four key
project documents: the statement of
work, the project requirements
document, the project planning
worksheet, and the project charter.
All you need is the plan, the road map, and the courage to press on to your destination.
Earl Nightingale
Notes: Once you have an idea of who your stakeholders are and what the project will achieve, it’s time to put it all in writing. This module will look at four key project documents: the statement of work, the project requirements document, the project planning worksheet, and the project charter.

## Slide 50: Creating a Statement of Work
Defines what the project will do
When it will be done
Contract of expectations
Notes: What is the Statement of Work? The SOW defines what the project will do and when it will be done. It forms a binding contract of expectations between all project stakeholders. As such, it should be created by the project team, and then signed off by the team and the stakeholders. It can be used to create other project documents, including the project charter. The Statement of Work often varies widely between organizations. However, the following basic elements should be included.
Project Team: Include all members of the project team and each person’s role, as well as a list of stakeholders and the sponsor.
Project Details: Include the name of the project, its estimated start and end date, and the client(s) involved. (Every project should have a client, whether it is an internal or external customer.)
Purpose: What is the purpose of the project? Try to keep this as simple and concrete as possible. If a business case or a cost-benefit analysis has been prepared, those documents should be referenced (but not included) here.
Scope: What will the project encompass? What items will the project not encompass? This section is extremely important as it will help avoid miscommunication and disappointment down the road.
Goals, Deliverables, and Requirements: Include your SMART goals, deliverables, and requirements here.
Basic Finances: List applicable rate and payment schedule information.
Assumptions: List any assumptions that have been made in the planning thus far.
Agreements: List any agreements that will apply to this project, such as union contracts or professional service agreements.

## Slide 51: Completing the Project Planning Worksheet
Project Planning Worksheet |  | 
Part I: Basic Information |  | 
Project Name: |  | Project Team Members:
Estimated Project Start Date: |  | 
Estimated Project End Date: |  | 
Budget Amount (if known): |  | 
Part II: Project Goals |  | 
List your SMART goals here. |  | 
Part III: Milestones |  | 
Milestone | Target Completion Date | 
Approved by: |  | 
Notes: Once the basics of the project are laid out, it’s time to put together your project planning worksheet. While the Statement of Work will remain static throughout the project, your worksheet will be a living, breathing document. As such, there are parts that you will not complete until after the Planning phase, but this worksheet will give you one place to capture the essential information about your project.
Like the SOW, you may need different fields based on your project and your organization, but we have included a sample worksheet below.

## Slide 52: Completing the Project Charter
Formal project document
Establishes the project as an entity
Customized for your organization
Notes: The project charter is the final, formal project document. It establishes the project as an entity and it gives the project manager the authority to get started. For small projects, the charter may be just a few pages. For large projects, the charter itself can be hundreds of pages and can take months to build.
Just like other project documents, the charter can be customized for your organization. At a minimum, it should include the following information:
Project name
Project due date
Team list, including responsibility matrix
Stakeholders
In scope and out of scope items
Goals
Requirements
Deliverables
Estimated cost vs. budget
Benefits of project (including cost-benefit analysis if appropriate)
Milestone descriptions and dates
Possible risks and opportunities
Communication plans
Assumptions and Constraints
Plans for documenting lessons learned
A page for sign off by the important parties
Ask your organization if they have a charter form that they would like you to use. This is especially important as a charter can be a legally binding document.

## Slide 53: Module Five: Review Questions
Once you have an idea of who your stakeholders are and what the project will achieve, what is the next step?
Achieve the deliverables
Assemble your project management team
Put it all in writing
End the project
What is the statement of work?
The SOW is a basis report on three types of financial activities: operating activities, investing activities, and financing activities.
The SOW is a statement which stakeholders create for the project management team.
The SOW defines the vague overall meaning of the work and is also specific enough that it conveys your unique interpretation.
The SOW defines what the project will do and when it will be done.

## Slide 54: Module Five: Review Questions
Who signs off on the statement of work?
The project management team
The stakeholders
Human resources and upper management
Both a & b
Which of these is not included in the project details?
Name of the project
The products needed
Its estimated state and end date
The client(s) involved

## Slide 55: Module Five: Review Questions
What question does ‘scope’ answer in the statement of work?
What will the project encompass?
What are our deliverables, goals, and requirements?
What is the purpose of the project?
Who is on the project management team?
Which of these statements is true of the project planning worksheet?
It remains static throughout the project.
It is a living, breathing document.
It is never complete.
It gives you several places to capture the essential information about your project.

## Slide 56: Module Five: Review Questions
How is the project planning worksheet similar to the statement of work?
They are both produced by the stakeholders.
They both must be signed off on by a number of supervisors.
In both, you may need different fields based on your project.
In both, you may need to be vague for the betterment of the project.
What is the final, formal project document?
The project planning worksheet
The project planning team
The project charter
The statement of work

## Slide 57: Module Five: Review Questions
How long should the project charter be?
It varies from a few pages to hundreds.
It varies from ten to fifteen pages.
It varies from one hundred to five hundred pages.
It is varies, but is never over one hundred pages.
Which of these would not be included in the project charter?
Estimated cost vs. budget
In house and out of house items.
Milestone descriptions and dates.
Communication plans.

## Slide 58: Module Five: Review Questions
Once you have an idea of who your stakeholders are and what the project will achieve, what is the next step?
Achieve the deliverables
Assemble your project management team
Put it all in writing
End the project
What is the statement of work?
The SOW is a basis report on three types of financial activities: operating activities, investing activities, and financing activities.
The SOW is a statement which stakeholders create for the project management team.
The SOW defines the vague overall meaning of the work and is also specific enough that it conveys your unique interpretation.
The SOW defines what the project will do and when it will be done.

## Slide 59: Module Five: Review Questions
Who signs off on the statement of work?
The project management team
The stakeholders
Human resources and upper management
Both a & b
Which of these is not included in the project details?
Name of the project
The products needed
Its estimated state and end date
The client(s) involved

## Slide 60: Module Five: Review Questions
What question does ‘scope’ answer in the statement of work?
What will the project encompass?
What are our deliverables, goals, and requirements?
What is the purpose of the project?
Who is on the project management team?
Which of these statements is true of the project planning worksheet?
It remains static throughout the project.
It is a living, breathing document.
It is never complete.
It gives you several places to capture the essential information about your project.

## Slide 61: Module Five: Review Questions
How is the project planning worksheet similar to the statement of work?
They are both produced by the stakeholders.
They both must be signed off on by a number of supervisors.
In both, you may need different fields based on your project.
In both, you may need to be vague for the betterment of the project.
What is the final, formal project document?
The project planning worksheet
The project planning team
The project charter
The statement of work

## Slide 62: Module Five: Review Questions
How long should the project charter be?
It varies from a few pages to hundreds.
It varies from ten to fifteen pages.
It varies from one hundred to five hundred pages.
It is varies, but is never over one hundred pages.
Which of these would not be included in the project charter?
Estimated cost vs. budget
In house and out of house items.
Milestone descriptions and dates.
Communication plans.

## Slide 63: Module Six: Planning (I)
Now it’s time to plan the nuts and bolts
of your project.
When building your plan, remember:
Everything in the plan is a prediction.
The only fact that you know for certain is that your plan is definitely not 100% right.
Contingency needs to be built in to cope with the uncertainty.
Those who fail to plan, plan to fail.
Anonymous
Notes: Congratulations! With the completion of the SOW, planning worksheet, and project charter, the initiation phase is complete. Now it’s time to plan the nuts and bolts of your project.
When building your plan, remember:
• Everything in the plan is a prediction.
• The only fact that you know for certain is that your plan is definitely not 100% right.
• Contingency needs to be built in to cope with the

## Slide 64: Managing Expectations
Functionality
Effort (Time & Cost)
Delivery Date
Quality
Notes: Each stakeholder and each project team member will have different expectations. As the project manager, you need to manage all of them. Unmanaged expectations will cause conflict and can cause the project to fail.
Expectations fall into four main categories:
Expectations for each area should be addressed in the Statement of Work, Project Planning Worksheet, and Project Charter.
Periodically reviewing these documents is important. Key checkpoints should include:
Does everyone involved have the same understanding of the project?
Clarify responsibilities as assigned
Clarify the outcomes and time frame
Clarify the requirements and budgets
Understand the budget and schedule linkages
Communicate to everyone who is relevant

## Slide 65: Creating a Task List
Details
Write in the order of tasks
Be aware of micro-managing
Notes: To begin the nuts-and-bolts planning process, you must first make a list of all the tasks that are going to be done. Let’s say you are going to paint a room. Tasks might include:
Get paint samples
Choose a paint color
Remove all furniture
Take off trim
Paint trim
Apply first coat
Apply second coat
Put trim back in
Put all furniture back in
How detailed the task list becomes is up to you. We suggest writing the task list in the way that you will accomplish it. For example, if you are going to apply the first coat of paint yourself; you may want to include all steps, such as crack-filling, sanding, taping, etc. If, however, you are contracting the task out, “Apply first coat” may be the only item you need to monitor. (Your painter probably wouldn’t appreciate being micro-managed!)

## Slide 66: Estimating Time
Tm
Probable Time
To
Optimistic Time
Calculated Time (Best Estimate)
Tp
Pessimistic Time
Te
To + 4Tm + Tp
6
Te =
Notes: When building your schedule, never guess times. Gather the most reliable information possible and use a scientific formula to get the best estimate. The better your estimates, the more reliable your plan will be.
First, make a table, list your tasks, and fill in the estimated time for each. (We have numbered our tasks in the example on the next page for easy identification.) Time can be listed in minutes, hours, days, weeks, months, or years. You should keep the same time scale for each task.
Next, identify what the best and worst case estimates would be. Now, for each task, plug the numbers into the formula given above. The result is the estimated time.

## Slide 67: Estimating Resources
People
Material
Money
Notes: Now that the task list is complete, it’s time to decide what resources will be used to accomplish the tasks. In project management, “resources” means people, materials, and money. For now, let’s just focus on people and materials – we’ll look at money in a moment.
A common method of resource listing is to list the tasks, estimated time, and resources required, all in the same table. We have started an example here.

## Slide 68: Estimating Costs
Salary
Material
Resources
Notes: Our next step is to add cost information to our table. Make sure to include salary information for everyone, even project team members, and to include line item cost information for each material resource. If you are doing a home project (as we are here), salary information will not be necessary.

## Slide 69: Module Six: Review Questions
When building a plan, what is important to remember?
At least half of the plan is a prediction.
The only fact you know for certain is that your plan is 100% right.
There is no room for vagueness as deadlines and outcomes will not change.
Contingency needs to be built in to cope with the uncertainty.
What can unmanaged expectations cause?
Conflict
The project to succeed
Improved time management
A new statement of work to be written

## Slide 70: Module Six: Review Questions
Which of these is a main category that expectations fall into?
Communication
Product management
Delivery date
Quantity
Which of these is not a key checkpoint to include when reviewing documents?
Clarify the outcomes and time frame.
Clarify the requirements and budgets.
Understand the budget and schedule linkages.
Communicate to everyone no matter what their relevance.

## Slide 71: Module Six: Review Questions
What is a good suggestion for writing the task list?
Write the task list before the statement of work is written.
Write the task list in the way that you will accomplish it.
Write the task list as you are completing each task.
Write the task list in the same manner you would your project charter.
When building your schedule, what should you never do?
Make concrete plans
Use outside help
Guess times
Estimate deliverables

## Slide 72: Module Six: Review Questions
What does the Te in the formula used for estimating time represent?
Calculated Time
Pessimistic Time
Optimistic Time
Probable time
What is the first thing you should do when properly estimating time?
Keep the same time scale for each task.
Identify what the best and worst case estimates would be.
Plug the numbers into the formula for estimating time.
Make a table, list your tasks, and fill in the estimated time for each.

## Slide 73: Module Six: Review Questions
In project management, what does “resources” mean?
Staff room, meeting, and deliverables.
People, materials, and money.
Materials, execution, and profit.
Stakeholders, statement of work, and end product.
What is a common method of resource listing?
List the tasks, estimated time, and resources required.
List the assumptions, agreements, and estimated time required.
List the resources, materials, and profits required.
List the tasks, agreements, and materials required.

## Slide 74: Module Six: Review Questions
When building a plan, what is important to remember?
At least half of the plan is a prediction.
The only fact you know for certain is that your plan is 100% right.
There is no room for vagueness as deadlines and outcomes will not change.
Contingency needs to be built in to cope with the uncertainty.
What can unmanaged expectations cause?
Conflict
The project to succeed
Improved time management
A new statement of work to be written

## Slide 75: Module Six: Review Questions
Which of these is a main category that expectations fall into?
Communication
Product management
Delivery date
Quantity
Which of these is not a key checkpoint to include when reviewing documents?
Clarify the outcomes and time frame.
Clarify the requirements and budgets.
Understand the budget and schedule linkages.
Communicate to everyone no matter what their relevance.

## Slide 76: Module Six: Review Questions
What is a good suggestion for writing the task list?
Write the task list before the statement of work is written.
Write the task list in the way that you will accomplish it.
Write the task list as you are completing each task.
Write the task list in the same manner you would your project charter.
When building your schedule, what should you never do?
Make concrete plans
Use outside help
Guess times
Estimate deliverables

## Slide 77: Module Six: Review Questions
What does the Te in the formula used for estimating time represent?
Calculated Time
Pessimistic Time
Optimistic Time
Probable time
What is the first thing you should do when properly estimating time?
Keep the same time scale for each task.
Identify what the best and worst case estimates would be.
Plug the numbers into the formula for estimating time.
Make a table, list your tasks, and fill in the estimated time for each.

## Slide 78: Module Six: Review Questions
In project management, what does “resources” mean?
Staff room, meeting, and deliverables.
People, materials, and money.
Materials, execution, and profit.
Stakeholders, statement of work, and end product.
What is a common method of resource listing?
List the tasks, estimated time, and resources required.
List the assumptions, agreements, and estimated time required.
List the resources, materials, and profits required.
List the tasks, agreements, and materials required.

## Slide 79: Module Seven: Planning (II)
The next part of the planning phase is
to bring together the nuts and bolts
information that we have gathered (the
tasks to be performed, plus the time,
resources, and costs required for each)
and to create an actual plan for
executing the project.
A work well begun is half ended.
Plato
Notes: The next part of the planning phase is to bring together the nuts and bolts information that we have gathered (the tasks to be performed, plus the time, resources, and costs required for each) and to create an actual plan for executing the project.

## Slide 80: Building the Work Breakdown Structure
Project Title
Task 1
Task 1.1
Task 1.2
Task 2
Task 2.1
Task 1.1.1
Notes: A work breakdown structure (WBS) is a graphical breakdown of all the work to be done in the project.
The WBS can be built in five easy steps.
Identify the purpose of the project and write the title at the top.
Establish the major segments of the work. Example for painting a room:
Gather materials
Prepare room
Paint room
Finish room
Break down the segments of the work into sub-components.
Gather materials
Prepare room
Paint room
Finish room
Continue breaking down the work until you reach the level where you will assign and monitor the project work. (Remember, if you are going to assign a task to someone, you may not need to break it down very far.)
Review the WBS with the stakeholders and project team to ensure all items are covered.

## Slide 81: Creating the Schedule
Perform activities simultaneously
Indicate milestones
Include deliverables
Include lag and lead time
Notes: The next task is to build the schedule. This will be your most important document during the project. It will grow and change throughout the project. Keep it up to date to make sure that you will meet your deadlines.
There are many scheduling tools available, which will be discussed in the next topic. For now, let’s look at a simple table format – an expansion of the table that we used earlier.
The first column lists the tasks that need to be performed. This list is typically organized in the order in which the tasks will be accomplished chronologically. In addition, think of how the project might be broken up into phases, to help subdivide tasks that will be performed.
The second column specifies the duration time of each task listed. This duration might be listed in terms of days, weeks, or hours, depending on the project. Next, people and equipment will be listed, followed by start and end dates and/or times.
In order to build the schedule, you will need the availability of people and machines, and sometimes material resources. This is where graphic tools can really help out.

## Slide 82: Creating a Risk Management Plan
Mitigate: Reduce the probability of risk
Avoid: Take steps to avoid the risk entirely
Transfer: Transfer the responsibility for the risk to someone outside the project
Accept: This is the best approach for risks with low probability and impact ratings
Notes: The Risk Management Plan details how to approach and manage project risks. A risk management plan should be completed for any project. All project team members and stakeholders should have a meeting to complete a first draft of the plan. This ensures everyone knows what problems could crop up.
The meeting should also identify the response options for each risk. There are four common approaches:
• Mitigate: Find ways to reduce the probability and impact levels of the risk.
• Avoid: Take steps to avoid the risk entirely. For example, if your chosen construction company may have a worker’s strike soon, perhaps you could choose another company.
• Transfer: Transfer the responsibility for the risk to someone outside the project. This will decrease your liability, but it may also decrease your level of control, too.
• Accept: Accept that the risk could happen, and choose not to act. This is the best approach for risks with low probability and impact ratings.
During the project, stakeholders and team members should be encouraged to bring up new risks to the project manager. The project manager can then update the plan and communicate it to the rest of the team.
A basic risk management plan looks like this, with one row for each risk:

## Slide 83: Creating a Communication Plan
What? | Status meetings
Who? | Project team
Where? | Whirlwind Room, Fourth Floor
When? | Every Monday at 9 a.m.
Why? | To report issues encountered last week and upcoming tasks for this week
How? | In-person
Notes: Effective communication can make the difference between success and failure in any kind of project. Developing and maintaining a good communication plan will ensure that everyone involved in the project stays up to date, and that information is shared appropriately.
A basic template should include the what, who, where, when, why, and how for each communication item.
As you can see, the communication plan can be formal or informal, highly detailed or broadly framed, based on the needs of the project. Like the schedule, the plan should be maintained, updated, and shared throughout the project.

## Slide 84: Module Seven: Review Questions
What is the definition of the work breakdown structure?
A graphical breakdown of all the work to be done in the project.
Team or project-based organizations.
The ability to use one's time effectively or productively, especially at work.
The structure in which people interact in large and small groups.
What is the first step of the work breakdown structure?
Identify the purpose of the project and write the title at the top.
Review the WBS with the stakeholders and project team to ensure all items are covered.
Establish the major segments of the work.
Break down the segments of the work into sub-components.

## Slide 85: Module Seven: Review Questions
After breaking down the segments of the work into sub-components, what is the next step?
Review the WBS with the stakeholders and project team to ensure all items are covered.
Continue breaking down the work until you reach the level where you will assign and monitor the project work.
Establish the major segments of the work.
Identify the purpose of the project and write the title at the top.
Which of these statements is not true about the schedule?
The schedule is the most important document during the project.
Graphic tools can really help out when building the schedule.
You must keep the schedule up to date to make sure that you will meet your deadlines.
The schedule is the only document that will not grow and change throughout the project.

## Slide 86: Module Seven: Review Questions
What might you need in order to build the schedule?
The availability of people
The availability of machines
Material resources
All of the above
Which of these is a helpful tip to make your schedule accurate, available and useful?
Look for places where resources can perform activities separately.
Identify milestone points in your project that require resources or time.
If you are delivering a business project, try to include deliverables with the milestones.
Make sure to exclude lag and lead time in your tasks.

## Slide 87: Module Seven: Review Questions
In team projects, which members of your team should have access to the schedule?
Only the project manager
Your team leads
The lower-level employees
Everyone
What is not a common approach when identifying responses options to risks?
Mitigate
Permit
Transfer
Accept

## Slide 88: Module Seven: Review Questions
During the project, what should team members and stakeholders be encouraged to do?
Transfer the blame for a risk to someone outside the team.
Update the plan and communicate it to the rest of the team.
Bring up new risks to the project manager.
Create new risks to test and prepare the team.
Which plan ensures that everyone involved in the project stays up to date, and that information is shared appropriately?
Risk management plan
Communication plan
Project charter
Schedule

## Slide 89: Module Seven: Review Questions
What is the definition of the work breakdown structure?
A graphical breakdown of all the work to be done in the project.
Team or project-based organizations.
The ability to use one's time effectively or productively, especially at work.
The structure in which people interact in large and small groups.
What is the first step of the work breakdown structure?
Identify the purpose of the project and write the title at the top.
Review the WBS with the stakeholders and project team to ensure all items are covered.
Establish the major segments of the work.
Break down the segments of the work into sub-components.

## Slide 90: Module Seven: Review Questions
After breaking down the segments of the work into sub-components, what is the next step?
Review the WBS with the stakeholders and project team to ensure all items are covered.
Continue breaking down the work until you reach the level where you will assign and monitor the project work.
Establish the major segments of the work.
Identify the purpose of the project and write the title at the top.
Which of these statements is not true about the schedule?
The schedule is the most important document during the project.
Graphic tools can really help out when building the schedule.
You must keep the schedule up to date to make sure that you will meet your deadlines.
The schedule is the only document that will not grow and change throughout the project.

## Slide 91: Module Seven: Review Questions
What might you need in order to build the schedule?
The availability of people
The availability of machines
Material resources
All of the above
Which of these is a helpful tip to make your schedule accurate, available and useful?
Look for places where resources can perform activities separately.
Identify milestone points in your project that require resources or time.
If you are delivering a business project, try to include deliverables with the milestones.
Make sure to exclude lag and lead time in your tasks.

## Slide 92: Module Seven: Review Questions
In team projects, which members of your team should have access to the schedule?
Only the project manager
Your team leads
The lower-level employees
Everyone
What is not a common approach when identifying responses options to risks?
Mitigate
Permit
Transfer
Accept

## Slide 93: Module Seven: Review Questions
During the project, what should team members and stakeholders be encouraged to do?
Transfer the blame for a risk to someone outside the team.
Update the plan and communicate it to the rest of the team.
Bring up new risks to the project manager.
Create new risks to test and prepare the team.
Which plan ensures that everyone involved in the project stays up to date, and that information is shared appropriately?
Risk management plan
Communication plan
Project charter
Schedule

## Slide 94: Module Eight: Planning Tools
In the last module, we looked at how to build a schedule in table format. This format will work well for small projects. However, for more complex projects, you will need additional tools. This module will explore four of the most popular tools, including graphical methods and Microsoft Project.
Good fortune is what happens when opportunity meets with planning.
Thomas Edison
Notes: In the last module, we looked at how to build a schedule in table format. This format will work well for small projects. However, for more complex projects, you will need additional tools. This module will explore four of the most popular tools, including graphical methods and Microsoft Project.

## Slide 95: The Gantt Chart
Notes: Gantt charts have become a common technique for representing the phases and activities of a project work breakdown structure, as they can be understood by a wide audience.
A Gantt chart is a type of bar chart that illustrates a project schedule. Gantt charts illustrate the start and finish dates of each task, as well as task dependencies and links. Gantt charts can be easily customized to show resources, costs, and other important information. They can also be color-coded for different task phases or responsibilities.

## Slide 96: The Network Diagram
Notes: A network diagram is another way of showing the path of tasks in the project. Tasks are each placed in a box and each box is placed in chronological order. Arrows are drawn from task to task, indicating the logical progression of work. Boxes can be customized to contain any information you like, including start and finish dates, task length, cost, resources, and more. Boxes can also be color-coded based on the phase of the project; resource required, team assignment, etc.
We recommend building the network diagram as a team using these steps.
Write all steps out on sticky notes.
Tape a large piece of paper to the wall.
Place sticky notes in order.
Once you think you have the right order, check to make sure lag and lead time is allowed for. Also look for ways that work can be completed simultaneously.
Draw arrows to indicate task links. Color-code the boxes if desired.
Post the diagram in a central location. Make a copy for reference, and keep the original drawing updated as the project progresses.
The network diagram will also help you identify the critical path: the shortest path through the project. This will help if an element of the triple constraint changes and you must alter your plan.

## Slide 97: Using a RACI Chart
R
A
Responsible for execution
Approver
Example | Sue | Bob | Joe | Jane
Build widget plan | A | R | I | I
Build widget | R | A | C | I
Ship widget to customers | I | I | I | R
C
I
Consult
Keep informed
Notes: A RACI chart is an excellent way to outline who is responsible for what during the project. To start, create a chart with tasks listed on the left hand side, and resources listed across the top. Now, put the appropriate letter in each cell:
• R: Responsible for execution
• A: Approver
• C: Consult
• I: Keep informed

## Slide 98: Going the Extra Mile: Microsoft Project
Microsoft Project is just a tool
Understand how it calculates numbers
Every project requires different tools
Notes: Throughout the course, we have made some references to using computer software to manage projects. We have even included some diagrams from Microsoft Project, a popular project management application.
Applications like Microsoft Project are extremely useful for project managers and their teams. Microsoft Project, as an example, stores information about resources, schedules, tasks, budgets, and more; generates reports on the fly; allows you to enter and view information in numerous ways; and even allows you to collaborate with other team members.
We urge everyone, particularly new project managers, to remember that Microsoft Project is just a tool. In order to make the best use of it, you must understand how it calculates numbers and generates diagrams. Once you have a solid understanding of basic project management concepts, feel free to take the time to learn about project management software if you desire.
Remember, too, that every project requires different tools. For small projects, you may not need the sophisticated features of a software program. If you choose to grow your project management skills, however, and take on larger projects, you will appreciate the extra tools available in these applications.

## Slide 99: Module Eight: Review Questions
Which of these statements is not true of the Gantt chart?
A Gantt chart is a type of bar chart that illustrates a project schedule.
Gantt charts can be easily customized to show resources, costs, and other important information.
Gantt charts illustrate the start and finish dates of each task, as well as task dependencies and links.
They have become a common technique for representing the phases and activities of a project work breakdown structure, as they can be understood by a small audience.
Which of these is an additional benefit of using the Gantt chart?
It helps you assign tasks to several other project manager’s team.
Arrows can be drawn from task to task, indicating the logical progression of work.
They can be color-coded for different task phases or responsibilities.
They can post the diagram in a central location.

## Slide 100: Module Eight: Review Questions
When building the network diagram as a team, what is the first step?
Write all steps out on sticky notes
Place sticky notes in order
Tape a large sheet to the wall
Draw arrows to indicate task links
How will using the network diagram to identify a critical path help?
It will help if you need to assign tasks to another project manager’s team.
It will help if an element of the triple constraint changes and you must alter your plan.
It will help if a task in the statement of work needs updating.
It will help if you need to keep all tasks and responsibilities the same.

## Slide 101: Module Eight: Review Questions
Which planning tool will be best to use for outlining who is responsible for what during the project?
The RACI Char
The Network Diagram.
The Gantt Chart
The Microsoft Project
How would you start to make a RACI chart?
Customize each cell to show resources, costs, and other important information.
Tasks are each placed in a box and each box is placed in chronological order.
Create a chart with tasks and put each task in the appropriate cell.
Create a chart with tasks listed on the left hand side and resources listed across the top.

## Slide 102: Module Eight: Review Questions
What does the “I” in RACI stand for?
Keep individualized
Keep informed
Include
Improvise
Which of these describes the Microsoft Project?
A program that allows the user to use the Gantt chart, the Network Diagram, and the RACI chart all at once
A template used by the RACI chart
A popular project management application
A little-known project management organizer

## Slide 103: Module Eight: Review Questions
Which of these statements is not true of Microsoft Project?
Microsoft Project stores information about resources, schedules, tasks, budgets, and more.
Microsoft Project allows you to collaborate with other team members.
Microsoft Project is extremely useful for project managers, not their teams as a whole.
Microsoft Project allows you to enter and view information in numerous ways.
When is it possible that you would not need the sophisticated features of a software program?
With large audiences
With startup companies
When more than one team is working together
With small projects

## Slide 104: Module Eight: Review Questions
Which of these statements is not true of the Gantt chart?
A Gantt chart is a type of bar chart that illustrates a project schedule.
Gantt charts can be easily customized to show resources, costs, and other important information.
Gantt charts illustrate the start and finish dates of each task, as well as task dependencies and links.
They have become a common technique for representing the phases and activities of a project work breakdown structure, as they can be understood by a small audience.
Which of these is an additional benefit of using the Gantt chart?
It helps you assign tasks to several other project manager’s team.
Arrows can be drawn from task to task, indicating the logical progression of work.
They can be color-coded for different task phases or responsibilities.
They can post the diagram in a central location.

## Slide 105: Module Eight: Review Questions
When building the network diagram as a team, what is the first step?
Write all steps out on sticky notes
Place sticky notes in order
Tape a large sheet to the wall
Draw arrows to indicate task links
How will using the network diagram to identify a critical path help?
It will help if you need to assign tasks to another project manager’s team.
It will help if an element of the triple constraint changes and you must alter your plan.
It will help if a task in the statement of work needs updating.
It will help if you need to keep all tasks and responsibilities the same.

## Slide 106: Module Eight: Review Questions
Which planning tool will be best to use for outlining who is responsible for what during the project?
The RACI Char
The Network Diagram.
The Gantt Chart
The Microsoft Project
How would you start to make a RACI chart?
Customize each cell to show resources, costs, and other important information.
Tasks are each placed in a box and each box is placed in chronological order.
Create a chart with tasks and put each task in the appropriate cell.
Create a chart with tasks listed on the left hand side and resources listed across the top.

## Slide 107: Module Eight: Review Questions
What does the “I” in RACI stand for?
Keep individualized
Keep informed
Include
Improvise
Which of these describes the Microsoft Project?
A program that allows the user to use the Gantt chart, the Network Diagram, and the RACI chart all at once
A template used by the RACI chart
A popular project management application
A little-known project management organizer

## Slide 108: Module Eight: Review Questions
Which of these statements is not true of Microsoft Project?
Microsoft Project stores information about resources, schedules, tasks, budgets, and more.
Microsoft Project allows you to collaborate with other team members.
Microsoft Project is extremely useful for project managers, not their teams as a whole.
Microsoft Project allows you to enter and view information in numerous ways.
When is it possible that you would not need the sophisticated features of a software program?
With large audiences
With startup companies
When more than one team is working together
With small projects

## Slide 109: Module Nine: Executing the Project
We have spent a lot of time talking about what the project will do and making plans for how to do it. Finally, it is time to get to work and put our plans into action.
You can only elevate individual performance by elevating that of the entire system.
W. Edwards Deming
Notes: We have spent a lot of time talking about what the project will do and making plans for how to do it. Finally, it is time to get to work and put our plans into action.

## Slide 110: Establishing Baselines
Formal end of the planning phase
Original plan
Measuring stick
Communicated to all stakeholders
Notes: There is actually one final task to complete before we can start work on our project. Establishing the baseline indicates the formal end of the planning phase and the beginning of project execution and control.
The baseline is your original plan, containing the original scope, cost, and time. This gives you a measuring stick throughout the project. For example, let’s say that your baseline budget was $20,000. If, after the first task, you have spent $15,000, you know you’re in trouble. You can then evaluate the situation and prepare an action plan – hopefully before things get too out of hand.
The baseline should be communicated to all stakeholders and the project team. Scope and resources can be outlined in text format. Cost and time can be displayed as a graph. Or, you can use a graphic scheduling tool (like a Gantt chart or network diagram) to display the original plan and track where you are. (More on that in a moment!)

## Slide 111: Monitoring Project Progress
Status meetings
Regular status reports
Hands-on observation
Notes: As the project manager, it is your responsibility to monitor all the parts of your project to make sure they are continuing as planned. If issues arise, it is your responsibility to resolve them, or to escalate them to someone who can resolve them.
Some popular, effective methods of tracking project progress include:
Regular status meetings
Regular status reports
Hands-on observation
Recording data manually or electronically and generating reports (for example, spending to date versus total budget)
Your visual scheduling tools can also help you record project progress and communicate it to your team.
As tasks are completed, they can be crossed off the Gantt chart and/or the network diagram.
If new resources need to be added, they can be added to network diagram boxes.
If tasks need to be re-scheduled, they can be moved around on the network diagram.
Risks, accomplishments, and lessons learned can be posted next to tasks.

## Slide 112: Triple Constraint Reduction Methods
Crashing: Reduce the schedule without changing the budget
Fast-Tracking: Where lag/lead time can be reduced or eliminated.
De-scoping: Removes items from the project scope to free up time and/or money.
Notes: Be forewarned: after all of your planning, it is very likely that one element of the triple constraint will change. Perhaps a team member has left the organization, the budget has been cut, or new technical requirements need to be met.
When approached with scope changes, don’t panic! There are three established methods that you can use to decide how to alter the course of the project.
Crashing: Reduce the schedule without changing the budget, or vice-versa (depending on project needs). This can be done by using cheaper resources, or by re-evaluating time estimates.
Fast-Tracking: Can be done with the schedule only. Looks at the schedule to see which tasks (if any) can be completed concurrently, and where lag/lead time can be reduced or eliminated.
De-scoping: Removes items from the project scope to free up time and/or money.
Make sure that you truly look at the big picture, and include short and long term benefits and consequences in your decision-making process.
Once you have performed careful analysis, gather documentation to back up your decision, clear the decision with the appropriate stakeholders, change the project plan accordingly, and communicate the plan change to everyone involved.

## Slide 113: Module Nine: Review Questions
What indicates the formal end of the planning phase and the beginning of project execution and control?
Establishing the baseline
Maintaining and controlling
Initiating
Resolving risk
Who should the baseline be communicated to?
The project team and those working on the budget.
All stakeholders and the project team.
All stakeholders and direct supervisors.
The project team and direct supervisors.

## Slide 114: Module Nine: Review Questions
When establishing baselines, what can be outlined in text format?
The baseline
Cost and time
Scope and resources
Both a & b
If an issue arises, what is the responsibility of the project manager?
To resolve the issues
To escalate the issues to someone who can resolve them
To ensure that issues do not arise in the first place
Both a & b

## Slide 115: Module Nine: Review Questions
Which of these is not a popular, effective method of tracking project progress?
Regular status meetings
Hands-off observation
Recording data manually or electronically and generating reports
Regular status reports
Which of these is a good suggestion when using your visual scheduling tools?
Risks, accomplishments, and lessons learned can be posted only in a Gantt Chart.
If tasks need to be re-scheduled, they cannot be moved around on the network diagram.
As tasks are completed, they can be crossed off the RACI chart.
If new resources need to be added, they can be added to network diagram boxes.

## Slide 116: Module Nine: Review Questions
After all your planning, what is very likely to change?
One element of the triple constraint
The guidance of your shareholders
One of the members of your project management team
The deliverables of the project
Which of these is not an established method that you can use to decide how to alter the course of the project?
Projecting
Crashing
Fast-tracking
De-scoping

## Slide 117: Module Nine: Review Questions
When faced with scope changes, how can you reduce the schedule without changing the budget (or vice versa)?
This can be done by removing items from the project scope to free up money
This can be done by removing items from the project scope to free up time
This can be done by using cheaper resources, or by re-evaluating time estimates
This can be done with the schedule only
When using triple constraint reduction methods, what is important to remember?
Include short and long term benefits and consequences in your decision-making process
Don’t panic
Make sure that you truly look at the big picture
All of the above

## Slide 118: Module Nine: Review Questions
What indicates the formal end of the planning phase and the beginning of project execution and control?
Establishing the baseline
Maintaining and controlling
Initiating
Resolving risk
Who should the baseline be communicated to?
The project team and those working on the budget.
All stakeholders and the project team.
All stakeholders and direct supervisors.
The project team and direct supervisors.

## Slide 119: Module Nine: Review Questions
When establishing baselines, what can be outlined in text format?
The baseline
Cost and time
Scope and resources
Both a & b
If an issue arises, what is the responsibility of the project manager?
To resolve the issues
To escalate the issues to someone who can resolve them
To ensure that issues do not arise in the first place
Both a & b

## Slide 120: Module Nine: Review Questions
Which of these is not a popular, effective method of tracking project progress?
Regular status meetings
Hands-off observation
Recording data manually or electronically and generating reports
Regular status reports
Which of these is a good suggestion when using your visual scheduling tools?
Risks, accomplishments, and lessons learned can be posted only in a Gantt Chart.
If tasks need to be re-scheduled, they cannot be moved around on the network diagram.
As tasks are completed, they can be crossed off the RACI chart.
If new resources need to be added, they can be added to network diagram boxes.

## Slide 121: Module Nine: Review Questions
After all your planning, what is very likely to change?
One element of the triple constraint
The guidance of your shareholders
One of the members of your project management team
The deliverables of the project
Which of these is not an established method that you can use to decide how to alter the course of the project?
Projecting
Crashing
Fast-tracking
De-scoping

## Slide 122: Module Nine: Review Questions
When faced with scope changes, how can you reduce the schedule without changing the budget (or vice versa)?
This can be done by removing items from the project scope to free up money
This can be done by removing items from the project scope to free up time
This can be done by using cheaper resources, or by re-evaluating time estimates
This can be done with the schedule only
When using triple constraint reduction methods, what is important to remember?
Include short and long term benefits and consequences in your decision-making process
Don’t panic
Make sure that you truly look at the big picture
All of the above

## Slide 123: Module Ten: Maintaining and Controlling the Project
The fourth phase of project
management is maintaining and
controlling. Although it is part of the
execution phase, it is so important that
the PMBOK separates it out into its
own set of activities. This module will
give you some key tools for keeping
your project on track.
Trying is just a noisy way of saying no progress.
Warren Bennis
Notes: The fourth phase of project management is maintaining and controlling. Although it is part of the execution phase, it is so important that the PMBOK separates it out into its own set of activities. This module will give you some key tools for keeping your project on track.

## Slide 124: Making the Most of Status Updates
Tasks planned for the previous week
Tasks completed in the previous week
Tasks planned for the following week
Issues and risks identified
Notes: Regular, mandatory status meetings for all project team members should be a part of any project. These meetings will give team members a chance to connect, discuss issues, and solve problems. It will also give you the opportunity to coach team members and make sure you’re on top of what everyone is doing.
Status meetings should be tied in with status reports. We recommend that both items be completed weekly or bi-weekly, depending on your project. Also, remember that meetings and reports can be brief or detailed – it all depends on what level of control you need and how big the project is.
We recommend a Friday-Monday schedule, where reports are submitted on Friday (before the end of the day) and status meetings are held on Monday. If a holiday happens to occur, reports could be submitted on the Thursday, and meetings could take place on the Tuesday.
Status reports should contain the following items:
• Team member name
• Status report date
• Tasks planned for the previous week
• Tasks completed in the previous week
• Tasks planned for the following week
• Issues and risks identified (highlight those that require project manager attention)
Status meetings, then, are a review of tasks that each member completed for the previous week, what they have planned for the upcoming week, and what issues they have encountered or predict.
Again, status reports and meetings should be customized for your projects’ needs. Team members should also know that issues should be reported to the project manager as they arise.

## Slide 125: Managing Change
Change Request Number: | Change Requested On:
Change Requested By: | Change Submitted By:
Change Details: | Tasks Affected:
Approved or Rejected? | By:
Notes: Change management is another way of controlling your project. This process ensures that any changes, whether they are to the objectives, requirements, tasks, or design of a particular component, are approved by the project team.
At the beginning of the project, all stakeholders and team members must agree not to make any changes to the project plan or to the design of its components, and to instead follow a change management process. Then, when a change is required, a change management form is completed.

## Slide 126: Monitoring Risks
Be proactive
Keep an eye out for assumptions
Keep a record of actions
Notes: Remember the risk management plan that we built during the planning phase? Make sure it doesn’t stay on a shelf. Continue to monitor and add to it.
Here are some additional tips for making sure risks don’t ruin your project:
• Be proactive. Have meetings with stakeholders and outside parties to ensure your risk assessment is accurate and that your action plan (if you have one) is valid.
• Keep an eye out for assumptions. Make sure that they continue to hold true. Identify what could happen if those assumptions are unfulfilled.
• Keep a record of what actions you take to mitigate risks.

## Slide 127: Module Ten: Review Questions
Which is the fourth phase of project management?
Planning
Maintaining and controlling
Preparing and executing
Initiating
How often is it recommended that status meetings and status updates be completed?
Weekly or bi-weekly
Monthly or bi-monthly
Every quarter, tied in with quarterly reports
Daily

## Slide 128: Module Ten: Review Questions
In a Friday-Monday schedule, if a holiday occurs on a Friday, when it recommended that status updates be submitted?
Thursday
Friday, even with the holiday
The following Monday
Wednesday
Which of these is not an item that should be contained within the status report?
Issues and risks identified
Status report date
Tasks planned for the previous week
Tasks planned for the following months

## Slide 129: Module Ten: Review Questions
What is a good rule of thumb for status reports and meetings?
Status meetings should be kept separate from status reports whenever possible.
Status meetings and reports should be kept brief.
Status meetings and reports should be kept intricately detailed.
Status meetings and reports should be customized for your projects’ needs.
What process assures that all changes are approved by the project team?
Status meetings and reports
Risk management
Change management
Project management team changes

## Slide 130: Module Ten: Review Questions
Who is the change management form submitted to?
Human resources
The project manager
The project management team
The stakeholders
For larger projects, who can be involved in managing change?
The project manager
The project management team
A separate task force
All of the above

## Slide 131: Module Ten: Review Questions
Which plan used during the planning phase can also be used in the maintaining and controlling phase?
Change management plan
Risk management plan
Status reports and updates
Communication plan
Which of these is not a helpful tip when using a risk management plan?
Have meetings with stakeholders and outside parties to ensure your risk assessment is accurate.
Keep a record of what actions you take to mitigate risks.
Be reactive when it comes to maintaining and controlling with stakeholders and outside parties.
Identify what could happen if assumptions are unfulfilled.

## Slide 132: Module Ten: Review Questions
Which is the fourth phase of project management?
Planning
Maintaining and controlling
Preparing and executing
Initiating
How often is it recommended that status meetings and status updates be completed?
Weekly or bi-weekly
Monthly or bi-monthly
Every quarter, tied in with quarterly reports
Daily

## Slide 133: Module Ten: Review Questions
In a Friday-Monday schedule, if a holiday occurs on a Friday, when it recommended that status updates be submitted?
Thursday
Friday, even with the holiday
The following Monday
Wednesday
Which of these is not an item that should be contained within the status report?
Issues and risks identified
Status report date
Tasks planned for the previous week
Tasks planned for the following months

## Slide 134: Module Ten: Review Questions
What is a good rule of thumb for status reports and meetings?
Status meetings should be kept separate from status reports whenever possible.
Status meetings and reports should be kept brief.
Status meetings and reports should be kept intricately detailed.
Status meetings and reports should be customized for your projects’ needs.
What process assures that all changes are approved by the project team?
Status meetings and reports
Risk management
Change management
Project management team changes

## Slide 135: Module Ten: Review Questions
Who is the change management form submitted to?
Human resources
The project manager
The project management team
The stakeholders
For larger projects, who can be involved in managing change?
The project manager
The project management team
A separate task force
All of the above

## Slide 136: Module Ten: Review Questions
Which plan used during the planning phase can also be used in the maintaining and controlling phase?
Change management plan
Risk management plan
Status reports and updates
Communication plan
Which of these is not a helpful tip when using a risk management plan?
Have meetings with stakeholders and outside parties to ensure your risk assessment is accurate.
Keep a record of what actions you take to mitigate risks.
Be reactive when it comes to maintaining and controlling with stakeholders and outside parties.
Identify what could happen if assumptions are unfulfilled.

## Slide 137: Module Eleven: Closing Out
You’ve reached the point where all the
tasks in your project plan have been
checked off: the widget is built, the
advertisements are on TV, and boxes
are being shipped to customers. Before
you consider the project complete,
however, there are a few more things
to be done.
The real problem is what to do with problem solvers after the problem is solved.
Gay Talese
Notes: You’ve reached the point where all the tasks in your project plan have been checked off: the widget is built, the advertisements are on TV, and boxes are being shipped to customers. Before you consider the project complete, however, there are a few more things to be done.

## Slide 138: Preparing for Closeout
Closure of a project can be difficult
Reviewing their performance
Help team members get through this tough time
Notes: increasing. Closure of a project can be difficult, particularly if the project has been long and/or difficult, or if team members will not be working together afterward.
To help team members get through this tough time, make sure they know what they will be working on after the project. Make sure they know who will be reviewing their performance. (If it is not you, let them know that you will pass on information about their performance to their regular supervisor. This expectation should have been set at the beginning of the project, too.) Encourage team members to come to you with questions.

## Slide 139: Celebrating Successes
Take time to celebrate
Recognize each person for their contributions
Have a close-out meeting
Notes: After the project, take time to celebrate the things that the project team did well. Try to recognize each person for their contributions and accomplishments.
Team celebrations, of course, are also an important part of project close-out. It is a great idea to have a team party. Another excellent idea is to have a close-out meeting with stakeholders, team members, and other interested parties. This provides an opportunity to review the project’s accomplishments and challenges – and it ties in with our next topic.

## Slide 140: Learning from Project Challenges
Effort put into the task is not wasted
Apply these lessons to future projects
Lessons learned should be documented
Ensures everyone is aware of the challenges encountered
Notes: No project will go perfectly. There will always be a risk you didn’t anticipate, tasks that run longer than they should have, project team members that didn’t perform as you expected… If it can happen, it probably will!
Meeting with team members and stakeholders to identify lessons learned throughout the project is a valuable exercise for several reasons.
It ensures everyone is aware of the challenges encountered and what was done to resolve them.
If something is learned from a mistake or failed endeavor, then the effort put into the task is not entirely wasted.
Participants can apply these lessons to future projects and be more successful.
Lessons learned should be documented and included with final project documentation.

## Slide 141: Scope Verification
Were all needs met?
Were all deliverables met?
Are the stakeholders happy with the results?
Notes: Another important part of project closeout is scope verification. This is where stakeholders and team members meet to determine whether or not the project did what it set out to do.
This checklist can be used as a guide for scope verification.
Were all needs met? Were any wants met?
Were all SMART objectives achieved?
Were all deliverables met?
Are the stakeholders happy with the results? Are team members happy?
If the project team realizes that an important deliverable has been missed, there are two options.
Return to the planning phase and create a plan for completing the missed tasks.
Choose to leave this item as unmet and create a separate project for it.

## Slide 142: A Final To-Do List
Pass on appropriate project information
Ensure all payments have been made and paperwork submitted
Dispose of or return materials
Notes: In addition to scope verification and lessons learned, the following tasks should also be completed during closeout:
Pass on appropriate project information (training documentation, blueprints, troubleshooting information, etc.) to the appropriate people
Ensure all payments have been made and paperwork submitted
Dispose of or return materials
All project documents, both electronic and paper, should be completed and compiled. Make sure to include the original document, the final document, and any revised versions. Key documents include:
Statement of work
Project charter
Project planning worksheet
Project schedule and related documents
Risk management plan
Communication plan
Change management requests
Team member evaluations
Lessons learned
Meeting minutes
Status reports

## Slide 143: Module Eleven: Review Questions
As your project winds down, what may you find happening?
Team morale dropping
Anxiety increasing
Closing of the project becoming difficult
All of the above
Which of these is a helpful way to help co-workers get through the closing of a project?
Make sure they know what they will be working on after the project.
Pass on comments about their work performance to their co-workers.
Try not to discuss performance review as this will only increase the difficulty.
Encourage team members to go to their human resources department with questions.

## Slide 144: Module Eleven: Review Questions
After the project, what should you take time to celebrate?
The anxiety your co-workers are experiencing.
The things the project team did well.
The risks and issues that were not avoided.
The relief the end of the project brings.
What is an important part of project close-out?
Status updates and reports
Risk management planning
A team celebration
Quickly focusing on the next project

## Slide 145: Module Eleven: Review Questions
Which of these statements is true about learning from project challenges?
Some projects go perfectly, and it’s important to learn what went wrong to get it perfect next time.
No project goes perfectly. If it can happen, it probably will!
There are always risks that you didn’t anticipate, but there are never tasks that run longer than they should have.
The best projects do not have challenges.
Which of these is not a good reason why meeting with team members and stakeholders to identify lessons learned is a valuable experience?
Participants can apply these lessons to future projects and be more successful.
It ensures everyone is aware of the challenges encountered and what was done to resolve them.
Lessons learned should be kept between the project manager and his team.
If something is learned from a mistake or failed endeavor, then the effort put into the task is not entirely wasted.

## Slide 146: Module Eleven: Review Questions
At which point in the project do stakeholders and team members meet to determine whether or not the project did what it set out to do?
Risk management plan.
When learning from project challenges.
Scope verification.
Celebrating successes.
Which of these questions can be used as a guide for scope verification?
Who else should we involve in this? Who might be affected?
What is a step in creating a network diagram?
What do we want the project to accomplish?
Were all needs met? Were any wants met?

## Slide 147: Module Eleven: Review Questions
If the project team realizes that an important deliverable has been missed, what is a good option?
Return to the planning phase and create a plan for completing the missed tasks.
Choose to leave the item at met as it is the end of the project.
Do whatever is necessary to ensure that stakeholders are happy on the return of their investment.
Apply lessons learned to future projects in order to be successful.
Which of these tasks is not completed during closeout?
Dispose of or return materials.
Complete a change management form at the end of the project.
Ensure all payments have been made and paperwork submitted.
Pass on appropriate project information to the appropriate people.

## Slide 148: Module Eleven: Review Questions
As your project winds down, what may you find happening?
Team morale dropping
Anxiety increasing
Closing of the project becoming difficult
All of the above
Which of these is a helpful way to help co-workers get through the closing of a project?
Make sure they know what they will be working on after the project.
Pass on comments about their work performance to their co-workers.
Try not to discuss performance review as this will only increase the difficulty.
Encourage team members to go to their human resources department with questions.

## Slide 149: Module Eleven: Review Questions
After the project, what should you take time to celebrate?
The anxiety your co-workers are experiencing.
The things the project team did well.
The risks and issues that were not avoided.
The relief the end of the project brings.
What is an important part of project close-out?
Status updates and reports
Risk management planning
A team celebration
Quickly focusing on the next project

## Slide 150: Module Eleven: Review Questions
Which of these statements is true about learning from project challenges?
Some projects go perfectly, and it’s important to learn what went wrong to get it perfect next time.
No project goes perfectly. If it can happen, it probably will!
There are always risks that you didn’t anticipate, but there are never tasks that run longer than they should have.
The best projects do not have challenges.
Which of these is not a good reason why meeting with team members and stakeholders to identify lessons learned is a valuable experience?
Participants can apply these lessons to future projects and be more successful.
It ensures everyone is aware of the challenges encountered and what was done to resolve them.
Lessons learned should be kept between the project manager and his team.
If something is learned from a mistake or failed endeavor, then the effort put into the task is not entirely wasted.

## Slide 151: Module Eleven: Review Questions
At which point in the project do stakeholders and team members meet to determine whether or not the project did what it set out to do?
Risk management plan.
When learning from project challenges.
Scope verification.
Celebrating successes.
Which of these questions can be used as a guide for scope verification?
Who else should we involve in this? Who might be affected?
What is a step in creating a network diagram?
What do we want the project to accomplish?
Were all needs met? Were any wants met?

## Slide 152: Module Eleven: Review Questions
If the project team realizes that an important deliverable has been missed, what is a good option?
Return to the planning phase and create a plan for completing the missed tasks.
Choose to leave the item at met as it is the end of the project.
Do whatever is necessary to ensure that stakeholders are happy on the return of their investment.
Apply lessons learned to future projects in order to be successful.
Which of these tasks is not completed during closeout?
Dispose of or return materials.
Complete a change management form at the end of the project.
Ensure all payments have been made and paperwork submitted.
Pass on appropriate project information to the appropriate people.

## Slide 153: Module Twelve: Wrapping Up
Although this workshop is coming to a close, we hope that your journey to improve your Project Management skills is just beginning. Please take a moment to review and update your action plan. This will be a key tool to guide your progress in the days, weeks, months, and years to come. We wish you the best of luck on the rest of your travels!
This feeling, finally, that we may change things - this is at the centre of everything we are. Lose that... lose everything.
Sir David Hare
Notes: Although this workshop is coming to a close, we hope that your journey to improve your project management skills is just beginning. Please take a moment to review and update your action plan. This will be a key tool to guide your progress in the days, weeks, months, and years to come. We wish you the best of luck on the rest of your travels!

## Slide 154: Words from the Wise
Yogi Berra
In theory there is no difference between theory and practice. In practice there is.
Dwight Eisenhower
Plans are nothing; planning is everything.
The reward for work well done is the opportunity to do more.
Jonas Salk:
Notes: • Yogi Berra: In theory there is no difference between theory and practice. In practice there is.
• Dwight Eisenhower: Plans are nothing; planning is everything.
• Jonas Salk: The reward for work well done is the opportunity to do more.