## Slide 1
Project Management
Corporate Training Materials

## Slide 2: Module One: Getting Started
In the past few decades, organizations have discovered something incredible: principles that have been used to create enormous successes in large projects can be applied to projects of any size to create amazing success. As a result, many employees are expected to understand project management techniques and how to apply them to projects of any size.
It must be considered that there is nothing more difficult to carry out nor more doubtful of success nor more dangerous to handle than to initiate a new order of things.
Machiavelli
Notes: It must be considered that there is nothing more difficult to carry out nor more doubtful of success nor more dangerous to handle than to initiate a new order of things.
Machiavelli
Welcome to the Project Management workshop. In the past few decades, organizations have discovered something incredible: principles that have been used to create enormous successes in large projects can be applied to projects of any size to create amazing success. As a result, many employees are expected to understand project management techniques and how to apply them to projects of any size. This workshop will give participants an overview of the entire project management process, as well as key project management tools that they can use every day.

## Slide 3: Workshop Objectives
Define projects
Project needs assessment
Project schedule
Planning tools
Notes: Research has consistently demonstrated that when clear goals are associated with learning that the learning occurs more easily and rapidly. With that in mind, let’s review our goals for today.
By the end of this workshop, participants will be able to:
Define projects, project management, and project managers
Identify the importance of the PMBOK and PMI
Identify the five process groups and ten knowledge areas as defined by the PMI
Describe the triple constraint
Perform a project needs assessment and write goals, requirements, and deliverables
Create key project documents, including the statement of work, project planning worksheet, and project charter
Build a project schedule by estimating time, costs, and resources
Understand and use the work breakdown structure
Create project planning documents, such as a schedule, risk management plan, and communication plan
Use planning tools, including the Gantt chart, network diagram, and RACI chart
Establish and use baselines
Monitor and maintain the project
Perform basic management tasks, including leading status meetings and ensuring all documents are complete at the end of the project

## Slide 4: Module Two: Key Concepts (I)
Before we get started, let’s make sure we all understand just what we mean by a project and by project management. We’ll also look at what a project manager’s role is.
Do not repeat the tactics which have gained you one victory, but let your methods be regulated by the infinite variety of circumstances.
Sun Tzu
Notes: Do not repeat the tactics which have gained you one victory, but let your methods be regulated by the infinite variety of circumstances.
Sun Tzu
Before we get started, let’s make sure we all understand just what we mean by a project and by project management. We’ll also look at what a project manager’s role is.

## Slide 5: What is a Project?
Limited endeavor
Start and end date
Clear goals
Defined responsibility
Notes: A project is a limited endeavor (meaning it has specific start and finish dates) that is undertaken to meet particular goals and objectives. Projects are different than processes or everyday operations, which are repetitive, permanent, or semi-permanent functional work taken on to produce products or services.
All successful projects share the following characteristics:
Clear goals
Defined ownership/responsibility
Timeline
Dedicated team
Defined methodology
Controlled execution
Completion evaluated based on original plan
Linked to business objectives
Supported by an organization’s management team
Estimated Time
10 minutes
Topic Objective
To understand what is meant by the term “project.”
Topic Summary
A project is a limited endeavor (meaning it has specific start and finish dates) that is undertaken to meet particular goals and objectives.
Materials Required
List of projects
Planning Checklist
Before the workshop, write the following list on the flip chart.
Daily invoice processing
Planning for annual picnic
Construction of a new home
Widget manufacturing
Widget manufacturing process review
Installation of a new computer system
Recommended Activity
Review the list with the class and determine which items could be classified as a project. Here are our answers.
Daily invoice processing: No
Planning for annual picnic: Yes
Construction of a new home: Yes
Widget manufacturing: No
Widget manufacturing process review: Yes
Installation of a new computer system: Yes
Delivery Tips
This activity can be performed in small or large groups.
Review Questions
What is one characteristic of a successful project?

## Slide 6: What is a Project Management?
Planning and organizing
Managing resources
Within budget
Notes: Project management is the combined art and science of planning, organizing, and managing resources to get a particular project done on time, within budget, and with the results that the organization set out to achieve.
There are many types of project management designed for different scenarios and different industries. This workshop will focus on the traditional method, used by the Project Management Institute, which follows five process groups. (See Module Three for more information.)
Estimated Time
10 minutes
Topic Objective
To understand what is meant by “project management.”
Topic Summary
Project management is the combined art and science of planning, organizing, and managing resources to get a particular project done on time, within budget, and with the results that the organization set out to achieve.
Recommended Activity
Have group members share uses of project management in their organization.
Stories to Share
The Apollo program conducted by NASA in the 1960’s is considered the dawn of project management.
Delivery Tips
This activity can be performed in small or large groups.
Review Questions
Which project management approach will this workshop use?

## Slide 7: What is Project Manager?
Responsible and accountable
Setting objectives
Balance wants and needs
Notes: A project manager is the person responsible and accountable for accomplishing the stated project objectives. Key project management responsibilities include creating clear and attainable project objectives, building the project requirements, and managing the triple constraint for projects.
The project manager is often required to perform a juggling act, balancing what the customer wants, and needs with what the team can provide in a particular time frame and with a particular budget. A successful project manager has a hodgepodge of skills and continues learning.
Key skills include:
Leadership
Negotiation
Influence and persuasion
Project management
Communication
Time management
Stress and anger management
Although you do need project management skills to be a project manager, you don’t need to be a project manager to use project management skills. You will find uses for most of the tools that we discuss today in your day-to-day life, both personal and professional.
Estimated Time
10 minutes
Topic Objective
To understand what the role of project manager encompasses.
Topic Summary
A project manager is the person responsible and accountable for accomplishing the stated project objectives.
Materials Required
Action plans
Planning Checklist
Print out one action plan per participant.
Recommended Activity
Have participants review the project management skill areas listed in the Student Training Guide and on the next page. Then, ask participants to choose three skill areas that they would like to work on and list them in their action plan.
If participants think of skill areas that are not listed, encourage them to share the area with the class.
Delivery Tips
If you handed out the action plans at the beginning of the workshop, this activity should go smoothly.
Review Questions
Do you need to be a project manager to use project management skills?

## Slide 8: Module Two: Review Questions
What is the definition of a project?
A planned series of future events, items, or performances.
A meeting of people face to face, especially for consultation.
A limited endeavor that is undertaken to meet particular goals and objectives.
An assembly of people, especially the members of a society or committee, for discussion or entertainment.
What is an example of a characteristic of a successful project?
Defined ownership and responsibility
Vague goals
A timeline that changes frequently
Methodology that is “plan-as-you-go”

## Slide 9: Module Two: Review Questions
What is not an example of a characteristic of a successful project?
Ambiguous communication
Dedicated team
Completion evaluated based on original plan
Supported by an organization’s management team
What can be defined as “the combined art and science of planning, organizing, and managing resources to get a particular project done on time, within budget, and with the results that the organization set out to achieve”?
Meeting planning
Project planning
Office management
Project management

## Slide 10: Module Two: Review Questions
Which of these statements is true of project management?
Project management involves repetitive, permanent, or semi-permanent functional activities to produce products or services.
Project management is just like meeting management, involving a chairperson, minute taker, and attendee participation.
There are many types of project management designed for different scenarios and different industries.
There is only one trusted method for project management, and that method is the traditional method.
What is the definition of a project manager?
The profession involving office supervisory positions.
The person responsible and accountable for accomplishing the stated project objectives.
The person ultimately responsible for the day-to-day operations or an organization.
The person who presides over a meeting, committee, or board.

## Slide 11: Module Two: Review Questions
What is not an example of a key project management responsibility?
Organizing the office before the project begins
Deconstructing the project requirements
Managing the triple constraint for projects
All of the above
What job is the project manager often required to do?
Balancing what the customer wants, and needs with what the team can provide in a particular time frame and with a particular budget.
Focusing on consistent and permanent projects that the company needs on a rolling basis.
Giving a brief explanation of the purpose of the meeting and an idea of what you are looking for in terms of topics.
Maintains focus while writing down information during the project’s many meetings.

## Slide 12: Module Two: Review Questions
Which of these is not a key skill of a project manager?
Excellent at taking orders from the team
Negotiation
Leadership
Stress and anger management
Which of these statement is true of project management?
A successful project manager has a basic skill set and is focused on application of these skills, not on learning new ones.
A project manager is the person who delegates responsibility for accomplishing the stated project objectives.
There is only one type of project management, designed for specific scenarios and specific industries.
One can find uses for most of the project management tools that are discussed in day-to-day life, both personal and professional.

## Slide 13: Module Two: Review Questions
What is the definition of a project?
A planned series of future events, items, or performances.
A meeting of people face to face, especially for consultation.
A limited endeavor that is undertaken to meet particular goals and objectives.
An assembly of people, especially the members of a society or committee, for discussion or entertainment.
What is an example of a characteristic of a successful project?
Defined ownership and responsibility
Vague goals
A timeline that changes frequently
Methodology that is “plan-as-you-go”

## Slide 14: Module Two: Review Questions
What is not an example of a characteristic of a successful project?
Ambiguous communication
Dedicated team
Completion evaluated based on original plan
Supported by an organization’s management team
What can be defined as “the combined art and science of planning, organizing, and managing resources to get a particular project done on time, within budget, and with the results that the organization set out to achieve”?
Meeting planning
Project planning
Office management
Project management

## Slide 15: Module Two: Review Questions
Which of these statements is true of project management?
Project management involves repetitive, permanent, or semi-permanent functional activities to produce products or services.
Project management is just like meeting management, involving a chairperson, minute taker, and attendee participation.
There are many types of project management designed for different scenarios and different industries.
There is only one trusted method for project management, and that method is the traditional method.
What is the definition of a project manager?
The profession involving office supervisory positions.
The person responsible and accountable for accomplishing the stated project objectives.
The person ultimately responsible for the day-to-day operations or an organization.
The person who presides over a meeting, committee, or board.

## Slide 16: Module Two: Review Questions
What is not an example of a key project management responsibility?
Organizing the office before the project begins
Deconstructing the project requirements
Managing the triple constraint for projects
All of the above
What job is the project manager often required to do?
Balancing what the customer wants, and needs with what the team can provide in a particular time frame and with a particular budget.
Focusing on consistent and permanent projects that the company needs on a rolling basis.
Giving a brief explanation of the purpose of the meeting and an idea of what you are looking for in terms of topics.
Maintains focus while writing down information during the project’s many meetings.

## Slide 17: Module Two: Review Questions
Which of these is not a key skill of a project manager?
Excellent at taking orders from the team
Negotiation
Leadership
Stress and anger management
Which of these statement is true of project management?
A successful project manager has a basic skill set and is focused on application of these skills, not on learning new ones.
A project manager is the person who delegates responsibility for accomplishing the stated project objectives.
There is only one type of project management, designed for specific scenarios and specific industries.
One can find uses for most of the project management tools that are discussed in day-to-day life, both personal and professional.

## Slide 18: Module Three: Key Concepts (II)
This module will look at the Project
Management Institute, a global project
management group that publishes and
promotes project management
standards, and its core ideas.
Life is a do-it-yourself project.
Napoleon Hill
Notes: Now that we understand what we mean by projects, project management, and project managers, let’s look at some of the other concepts related to projects. This module will look at the Project Management Institute, a global project management group that publishes and promotes project management standards, and its core ideas.

## Slide 19: The Project Management Institute (PMI)
PMBOK
Project management standards
Techniques
Notes: Project Management Institute (PMI)
The Project Management Institute is a global association for the project management profession. Since being founded in 1969, they have been at the forefront of working with businesses to create project management standards and techniques that work.
Their core ideas include:
The Project Management Body of Knowledge( PMBOK), which we will discuss in a moment
Five process groups, which outline the path a project should take
Ten knowledge areas, which outline various parts of each process group
The triple constraint, which illustrates how a project is balanced
Estimated Time
10 minutes
Topic Objective
To understand what the Project Management Institute is.
Topic Summary
The Project Management Institute is a global association for the project management profession. It was founded in 1969.
Recommended Activity
Discuss other alternatives to the PMI, including:
Association for Project Management, based in the UK
Australian Institute for Project Management
The European Institute of Advanced Project and Contract Management
Asia Pacific Regional Project Management Forum
Project Management Institute South Africa
Stories to Share
The PMI was founded by five volunteers in 1969. In 2008, it had over 260,000 members in 150 different countries.
Delivery Tips
Encourage participants to share other organizations that they are familiar with.

## Slide 20: The Project Management Body Of Knowledge (PMBOK)
Processes and knowledge
Best practices
Standards
Notes: The Project Management Body of Knowledge (PMBOK) is the PMI bible. It includes a detailed overview of the processes and knowledge areas promoted by the PMI as best practice within the project management discipline.
This global standard allows consistent procedures, methods, and processes to be applied to any project and measured equally, no matter what the actual project is about.
The guide is built around five process groups and ten knowledge areas.
Estimated Time
10 minutes
Topic Objective
To understand what the PMBOK is.
Topic Summary
The Project Management Body of Knowledge (PMBOK) is the PMI bible.
Materials Required
Copy of the PMBOK
Planning Checklist
Obtain a copy of the PMBOK before the workshop.
Recommended Activity
Pass around the PMBOK for participants to look at.
Stories to Share
The PMBOK was first drafted in 1986. The first official edition was published in 1994. The latest version of the PMBOK is the 5th Edition.
Delivery Tips
The latest edition of the PMBOK was released in 2008.
Review Questions
What does PMBOK stand for?

## Slide 21: The Five Process Groups
Initiating
Monitoring and Controlling
Closing
Planning
Executing
Notes: These processes form the core structure of any project. Although they are illustrated here as a continuous process, they can overlap and interact throughout a project.
Processes are described in terms of:
Inputs (documents, plans, designs, etc.)
Tools and Techniques (mechanisms applied to inputs)
Outputs (documents, products, etc.)
Estimated Time
10 minutes
Topic Objective
To understand the life cycle of a project.
Topic Summary
The five phases are Initiating, Planning, Executing, Monitoring and Controlling, and Closing.
Materials Required
Prepared sheets of flip chart paper
Sticky notes
Tape
Markers
Planning Checklist
Each sheet of flip chart paper should be divided into five columns. Each column should be headed with a process group name.
Recommended Activity
Divide participants into groups of four to six. Ask each group to write these activities on sticky notes (one activity per note):
Setting project goals
Returning supplies
Deciding who will be on the project team
Building a schedule
Having a success party
Building a prototype widget
Adjusting the schedule due to a worker’s strike
Having weekly status meetings
Installing a new computer system
Setting up the project plan on a computer
Now, ask participants to place the notes in their proper column.
Delivery Tips
We have included the answers in Worksheet One in the activities folder.
Review Questions
Name one process group.

## Slide 22: The Ten Knowledge Areas
Integration
Procurement
Scope
Risk
Time
Quality and Stakeholder
Communications
Cost
Human Resources
Notes: The PMBOK guide focuses on ten knowledge areas that are crucial to the project management processes. The areas are:
Integration Management
Procurement Management
Scope Management
Risk Management
Time Management
Communications Management
Cost Management
Human Resources Management
Quality Management
Stakeholder Management
Each knowledge area contains some or all of the project management processes. For example, Project Procurement Management includes:
Plan Procurement Management
Conduct Procurements
Control Procurements
Close Procurements
Estimated Time
10 minutes
Topic Objective
To understand the ten knowledge areas of the PMBOK.
Topic Summary
The PMBOK guide focuses on ten knowledge areas that are crucial to the project management processes.
Integration Management
Procurement Management
Scope Management
Risk Management
Time Management
Communications Management
Cost Management
Human Resources Management
Quality Management
Stakeholder Management
Materials Required
Copy of the PMBOK
Planning Checklist
Obtain a copy of the PMBOK before the workshop.
Recommended Activity
Choose a few knowledge areas of interest to participants. Look these areas up in the PMBOK. This will spur participants to think of areas of further interest, and it will give them some practical experience with the PMBOK.
Delivery Tips
If you have a small group or several copies of the PMBOK, let participants look through the PMBOK on their own.
Review Questions
Name one of the knowledge areas.

## Slide 23: The Triple Constraint
Schedule
(Time)
Scope
Quality
Customer Satisfaction
Budget (Cost)
Resources
Risk
Notes: The Triple Constraint illustrates the balance of the project’s scope, schedule (time), and budget (cost). During the planning phase of a project, the project management team defines the project scope, schedule (time), and budget (cost)of a project. As the process continues, the project managers discover that there may be changes or adjustments to be made in one of these areas. When this happens, the other factors of the triple constraint are likely to be affected as well.
For example, if the budget (cost) increases, it is logical to assume that the scope and schedule (time) will increase as well. The same thing happens if the budget (cost) decreases; the scope and schedule (time) will decrease too.
It is the job of the project manager, and sometimes the project team, to identify how a change to a single element will change the other elements.
Estimated Time
10 minutes
Topic Objective
To understand the triangle of factors that can affect a project.
Topic Summary
The Triple Constraint illustrates the balance of the project’s scope, schedule (time), and budget (cost).
Materials Required
Flip chart paper
Markers
Planning Checklist
Review the scenarios below before the workshop and come up with some ideas of your own.
Recommended Activity
Discuss the following scenarios with the group. Explore which constraint in each scenario is changing, and how that could affect the other elements.
Budget is reduced by 25%
Building needs to be completed three months earlier
Product must have 99% purity instead of 95%
Need to renovate three office buildings instead of one
Delivery Tips
There are no “right” answers for this activity. The objective is to have participants see how changes can have a ripple effect.
Review Questions
Name one of the triple constraints.

## Slide 24: Module Three: Review Questions
What is the Global Project Institute?
The process of international integration arising from the interchange of world views, products, ideas, and other aspects of culture.
A global association for the project management profession.
The combined art and science of planning, organizing, and managing resources to get a particular project done on time, within budget, and with the results that the organization set out to achieve.
A society or organization having a particular object or common factor, especially a scientific, educational, or social one.
What is included in the Global Project Institute’s core ideas?
The Project Management Body of Management ( PMBOM).
Five process groups, which outline the path a project should take.
Seven knowledge areas, which outline various parts of each process group.
The double constraint, which illustrates how a project is balanced.

## Slide 25: Module Three: Review Questions
Which of these forms the core structure of any project?
The Five Process Groups
The Five Management Groups
The Four Process Groups
The Four Management Groups
Which of these is a term that could describe the processes?
Means
Products
Amounts
Inputs

## Slide 26: Module Three: Review Questions
How many knowledge areas are crucial to the project management processes?
Thirteen
Ten
Nine
Three
What is not a knowledge area the PMBOK focuses on?
Integration
Settlement
Scope
Procurement

## Slide 27: Module Three: Review Questions
Which of these does Project Procurement Management include?
Elements
Predictions
Human Resources
Contract Administration
What illustrates the balance of the project’s scope, schedule (time), quality, and cost?
The triple constraint
The double constraint
Solicitation Planning
Procurement Planning

## Slide 28: Module Three: Review Questions
During the planning phase of a project, who defines the scope, time, cost, and quality?
Human resources
Solicitation team
Planning resources
Project Management Team
What is the job of the project manager?
To take on long term, permanent projects that are managed on an ongoing basis.
To balance day-to-day office management with project planning.
To identify how a change to a single element will change the other elements.
To procure funds for the projects that are being managed.

## Slide 29: Module Three: Review Questions
What is the Global Project Institute?
The process of international integration arising from the interchange of world views, products, ideas, and other aspects of culture.
A global association for the project management profession.
The combined art and science of planning, organizing, and managing resources to get a particular project done on time, within budget, and with the results that the organization set out to achieve.
A society or organization having a particular object or common factor, especially a scientific, educational, or social one.
What is included in the Global Project Institute’s core ideas?
The Project Management Body of Management ( PMBOM).
Five process groups, which outline the path a project should take.
Seven knowledge areas, which outline various parts of each process group.
The double constraint, which illustrates how a project is balanced.

## Slide 30: Module Three: Review Questions
Which of these forms the core structure of any project?
The Five Process Groups
The Five Management Groups
The Four Process Groups
The Four Management Groups
Which of these is a term that could describe the processes?
Means
Products
Amounts
Inputs

## Slide 31: Module Three: Review Questions
How many knowledge areas are crucial to the project management processes?
Thirteen
Ten
Nine
Three
What is not a knowledge area the PMBOK focuses on?
Integration
Settlement
Scope
Procurement

## Slide 32: Module Three: Review Questions
Which of these does Project Procurement Management include?
Elements
Predictions
Human Resources
Contract Administration
What illustrates the balance of the project’s scope, schedule (time), quality, and cost?
The triple constraint
The double constraint
Solicitation Planning
Procurement Planning

## Slide 33: Module Three: Review Questions
During the planning phase of a project, who defines the scope, time, cost, and quality?
Human resources
Solicitation team
Planning resources
Project Management Team
What is the job of the project manager?
To take on long term, permanent projects that are managed on an ongoing basis.
To balance day-to-day office management with project planning.
To identify how a change to a single element will change the other elements.
To procure funds for the projects that are being managed.

## Slide 34: Module Four: Initiation (I)
The first phase of project management
is initiation.
This module will explore the first part
of that process: identifying what
success will look like for your particular
project.
No sensible decision can be made without taking into account not only the world as it is, but the world as it will be.
Isaac Asimov
Notes: The first phase of project management is initiation. This is where the project starts to take shape. Stakeholders and team member’s work together to identify wants and needs, and then the project team creates a plan to accomplish the objectives with the time and budget available. This module will explore the first part of that process: identifying what success will look like for your particular project.

## Slide 35: Identifying Your Stakeholders
Has an interest
Feedback
Guidance
Who might be affected?
Notes: A stakeholder is someone who has an interest in the development and/or outcome in the project. This person is usually only involved at key project gateways, such as project initiation and evaluation. Their main role is to provide feedback and guidance.
When you are identifying stakeholders, think outside the box. Ask other members of the team and the organization, “Who else should we involve in this? Who might be affected?”
If it turns out you missed a stakeholder, ask them for their feedback. You may not be able to change the project’s course at that point, but you may receive valuable information on possible opportunities or potential issues.
Estimated Time
5 minutes
Topic Objective
To understand what is meant by the term “stakeholder” in project management.
Topic Summary
A stakeholder is someone who has an interest in the development and/or outcome in the project.
Materials Required
Worksheet Two Case Study
Module Four Questions from Worksheet Two
Planning Checklist
Print out one copy of the Worksheet Two Case Study and the Module Four Questions for each participant.
Recommended Activity
Divide participants into pairs. Ask them to review the case study and identify possible stakeholders.
Stories to Share
The word “stakeholder” dates from the early 1700’s. It originally meant, “a person who holds the stake(s) in a bet.”
Delivery Tips
If there is time, bring the large group back together, and discuss results.
Review Questions
Encourage participants to think of some stakeholders for their project.

## Slide 36: Assessing Needs and Wants
Decide which items are necessary (needs)
“nice to haves” (wants)
Prioritize the needs
Notes: When stakeholders and other project members begin identifying the goals of the project, encourage them to list any and all possibilities. If the sky is the limit, what would they want the project to accomplish?
Then, they should decide which items are necessary for the project’s success (needs), and which are “nice to haves” (wants). If the list is lengthy, wants and needs can be prioritized to help the project team identify the most important tasks. (Remember, this is not a final list, just brainstorming to kick things off.)
To wow your stakeholders, keep this list on hand during the project. Keep an eye out for ways to incorporate wants and maximize their value.
Estimated Time
10 minutes
Topic Objectives
To understand the difference between needs and wants.
To understand how to use “wants” to deliver maximum value.
Topic Summary
When stakeholders and other project members begin identifying the goals of the project, encourage them to list any and all possibilities.
Then, they should decide which items are necessary for the project’s success (needs), and which are “nice to haves” (wants).
Materials Required
Worksheet Two Case Study
Module Four Questions from Worksheet Two
Planning Checklist
Print out one copy of the Worksheet Two Case Study and the Module Four Questions for each participant.
Recommended Activity
Divide the class into teams of ten. Then, divide each team into two parts. Ask one half of the team to take on the role of project team members, and the other half to take on the role of stakeholders. (You may want the team members to elect a project manager too.) Then, have the teams work together to identify needs and wants.
Stories to Share
Wants and needs analysis is a useful tool for many applications.
Delivery Tips
If there is time, have each group present a brief list of their wants and needs.
Review Questions
How can you use wants to wow your stakeholders?

## Slide 37: Setting a SMART Project Goal
Specific
Measurable
Relevant
Timed
Agreed Upon
Notes: Each project should have a goal statement. SMART is a convenient acronym for the set of criteria that a goal must have in order for it to be realized by the goal achiever.
Specific: In order for the project team to achieve a goal, stakeholders must be very clear about what they want. As Jack Canfield says, “Vague goals produce vague results.”
Measurable: It’s crucial that you are able to track your progress towards your goal. That’s why all goals need some form of objective measuring system so that you can stay on track and become motivated when you enjoy the sweet taste of quantifiable progress.
Agreed Upon: All team members and stakeholders must agree on the goal.
Relevant: The goal must be relevant to the business’ purpose.
Timed: In order for a project to be considered a project, it must have a specific start and end date.
Some examples of good project goals:
To upgrade the existing sales system to EasySell 5.1 by January 1, 2015.
To begin production of a new widget by September 1, 2016.
To build a new 5,000 square foot office facility and have all staff relocated to it by December 31, 2015.
Estimated Time
10 minutes
Topic Objective
To understand how to write a good project goal.
Topic Summary
Project goals should be SMART.
Specific
Measurable
Agreed upon
Relevant
Timed
Materials Required
Worksheet Two Case Study
Module Four questions from Worksheet Two
Planning Checklist
Print out one copy of the Worksheet Two Case Study and the Module Four questions for each participant.
Recommended Activity
Ask participants to pair off and write a SMART goal for the case study.
Stories to Share
SMART goals can be used to help individuals achieve things, too.
Delivery Tips
After a few minutes, bring the group back together and write a SMART goal as a group.
Review Questions
What does SMART stand for?

## Slide 38: Creating Requirements and Deliverables
What a project must do in order for it to be considered successful
Define what people can expect to hold in their hands after the project is complete
Notes: Now that we have some idea of what we want our project to accomplish, we can begin setting requirements. Requirements outline exactly what a project must do in order for it to be considered successful. Remember, good requirements are highly specific. Although they are particularly useful in IT projects, they should be used for any project that you want to succeed.
For example, let’s say one goal for our project is this: “To reduce the time to process inbound orders to 15 minutes by January 1, 2015.” A corresponding project requirement could be, “Implement version 5.0 of Superior Records Processing on all 14 customer service representative stations.”
As part of this, you should then be able to create your deliverables. These define what people can expect to hold in their hands after the project is complete. These deliverables will help you set clear expectations at the beginning of your project, and maintain a clear idea of what you are doing as you execute the project.
Estimated Time
10 minutes
Topic Objective
To understand how to frame project requirements and deliverables.
Topic Summary
Requirements outline exactly what a project must do in order for it to be considered successful. Deliverables define what people can expect to hold in their hands after the project is complete.
Materials Required
Worksheet Two Case Study
Module Four questions from Worksheet Two
Planning Checklist
Print out one copy of the Worksheet Two Case Study and the Module Four questions for each participant.
Recommended Activity
Ask participants to pair off and write two requirements and two deliverables for their case study.
Stories to Share
Requirements are most often used in technology-based projects, but can be useful in other areas.
Delivery Tips
Examples of requirements:
Computer application must support graphic reporting
Office building must have air conditioning
Examples of deliverables:
Installation of EzeeReports 2.5 on 400 systems by September20, 2031
Refurbishment of current heating system to provide heat, air conditioning, humidification, and dehumidification, to be complete by January 1, 2015
Review Questions
What is the difference between a requirement and deliverable?

## Slide 39: Module Four: Review Questions
What is the first phase of project management?
Foundation
Prophase
Initiation
Induction
What is the definition of a stakeholder?
The supervisor who must take responsibility for and is accountable for the success or failure of their particular operation.
Someone who has an interest in the development and/or outcome in the project.
Someone who competes against or fights another in a contest, game, or argument; a rival or adversary.
A person who supervises a person or an activity.

## Slide 40: Module Four: Review Questions
If it turns out that you missed a stakeholder, why should you ask them for their feedback?
You may receive valuable information on possible opportunities or potential issues.
You will be able to change the project’s course at that point.
You will be able to initiate other projects in the future with this person.
You will save the company on time and cost.
When stakeholders and other project members begin identifying the goals of the project, what is the first step should you take?
Work on creating your deliverables.
Get all team members and stakeholders to agree on the goals.
Assemble an outside team to list any and all possibilities.
Encourage them to list any and all possibilities.

## Slide 41: Module Four: Review Questions
What does the “M” in the SMART acronym stand for?
Meaningful
Measurable
Money-making
Matter-of-fact
According to Jack Canfield, what do vague goals produce?
Specific goals
Clear planning
Vague results
Vague stakeholders

## Slide 42: Module Four: Review Questions
In order for a project to be considered a project what does it need?
A transitory name and title
Extra funding to prepare for possible emergencies
A specific start and end date
A vague purpose and results
What is not an example of a good project goal?
To upgrade the existing sales system to EasySell 5.1 by January 1, 2010.
To begin production of a new widget by September 1, 2011.
To build a new 5,000 square foot office facility and have all staff relocated to it by December 31, 2010.
To design a new data entry system to a future buyer at a time to be determined.

## Slide 43: Module Four: Review Questions
Which of these statements is true about setting requirements?
Requirements outline exactly what a project must do in order for it to be considered successful.
Good requirements are at least somewhat specific.
They should not be used for just any project, but are particularly useful in IT projects.
When it comes to requirements it is best to be vague in order to not miss important deadlines.
Which of these describes deliverable?
They define what people can expect to hold in their hands after the project is complete.
They define the goals set by the project management team.
They help you set clear expectations at the end of your project.
They maintain a clear idea of what the stakeholders should be executing.

## Slide 44: Module Four: Review Questions
What is the first phase of project management?
Foundation
Prophase
Initiation
Induction
What is the definition of a stakeholder?
The supervisor who must take responsibility for and is accountable for the success or failure of their particular operation.
Someone who has an interest in the development and/or outcome in the project.
Someone who competes against or fights another in a contest, game, or argument; a rival or adversary.
A person who supervises a person or an activity.

## Slide 45: Module Four: Review Questions
If it turns out that you missed a stakeholder, why should you ask them for their feedback?
You may receive valuable information on possible opportunities or potential issues.
You will be able to change the project’s course at that point.
You will be able to initiate other projects in the future with this person.
You will save the company on time and cost.
When stakeholders and other project members begin identifying the goals of the project, what is the first step should you take?
Work on creating your deliverables.
Get all team members and stakeholders to agree on the goals.
Assemble an outside team to list any and all possibilities.
Encourage them to list any and all possibilities.

## Slide 46: Module Four: Review Questions
What does the “M” in the SMART acronym stand for?
Meaningful
Measurable
Money-making
Matter-of-fact
According to Jack Canfield, what do vague goals produce?
Specific goals
Clear planning
Vague results
Vague stakeholders

## Slide 47: Module Four: Review Questions
In order for a project to be considered a project what does it need?
A transitory name and title
Extra funding to prepare for possible emergencies
A specific start and end date
A vague purpose and results
What is not an example of a good project goal?
To upgrade the existing sales system to EasySell 5.1 by January 1, 2010.
To begin production of a new widget by September 1, 2011.
To build a new 5,000 square foot office facility and have all staff relocated to it by December 31, 2010.
To design a new data entry system to a future buyer at a time to be determined.

## Slide 48: Module Four: Review Questions
Which of these statements is true about setting requirements?
Requirements outline exactly what a project must do in order for it to be considered successful.
Good requirements are at least somewhat specific.
They should not be used for just any project, but are particularly useful in IT projects.
When it comes to requirements it is best to be vague in order to not miss important deadlines.
Which of these describes deliverable?
They define what people can expect to hold in their hands after the project is complete.
They define the goals set by the project management team.
They help you set clear expectations at the end of your project.
They maintain a clear idea of what the stakeholders should be executing.

## Slide 49: Module Five: Initiation (II)
This module will look at four key
project documents: the statement of
work, the project requirements
document, the project planning
worksheet, and the project charter.
All you need is the plan, the road map, and the courage to press on to your destination.
Earl Nightingale
Notes: All you need is the plan, the road map, and the courage to press on to your destination.
Earl Nightingale
Once you have an idea of who your stakeholders are and what the project will achieve, it’s time to put it all in writing. This module will look at four key project documents: the statement of work, the project requirements document, the project planning worksheet, and the project charter.

## Slide 50: Creating a Statement of Work
Defines what the project will do
When it will be done
Contract of expectations
Notes: What is the Statement of Work? The SOW defines what the project will do and when it will be done. It forms a binding contract of expectations between all project stakeholders. As such, it should be created by the project team, and then signed off by the team and the stakeholders. It can be used to create other project documents, including the project charter. The Statement of Work often varies widely between organizations. However, the following basic elements should be included.
Project Team: Include all members of the project team and each person’s role, as well as a list of stakeholders and the sponsor.
Project Details: Include the name of the project, its estimated start and end date, and the client(s) involved. (Every project should have a client, whether it is an internal or external customer.)
Purpose: What is the purpose of the project? Try to keep this as simple and concrete as possible. If a business case or a cost-benefit analysis has been prepared, those documents should be referenced (but not included) here.
Scope: What will the project encompass? What items will the project not encompass? This section is extremely important as it will help avoid miscommunication and disappointment down the road.
Goals, Deliverables, and Requirements: Include your SMART goals, deliverables, and requirements here.
Basic Finances: List applicable rate and payment schedule information.
Assumptions: List any assumptions that have been made in the planning thus far.
Agreements: List any agreements that will apply to this project, such as union contracts or professional service agreements.
Estimated Time
10 minutes
Topic Objective
To understand what the Statement of Work is.
Topic Summary
The Statement of Work defines what the project will do and when it will be done.
Materials Required
List of SOW elements
Planning Checklist
Have a copy of the SOW elements (listed on the previous page) on flip chart or PowerPoint slides.
Recommended Activity
Discuss what SOW elements participants would customize for their organization.
Stories to Share
The Statement of Work can take many different forms. Encourage participants to do research on standards for their industry.
Delivery Tips
This list is also in the Student Training Guide.
Review Questions
True or False: The SOW must contain the same elements no matter where or how it is used.

## Slide 51: Completing the Project Planning Worksheet
Project Planning Worksheet |  | 
Part I: Basic Information |  | 
Project Name: |  | Project Team Members:
Estimated Project Start Date: |  | 
Estimated Project End Date: |  | 
Budget Amount (if known): |  | 
Part II: Project Goals |  | 
List your SMART goals here. |  | 
Part III: Milestones |  | 
Milestone | Target Completion Date | 
Approved by: |  | 
Notes: Once the basics of the project are laid out, it’s time to put together your project planning worksheet. While the Statement of Work will remain static throughout the project, your worksheet will be a living, breathing document. As such, there are parts that you will not complete until after the Planning phase, but this worksheet will give you one place to capture the essential information about your project.
Like the SOW, you may need different fields based on your project and your organization, but we have included a sample worksheet on the next page.
Estimated Time
10 minutes
Topic Objective
To understand what a project planning worksheet looks like.
Topic Summary
This worksheet will give you one place to capture the essential information about your project.
Materials Required
Sample Project Planning Worksheet template
Planning Checklist
Have copies of the Project Planning Worksheet template (shown on the next page) available for participants to review.
Recommended Activity
As a large group, review the Project Planning Worksheet. Encourage participants to identify customizations and changes.
Delivery Tips
This sample is also in the Student Training Guide.
Review Questions
List one piece of information that should be included in the Project Planning Worksheet.
Project Planning Worksheet
Part I: Basic Information
Project Name:
Project Team Members:
Estimated Project Start Date:
Estimated Project End Date:
Budget Amount (if known):
Part II: Project Goals
List your SMART goals here.
Part III: Milestones
Milestone
Target Completion Date
Approved by:

## Slide 52: Completing the Project Charter
Formal project document
Establishes the project as an entity
Customized for your organization
Notes: The project charter is the final, formal project document. It establishes the project as an entity and it gives the project manager the authority to get started. For small projects, the charter may be just a few pages. For large projects, the charter itself can be hundreds of pages and can take months to build.
Just like other project documents, the charter can be customized for your organization. At a minimum, it should include the following information:
Project name
Project due date
Team list, including responsibility matrix
Stakeholders
In scope and out of scope items
Goals
Requirements
Deliverables
Estimated cost vs. budget
Benefits of project (including cost-benefit analysis if appropriate)
Milestone descriptions and dates
Possible risks and opportunities
Communication plans
Assumptions and Constraints
Plans for documenting lessons learned
A page for sign off by the important parties
Ask your organization if they have a charter form that they would like you to use. This is especially important as a charter can be a legally binding document.
Estimated Time
10 minutes
Topic Objective
To understand what the project charter is.
Topic Summary
The project charter is the final, formal project document. It establishes the project as an entity and it gives the project manager the authority to get started.
Materials Required
Project charter examples
Planning Checklist
Prior to the workshop, gather examples of completed project charters and/or templates.
Recommended Activity
Review the various examples with the class. Encourage discussion about what elements they would use, and which they would change.
Delivery Tips
Make sure to obtain proper permissions for the materials you gather.
Review Questions
What is the difference between the charter and the SOW?

## Slide 53: Module Five: Review Questions
Once you have an idea of who your stakeholders are and what the project will achieve, what is the next step?
Achieve the deliverables
Assemble your project management team
Put it all in writing
End the project
What is the statement of work?
The SOW is a basis report on three types of financial activities: operating activities, investing activities, and financing activities.
The SOW is a statement which stakeholders create for the project management team.
The SOW defines the vague overall meaning of the work and is also specific enough that it conveys your unique interpretation.
The SOW defines what the project will do and when it will be done.

## Slide 54: Module Five: Review Questions
Who signs off on the statement of work?
The project management team
The stakeholders
Human resources and upper management
Both a & b
Which of these is not included in the project details?
Name of the project
The products needed
Its estimated state and end date
The client(s) involved

## Slide 55: Module Five: Review Questions
What question does ‘scope’ answer in the statement of work?
What will the project encompass?
What are our deliverables, goals, and requirements?
What is the purpose of the project?
Who is on the project management team?
Which of these statements is true of the project planning worksheet?
It remains static throughout the project.
It is a living, breathing document.
It is never complete.
It gives you several places to capture the essential information about your project.

## Slide 56: Module Five: Review Questions
How is the project planning worksheet similar to the statement of work?
They are both produced by the stakeholders.
They both must be signed off on by a number of supervisors.
In both, you may need different fields based on your project.
In both, you may need to be vague for the betterment of the project.
What is the final, formal project document?
The project planning worksheet
The project planning team
The project charter
The statement of work

## Slide 57: Module Five: Review Questions
How long should the project charter be?
It varies from a few pages to hundreds.
It varies from ten to fifteen pages.
It varies from one hundred to five hundred pages.
It is varies, but is never over one hundred pages.
Which of these would not be included in the project charter?
Estimated cost vs. budget
In house and out of house items.
Milestone descriptions and dates.
Communication plans.

## Slide 58: Module Five: Review Questions
Once you have an idea of who your stakeholders are and what the project will achieve, what is the next step?
Achieve the deliverables
Assemble your project management team
Put it all in writing
End the project
What is the statement of work?
The SOW is a basis report on three types of financial activities: operating activities, investing activities, and financing activities.
The SOW is a statement which stakeholders create for the project management team.
The SOW defines the vague overall meaning of the work and is also specific enough that it conveys your unique interpretation.
The SOW defines what the project will do and when it will be done.

## Slide 59: Module Five: Review Questions
Who signs off on the statement of work?
The project management team
The stakeholders
Human resources and upper management
Both a & b
Which of these is not included in the project details?
Name of the project
The products needed
Its estimated state and end date
The client(s) involved

## Slide 60: Module Five: Review Questions
What question does ‘scope’ answer in the statement of work?
What will the project encompass?
What are our deliverables, goals, and requirements?
What is the purpose of the project?
Who is on the project management team?
Which of these statements is true of the project planning worksheet?
It remains static throughout the project.
It is a living, breathing document.
It is never complete.
It gives you several places to capture the essential information about your project.

## Slide 61: Module Five: Review Questions
How is the project planning worksheet similar to the statement of work?
They are both produced by the stakeholders.
They both must be signed off on by a number of supervisors.
In both, you may need different fields based on your project.
In both, you may need to be vague for the betterment of the project.
What is the final, formal project document?
The project planning worksheet
The project planning team
The project charter
The statement of work

## Slide 62: Module Five: Review Questions
How long should the project charter be?
It varies from a few pages to hundreds.
It varies from ten to fifteen pages.
It varies from one hundred to five hundred pages.
It is varies, but is never over one hundred pages.
Which of these would not be included in the project charter?
Estimated cost vs. budget
In house and out of house items.
Milestone descriptions and dates.
Communication plans.

## Slide 63: Module Six: Planning (I)
Now it’s time to plan the nuts and bolts
of your project.
When building your plan, remember:
Everything in the plan is a prediction.
The only fact that you know for certain is that your plan is definitely not 100% right.
Contingency needs to be built in to cope with the uncertainty.
Those who fail to plan, plan to fail.
Anonymous
Notes: Those who fail to plan, plan to fail.
Anonymous
Congratulations! With the completion of the SOW, planning worksheet, and project charter, the initiation phase is complete. Now it’s time to plan the nuts and bolts of your project. When building your plan, remember:
Everything in the plan is a prediction.
The only fact that you know for certain is that your plan is definitely not 100% right.
Contingency needs to be built in to cope with the uncertainty.

## Slide 64: Managing Expectations
Functionality
Effort (Time & Cost)
Delivery Date
Quality
Notes: Each stakeholder and each project team member will have different expectations. As the project manager, you need to manage all of them. Unmanaged expectations will cause conflict and can cause the project to fail.
Expectations fall into four main categories:
Expectations for each area should be addressed in the Statement of Work, Project Planning Worksheet, and Project Charter.
Periodically reviewing these documents is important. Key checkpoints should include:
Does everyone involved have the same understanding of the project?
Clarify responsibilities as assigned
Clarify the outcomes and time frame
Clarify the requirements and budgets
Understand the budget and schedule linkages
Communicate to everyone who is relevant
Estimated Time
10 minutes
Topic Objective
To understand the four categories of expectations and how to manage them.
Topic Summary
Expectations fall into four main categories:
Functionality
Effort (time and cost)
Delivery date
Quality
Materials Required
Worksheet Two Case Study
Module Six Questions from Worksheet Two
Planning Checklist
Print out one copy of the Worksheet Two Case Study and the Module Six Questions for each participant.
Recommended Activity
Divide participants into groups of four to six. Ask each group to identify possible expectations from stakeholders and project team members.
Delivery Tips
Teams can be divided into stakeholders and team members if you desire.
Review Questions
What are the four categories of expectations?

## Slide 65: Creating a Task List
Details
Write in the order of tasks
Be aware of micro-managing
Notes: To begin the nuts-and-bolts planning process, you must first make a list of all the tasks that are going to be done. Let’s say you are going to paint a room. Tasks might include:
Get paint samples
Choose a paint color
Remove all furniture
Take off trim
Paint trim
Apply first coat
Apply second coat
Put trim back in
Put all furniture back in
How detailed the task list becomes is up to you. We suggest writing the task list in the way that you will accomplish it. For example, if you are going to apply the first coat of paint yourself; you may want to include all steps, such as crack-filling, sanding, taping, etc. If, however, you are contracting the task out, “Apply first coat” may be the only item you need to monitor. (Your painter probably wouldn’t appreciate being micro-managed!)
Estimated Time
10 minutes
Topic Objective
To understand how to identify the work to be done in a project.
Topic Summary
To begin the nuts-and-bolts planning process, you must first make a list of all the tasks that are going to be done.
Materials Required
Flip chart paper
Markers
Worksheet Two Case Study
Planning Checklist
Print out one copy of the Worksheet Two Case Study for each participant.
Recommended Activity
Work with the group to identify a list of tasks for the case study. Tasks can be kept at a high level.
Delivery Tips
This activity can also be performed in small groups.
After the activity is over, write out a final list of tasks on flip chart paper.

## Slide 66: Estimating Time
Tm
Probable Time
To
Optimistic Time
Calculated Time (Best Estimate)
Tp
Pessimistic Time
Te
To + 4Tm + Tp
6
Te =
Notes: When building your schedule, never guess times. Gather the most reliable information possible and use a scientific formula to get the best estimate. The better your estimates, the more reliable your plan will be.
This formula is considered the standard for estimating time (Te):
To+4Tm+Tp
6
Tm= Probable Time
To= Optimistic Time
Tp=Pessimistic Time
Te=Calculated Time (Best Estimate)
First, make a table, list your tasks, and fill in the estimated time for each. (We have numbered our tasks in the example on the next page for easy identification.) Time can be listed in minutes, hours, days, weeks, months, or years. You should keep the same time scale for each task.
Next, identify what the best and worst case estimates would be. Now, for each task, plug the numbers into the formula given above. The result is the estimated time.
Task
Probable Time
Optimistic Time
Pessimistic Time
Calculated Time
Get paint samples
Choose a paint color
Remove all furniture
Take off trim
Paint trim
Apply first coat
Apply second coat
Put trim back in
Put all furniture back in
Estimated Time
10 minutes
Topic Objective
To understand how to calculate estimated times for tasks.
Topic Summary
This formula is considered the standard for estimating time (Te):
To+4Tm+Tp
6
Materials Required
Worksheet Two Case Study
Module Six questions from Worksheet Two
Planning Checklist
Print out one copy of the Worksheet Two Case Study and the Module Six questions for each participant.
Recommended Activity
Pair participants off. Have them copy the task list created in the previous topic to the worksheet. Then, have them estimate time for each task.
Stories to Share
There is also a basic three-point formula that takes the three numbers and averages them. Most project managers find the weighted formula (used here) to be more accurate.
Delivery Tips
Prepare your own worksheet while participants are doing the activity.
Review Questions
What does Tm represent?

## Slide 67: Estimating Resources
People
Material
Money
Notes: Now that the task list is complete, it’s time to decide what resources will be used to accomplish the tasks. In project management, “resources” means people, materials, and money. For now, let’s just focus on people and materials – we’ll look at money in a moment.
A common method of resource listing is to list the tasks, estimated time, and resources required, all in the same table. We have started an example here.
Task
Calculated Time
People Required
Materials Required
Get paint samples
1 hour
Me, Joe
Car
Choose a paint color
2 hours
Me, Joe
Paint Samples
Remove all furniture
1 hour
Take off trim
½ hour
Paint trim
1 hour
Apply first coat
2 hours
Apply second coat
2 hours
Put trim back in
½ hour
Put all furniture back in
1 hour
How detailed you get with your resource list is up to you. For people resources, make sure you include all people who are going to be spending their time on the project, even yourself.
Estimated Time
10 minutes
Topic Objective
To understand what the term “resources” means in project management.
Topic Summary
In project management, “resources” means people, materials, and money. For now, let’s just focus on people and materials.
Materials Required
Worksheet Two Case Study
Module Six questions from Worksheet Two
Planning Checklist
Print out one copy of the Worksheet Two Case study and the Module Six questions for each participant.
Recommended Activity
Divide participants into groups of four to six. Ask participants to list people and things that will be required to complete this project.
Review Questions
What are the three types of resources?

## Slide 68: Estimating Costs
Salary
Material
Resources
Notes: Our next step is to add cost information to our table. Make sure to include salary information for everyone, even project team members, and to include line item cost information for each material resource. If you are doing a home project (as we are here), salary information will not be necessary.
Task
Calculated Time
People Required
Estimated Cost for People
Materials Required
Estimated Cost for Resources
Get paint samples
1 hour
Sue, Joe
$0
Car
$10 (gas)
Choose a paint color
2 hours
Sue, Joe
$0
Paint Samples
$0
Remove all furniture
1 hour
Take off trim
½ hour
Paint trim
1 hour
Apply first coat
2 hours
Apply second coat
2 hours
Put trim back in
½ hour
Put all furniture back in
1 hour
Estimated Time
10 minutes
Topic Objective
To understand what project costs can encompass.
Topic Summary
Cost information should include the price for materials, as well as salaries and fees for people working on your project.
Materials Required
Flip chart paper
Markers
Worksheet Two Case Study
Planning Checklist
Print out one copy of the Worksheet Two Case Study for each participant.
Recommended Activity
In a large group, brainstorm some costs that would need to be considered for this project.
Stories to Share
This is intended to be a high-level overview of costs. Building a full project budget can be a difficult task, and is out of the scope of this course.
Delivery Tips
This activity can also be performed in small groups.

## Slide 69: Module Six: Review Questions
When building a plan, what is important to remember?
At least half of the plan is a prediction.
The only fact you know for certain is that your plan is 100% right.
There is no room for vagueness as deadlines and outcomes will not change.
Contingency needs to be built in to cope with the uncertainty.
What can unmanaged expectations cause?
Conflict
The project to succeed
Improved time management
A new statement of work to be written

## Slide 70: Module Six: Review Questions
Which of these is a main category that expectations fall into?
Communication
Product management
Delivery date
Quantity
Which of these is not a key checkpoint to include when reviewing documents?
Clarify the outcomes and time frame.
Clarify the requirements and budgets.
Understand the budget and schedule linkages.
Communicate to everyone no matter what their relevance.

## Slide 71: Module Six: Review Questions
What is a good suggestion for writing the task list?
Write the task list before the statement of work is written.
Write the task list in the way that you will accomplish it.
Write the task list as you are completing each task.
Write the task list in the same manner you would your project charter.
When building your schedule, what should you never do?
Make concrete plans
Use outside help
Guess times
Estimate deliverables

## Slide 72: Module Six: Review Questions
What does the Te in the formula used for estimating time represent?
Calculated Time
Pessimistic Time
Optimistic Time
Probable time
What is the first thing you should do when properly estimating time?
Keep the same time scale for each task.
Identify what the best and worst case estimates would be.
Plug the numbers into the formula for estimating time.
Make a table, list your tasks, and fill in the estimated time for each.

## Slide 73: Module Six: Review Questions
In project management, what does “resources” mean?
Staff room, meeting, and deliverables.
People, materials, and money.
Materials, execution, and profit.
Stakeholders, statement of work, and end product.
What is a common method of resource listing?
List the tasks, estimated time, and resources required.
List the assumptions, agreements, and estimated time required.
List the resources, materials, and profits required.
List the tasks, agreements, and materials required.

## Slide 74: Module Six: Review Questions
When building a plan, what is important to remember?
At least half of the plan is a prediction.
The only fact you know for certain is that your plan is 100% right.
There is no room for vagueness as deadlines and outcomes will not change.
Contingency needs to be built in to cope with the uncertainty.
What can unmanaged expectations cause?
Conflict
The project to succeed
Improved time management
A new statement of work to be written

## Slide 75: Module Six: Review Questions
Which of these is a main category that expectations fall into?
Communication
Product management
Delivery date
Quantity
Which of these is not a key checkpoint to include when reviewing documents?
Clarify the outcomes and time frame.
Clarify the requirements and budgets.
Understand the budget and schedule linkages.
Communicate to everyone no matter what their relevance.

## Slide 76: Module Six: Review Questions
What is a good suggestion for writing the task list?
Write the task list before the statement of work is written.
Write the task list in the way that you will accomplish it.
Write the task list as you are completing each task.
Write the task list in the same manner you would your project charter.
When building your schedule, what should you never do?
Make concrete plans
Use outside help
Guess times
Estimate deliverables

## Slide 77: Module Six: Review Questions
What does the Te in the formula used for estimating time represent?
Calculated Time
Pessimistic Time
Optimistic Time
Probable time
What is the first thing you should do when properly estimating time?
Keep the same time scale for each task.
Identify what the best and worst case estimates would be.
Plug the numbers into the formula for estimating time.
Make a table, list your tasks, and fill in the estimated time for each.

## Slide 78: Module Six: Review Questions
In project management, what does “resources” mean?
Staff room, meeting, and deliverables.
People, materials, and money.
Materials, execution, and profit.
Stakeholders, statement of work, and end product.
What is a common method of resource listing?
List the tasks, estimated time, and resources required.
List the assumptions, agreements, and estimated time required.
List the resources, materials, and profits required.
List the tasks, agreements, and materials required.

## Slide 79: Module Seven: Planning (II)
The next part of the planning phase is
to bring together the nuts and bolts
information that we have gathered (the
tasks to be performed, plus the time,
resources, and costs required for each)
and to create an actual plan for
executing the project.
A work well begun is half ended.
Plato
Notes: A work well begun is half ended.
Plato
The next part of the planning phase is to bring together the nuts and bolts information that we have gathered (the tasks to be performed, plus the time, resources, and costs required for each) and to create an actual plan for executing the project.

## Slide 80: Building the Work Breakdown Structure
Project Title
Task 1
Task 1.1
Task 1.2
Task 2
Task 2.1
Task 1.1.1
Notes: A work breakdown structure (WBS) is a graphical breakdown of all the work to be done in the project.
The WBS can be built in five easy steps.
Identify the purpose of the project and write the title at the top.
Establish the major segments of the work. Example for painting a room:
Gather materials
Prepare room
Paint room
Finish room
Break down the segments of the work into sub-components.
Gather materials
Prepare room
Paint room
Finish room
Continue breaking down the work until you reach the level where you will assign and monitor the project work. (Remember, if you are going to assign a task to someone, you may not need to break it down very far.)
Review the WBS with the stakeholders and project team to ensure all items are covered.
Estimated Time
10 minutes
Topic Objective
To understand what the Work Breakdown Structure is.
Topic Summary
A work breakdown structure (WBS) is a graphical breakdown of all the work to be done in the project.
Materials Required
List of tasks from Module Six, Creating a Task List
Sticky notes
Blank sheets of flip chart paper
Markers
Recommended Activity
Divide participants into groups of four to six. Ask each group to copy the list of tasks onto sticky notes (one task per note). Then, ask participants to build a work breakdown structure.
Stories to Share
This tool was originally developed by the United States military in the 1950’s.
Delivery Tips
If your class is small, this activity can be performed in a large group.
Review Questions
What does WBS stand for?

## Slide 81: Creating the Schedule
Perform activities simultaneously
Indicate milestones
Include deliverables
Include lag and lead time
Notes: The next task is to build the schedule. This will be your most important document during the project. It will grow and change throughout the project. Keep it up to date to make sure that you will meet your deadlines.
There are many scheduling tools available, which will be discussed in the next topic. For now, let’s look at a simple table format – an expansion of the table that we used earlier.
The first column lists the tasks that need to be performed. This list is typically organized in the order in which the tasks will be accomplished chronologically. In addition, think of how the project might be broken up into phases, to help subdivide tasks that will be performed.
The second column specifies the duration time of each task listed. This duration might be listed in terms of days, weeks, or hours, depending on the project. Next, people and equipment will be listed, followed by start and end dates and/or times.
In order to build the schedule, you will need the availability of people and machines, and sometimes material resources. This is where graphic tools can really help out.
For our room-painting project, Joe and Sue are going to do all the work. We are going to start on Friday at 5 p.m. Here is a summary of their availabilities:
Friday
Saturday
Joe
5 p.m.-10 p.m.
9 a.m.-10 a.m.
1 p.m.-5 p.m.
Sue
5 p.m.-10 p.m.
10 a.m.-noon
1 p.m.-5 p.m.
Here is an example schedule for our room-painting project.
Task
Calculated Time
People Required
Start Time and Date
End Time and Date
Get paint samples
1 hour
Sue, Joe
5 p.m. Friday
6 p.m. Friday
Choose a paint color
2 hours
Sue, Joe
6 p.m. Friday
8 p.m. Friday
Remove all furniture
1 hour
Joe
8 p.m. Friday
9 p.m. Friday
Take off trim
½ hour
Joe
9 p.m. Friday
10 p.m. Friday
Paint trim
1 hour
Sue or Joe
9 a.m. Saturday
10 a.m. Saturday
Apply first coat
2 hours
Sue or Joe
10 .am. Saturday
Noon Saturday
Apply second coat
2 hours
Sue or Joe
1 p.m. Saturday
3 p.m. Saturday
Put trim back in
½ hour
Joe
3 p.m. Saturday
3:30 p.m. Saturday
Put all furniture back in
1 hour
Joe
3:30 p.m. Saturday
4:30 p.m. Saturday
Here are some tips to make your schedule efficient, accurate, and useful.
Look for places where resources can perform activities simultaneously.
Indicate milestones in your schedule. Milestones are identifiable points in your project that require no resources or time. They are simply a key point in time. They can also help you group your project into phases. Milestones in this project might be:
  Have paint color chosen
  Have room cleaned out
  Get painting complete
  Have room put back together
If you are delivering a business project, try to include deliverables with the milestones. This way, sponsors and stakeholders have tangible results at various stages in the project, and are more likely to stay interested and committed.
Make sure to include lag and lead time in your tasks. In the painting project, for example, there is little to no time allotted for the paint to dry between coats. The project will definitely fall behind schedule.
For team projects, make a large copy of the schedule and post it where everyone can see. (You may want to choose a graphic format, discussed in the next module.)
Estimated Time
10 minutes
Topic Objective
To understand how to build a project schedule.
Topic Summary
To build a schedule, take the time required for each task and the availability of the resources. Use this to determine how long the entire project will take.
Materials Required
Worksheet Two Case Study
Module Seven activities from Worksheet Two
Planning Checklist
Print out one copy of the Worksheet Two case study and the Module Seven activities for each participant.
Recommended Activity
In pairs, have participants build the schedule for this project.
Stories to Share
We will explore more scheduling tools in the next module.
Delivery Tips
You may want to assign a portion of the WBS to each group.
Review Questions
True or False: There is only one right way to display a project schedule.

## Slide 82: Creating a Risk Management Plan
Mitigate: Reduce the probability of risk
Avoid: Take steps to avoid the risk entirely
Transfer: Transfer the responsibility for the risk to someone outside the project
Accept: This is the best approach for risks with low probability and impact ratings
Notes: The Risk Management Plan details how to approach and manage project risks. A risk management plan should be completed for any project. All project team members and stakeholders should have a meeting to complete a first draft of the plan. This ensures everyone knows what problems could crop up.
The meeting should also identify the response options for each risk. There are four common approaches:
Mitigate: Find ways to reduce the probability and impact levels of the risk.
Avoid: Take steps to avoid the risk entirely. For example, if your chosen construction company may have a worker’s strike soon, perhaps you could choose another company.
Transfer: Transfer the responsibility for the risk to someone outside the project. This will decrease your liability, but it may also decrease your level of control, too.
Accept: Accept that the risk could happen, and choose not to act. This is the best approach for risks with low probability and impact ratings.
During the project, stakeholders and team members should be encouraged to bring up new risks to the project manager. The project manager can then update the plan and communicate it to the rest of the team.
A basic risk management plan looks like this, with one row for each risk:
Risk
Date Identified
Risk Raised By
Probability Rating (/10)
Impact Rating (/10)
Response Options
Estimated Time
5 minutes
Topic Objective
To understand what a project risk is and how risks can be managed.
Topic Summary
The Risk Management Plan details how to approach and manage project risks.
Materials Required
Worksheet Two Case Study
Prepared sheet of flip chart paper
Planning Checklist
Print out one copy of the Worksheet Two case study. Prepare a sheet of flip chart paper with the risk management template shown on the next page.
Recommended Activity
In a large group, have participants identify some possible risks. Choose one or two key risks and fill out the risk management plan.
Delivery Tips
This activity can also be performed in small groups.

## Slide 83: Creating a Communication Plan
What? | Status meetings
Who? | Project team
Where? | Whirlwind Room, Fourth Floor
When? | Every Monday at 9 a.m.
Why? | To report issues encountered last week and upcoming tasks for this week
How? | In-person
Notes: Effective communication can make the difference between success and failure in any kind of project. Developing and maintaining a good communication plan will ensure that everyone involved in the project stays up to date, and that information is shared appropriately.
A basic template should include the what, who, where, when, why, and how for each communication item.
Example
What?
Status meetings
Who?
Project team
Where?
Whirlwind Room, Fourth Floor
When?
Every Monday at 9 a.m.
Why?
To report issues encountered last week and upcoming tasks for this week
How?
In-person
As you can see, the communication plan can be formal or informal, highly detailed or broadly framed, based on the needs of the project. Like the schedule, the plan should be maintained, updated, and shared throughout the project.
Estimated Time
5 minutes
Topic Objective
To understand how to ensure there is good communication within your project.
Topic Summary
A basic template should include the what, who, where, when, why, and how for each communication item.
Materials Required
Worksheet Two Case Study
Planning Checklist
Print out one copy of the Worksheet Two case study for each participant.
Recommended Activity
Divide participants into groups of eight to ten. Have each group identify some key communication points.
Stories to Share
The “When” in this template can correspond to tasks, phases, and/or risks.
Delivery Tips
This activity can also be performed in large groups.
Review Questions
Why is good communication important to a project?

## Slide 84: Module Seven: Review Questions
What is the definition of the work breakdown structure?
A graphical breakdown of all the work to be done in the project.
Team or project-based organizations.
The ability to use one's time effectively or productively, especially at work.
The structure in which people interact in large and small groups.
What is the first step of the work breakdown structure?
Identify the purpose of the project and write the title at the top.
Review the WBS with the stakeholders and project team to ensure all items are covered.
Establish the major segments of the work.
Break down the segments of the work into sub-components.

## Slide 85: Module Seven: Review Questions
After breaking down the segments of the work into sub-components, what is the next step?
Review the WBS with the stakeholders and project team to ensure all items are covered.
Continue breaking down the work until you reach the level where you will assign and monitor the project work.
Establish the major segments of the work.
Identify the purpose of the project and write the title at the top.
Which of these statements is not true about the schedule?
The schedule is the most important document during the project.
Graphic tools can really help out when building the schedule.
You must keep the schedule up to date to make sure that you will meet your deadlines.
The schedule is the only document that will not grow and change throughout the project.

## Slide 86: Module Seven: Review Questions
What might you need in order to build the schedule?
The availability of people
The availability of machines
Material resources
All of the above
Which of these is a helpful tip to make your schedule accurate, available and useful?
Look for places where resources can perform activities separately.
Identify milestone points in your project that require resources or time.
If you are delivering a business project, try to include deliverables with the milestones.
Make sure to exclude lag and lead time in your tasks.

## Slide 87: Module Seven: Review Questions
In team projects, which members of your team should have access to the schedule?
Only the project manager
Your team leads
The lower-level employees
Everyone
What is not a common approach when identifying responses options to risks?
Mitigate
Permit
Transfer
Accept

## Slide 88: Module Seven: Review Questions
During the project, what should team members and stakeholders be encouraged to do?
Transfer the blame for a risk to someone outside the team.
Update the plan and communicate it to the rest of the team.
Bring up new risks to the project manager.
Create new risks to test and prepare the team.
Which plan ensures that everyone involved in the project stays up to date, and that information is shared appropriately?
Risk management plan
Communication plan
Project charter
Schedule

## Slide 89: Module Seven: Review Questions
What is the definition of the work breakdown structure?
A graphical breakdown of all the work to be done in the project.
Team or project-based organizations.
The ability to use one's time effectively or productively, especially at work.
The structure in which people interact in large and small groups.
What is the first step of the work breakdown structure?
Identify the purpose of the project and write the title at the top.
Review the WBS with the stakeholders and project team to ensure all items are covered.
Establish the major segments of the work.
Break down the segments of the work into sub-components.

## Slide 90: Module Seven: Review Questions
After breaking down the segments of the work into sub-components, what is the next step?
Review the WBS with the stakeholders and project team to ensure all items are covered.
Continue breaking down the work until you reach the level where you will assign and monitor the project work.
Establish the major segments of the work.
Identify the purpose of the project and write the title at the top.
Which of these statements is not true about the schedule?
The schedule is the most important document during the project.
Graphic tools can really help out when building the schedule.
You must keep the schedule up to date to make sure that you will meet your deadlines.
The schedule is the only document that will not grow and change throughout the project.

## Slide 91: Module Seven: Review Questions
What might you need in order to build the schedule?
The availability of people
The availability of machines
Material resources
All of the above
Which of these is a helpful tip to make your schedule accurate, available and useful?
Look for places where resources can perform activities separately.
Identify milestone points in your project that require resources or time.
If you are delivering a business project, try to include deliverables with the milestones.
Make sure to exclude lag and lead time in your tasks.

## Slide 92: Module Seven: Review Questions
In team projects, which members of your team should have access to the schedule?
Only the project manager
Your team leads
The lower-level employees
Everyone
What is not a common approach when identifying responses options to risks?
Mitigate
Permit
Transfer
Accept

## Slide 93: Module Seven: Review Questions
During the project, what should team members and stakeholders be encouraged to do?
Transfer the blame for a risk to someone outside the team.
Update the plan and communicate it to the rest of the team.
Bring up new risks to the project manager.
Create new risks to test and prepare the team.
Which plan ensures that everyone involved in the project stays up to date, and that information is shared appropriately?
Risk management plan
Communication plan
Project charter
Schedule

## Slide 94: Module Eight: Planning Tools
In the last module, we looked at how to build a schedule in table format. This format will work well for small projects. However, for more complex projects, you will need additional tools. This module will explore four of the most popular tools, including graphical methods and Microsoft Project.
Good fortune is what happens when opportunity meets with planning.
Thomas Edison
Notes: Gantt charts have become a common technique for representing the phases and activities of a project work breakdown structure, as they can be understood by a wide audience.
A Gantt chart is a type of bar chart that illustrates a project schedule. Gantt charts illustrate the start and finish dates of each task, as well as task dependencies and links. Gantt charts can be easily customized to show resources, costs, and other important information. They can also be color-coded for different task phases or responsibilities.
Example
Estimated Time
10 minutes
Topic Objective
To understand what a Gantt chart is and what it is used for.
Topic Summary
A Gantt chart is a type of bar chart that illustrates a project schedule.
Materials Required
Example Gantt chart (shown on the next page)
Planning Checklist
Make sure you have the PowerPoint slides for this course. Or, you can blow up the provided diagram and show it on overhead or flip chart.
Recommended Activity
Review the sample Gantt chart with participants.
Stories to Share
The Gantt chart was developed by Henry Gantt in the 1920’s. One of the first projects that it was used on was the construction of the Hoover Dam.
Delivery Tips
Make sure that participants know that this is a very simple example. Part of the power of Gantt charts is that they can be easily customized.
Although our example was created with Microsoft Project, Gantt charts can be drawn by hand.
Review Questions
What type of chart is a Gantt chart?

## Slide 95: The Gantt Chart
Notes: Gantt charts have become a common technique for representing the phases and activities of a project work breakdown structure, as they can be understood by a wide audience.
A Gantt chart is a type of bar chart that illustrates a project schedule. Gantt charts illustrate the start and finish dates of each task, as well as task dependencies and links. Gantt charts can be easily customized to show resources, costs, and other important information. They can also be color-coded for different task phases or responsibilities.
Example
Estimated Time
10 minutes
Topic Objective
To understand what a Gantt chart is and what it is used for.
Topic Summary
A Gantt chart is a type of bar chart that illustrates a project schedule.
Materials Required
Example Gantt chart (shown on the next page)
Planning Checklist
Make sure you have the PowerPoint slides for this course. Or, you can blow up the provided diagram and show it on overhead or flip chart.
Recommended Activity
Review the sample Gantt chart with participants.
Stories to Share
The Gantt chart was developed by Henry Gantt in the 1920’s. One of the first projects that it was used on was the construction of the Hoover Dam.
Delivery Tips
Make sure that participants know that this is a very simple example. Part of the power of Gantt charts is that they can be easily customized.
Although our example was created with Microsoft Project, Gantt charts can be drawn by hand.
Review Questions
What type of chart is a Gantt chart?

## Slide 96: The Network Diagram
Notes: A network diagram is another way of showing the path of tasks in the project. Tasks are each placed in a box and each box is placed in chronological order. Arrows are drawn from task to task, indicating the logical progression of work. Boxes can be customized to contain any information you like, including start and finish dates, task length, cost, resources, and more. Boxes can also be color-coded based on the phase of the project; resource required, team assignment, etc.
Here is an example of a network diagram from Microsoft Project. (We have scheduled the “Remove furniture” and “Take off trim” tasks to happen at the same time for demonstration purposes.)
We recommend building the network diagram as a team using these steps.
Write all steps out on sticky notes.
Tape a large piece of paper to the wall.
Place sticky notes in order.
Once you think you have the right order, check to make sure lag and lead time is allowed for. Also look for ways that work can be completed simultaneously.
Draw arrows to indicate task links. Color-code the boxes if desired.
Post the diagram in a central location. Make a copy for reference, and keep the original drawing updated as the project progresses.
The network diagram will also help you identify the critical path: the shortest path through the project. This will help if an element of the triple constraint changes and you must alter your plan.
Estimated Time
10 minutes
Topic Objective
To understand what a network diagram is and what it is used for.
Topic Summary
A network diagram is another way of showing the path of tasks in the project.
Materials Required
Example network diagram, provided on the next page
Planning Checklist
Make sure you have the PowerPoint slides for this course. Or, you can blow up the provided diagram and show it on overhead or flip chart.
Recommended Activity
Review the sample network diagram with participants.
Stories to Share
The Network Diagram was also originally developed by the United States military.
Delivery Tips
Emphasize that the network diagram can be customized.
Although our sample diagram was created with Microsoft Project, network diagrams can be drawn by hand.
Review Questions
What is the first step to creating a network diagram?

## Slide 97: Using a RACI Chart
R
A
Responsible for execution
Approver
Example | Sue | Bob | Joe | Jane
Build widget plan | A | R | I | I
Build widget | R | A | C | I
Ship widget to customers | I | I | I | R
C
I
Consult
Keep informed
Notes: A RACI chart is an excellent way to outline who is responsible for what during the project. To start, create a chart with tasks listed on the left hand side, and resources listed across the top. Now, put the appropriate letter in each cell:
R: Responsible for execution
A: Approver
C: Consult
I: Keep informed
Example
Sue
Bob
Joe
Jane
Build widget plan
A
R
I
I
Build widget
R
A
C
I
Ship widget to customers
I
I
I
R
Estimated Time
5 minutes
Topic Objective
To understand what a RACI chart is and when to use it.
Topic Summary
A RACI chart, also known as a responsibility matrix, outlines who is responsible for what during the project.
Materials Required
Example RACI chart, provided on the next page
Planning Checklist
Make sure you have the PowerPoint slides for this course. Or, you can blow up the provided chart and show it on overhead or flip chart.
Recommended Activity
Review the sample RACI chart with participants.
Stories to Share
Some project managers add an E to the legend, so that the R stands for responsible (i.e., the project sponsor), while the E indicates who must actually perform the task.
Review Questions
What does each letter of RACI stand for?

## Slide 98: Going the Extra Mile: Microsoft Project
Microsoft Project is just a tool
Understand how it calculates numbers
Every project requires different tools
Notes: Throughout the course, we have made some references to using computer software to manage projects. We have even included some diagrams from Microsoft Project, a popular project management application.
Applications like Microsoft Project are extremely useful for project managers and their teams. Microsoft Project, as an example, stores information about resources, schedules, tasks, budgets, and more; generates reports on the fly; allows you to enter and view information in numerous ways; and even allows you to collaborate with other team members.
We urge everyone, particularly new project managers, to remember that Microsoft Project is just a tool. In order to make the best use of it, you must understand how it calculates numbers and generates diagrams. Once you have a solid understanding of basic project management concepts, feel free to take the time to learn about project management software if you desire.
Remember, too, that every project requires different tools. For small projects, you may not need the sophisticated features of a software program. If you choose to grow your project management skills, however, and take on larger projects, you will appreciate the extra tools available in these applications.
Estimated Time
5 minutes
Topic Objective
To understand what Microsoft Project is and when to use it.
Topic Summary
Microsoft Project is one of the most popular project management software applications.
Recommended Activity
In a large group, discuss the following questions:
What are the advantages to using Microsoft Project? What are the disadvantages?
Is Microsoft Project used in your organization? If so, how?
Have you used Microsoft Project? If so, what have your experiences been like?
Stories to Share
Microsoft Project was first released in 1984.
Delivery Tips
If possible, have a laptop with Microsoft Project installed and a sample project set up for participants to view.
Review Questions
True or False: All projects should be set up in Microsoft Project.

## Slide 99: Module Eight: Review Questions
Which of these statements is not true of the Gantt chart?
A Gantt chart is a type of bar chart that illustrates a project schedule.
Gantt charts can be easily customized to show resources, costs, and other important information.
Gantt charts illustrate the start and finish dates of each task, as well as task dependencies and links.
They have become a common technique for representing the phases and activities of a project work breakdown structure, as they can be understood by a small audience.
Which of these is an additional benefit of using the Gantt chart?
It helps you assign tasks to several other project manager’s team.
Arrows can be drawn from task to task, indicating the logical progression of work.
They can be color-coded for different task phases or responsibilities.
They can post the diagram in a central location.

## Slide 100: Module Eight: Review Questions
When building the network diagram as a team, what is the first step?
Write all steps out on sticky notes
Place sticky notes in order
Tape a large sheet to the wall
Draw arrows to indicate task links
How will using the network diagram to identify a critical path help?
It will help if you need to assign tasks to another project manager’s team.
It will help if an element of the triple constraint changes and you must alter your plan.
It will help if a task in the statement of work needs updating.
It will help if you need to keep all tasks and responsibilities the same.

## Slide 101: Module Eight: Review Questions
Which planning tool will be best to use for outlining who is responsible for what during the project?
The RACI Char
The Network Diagram.
The Gantt Chart
The Microsoft Project
How would you start to make a RACI chart?
Customize each cell to show resources, costs, and other important information.
Tasks are each placed in a box and each box is placed in chronological order.
Create a chart with tasks and put each task in the appropriate cell.
Create a chart with tasks listed on the left hand side and resources listed across the top.

## Slide 102: Module Eight: Review Questions
What does the “I” in RACI stand for?
Keep individualized
Keep informed
Include
Improvise
Which of these describes the Microsoft Project?
A program that allows the user to use the Gantt chart, the Network Diagram, and the RACI chart all at once
A template used by the RACI chart
A popular project management application
A little-known project management organizer

## Slide 103: Module Eight: Review Questions
Which of these statements is not true of Microsoft Project?
Microsoft Project stores information about resources, schedules, tasks, budgets, and more.
Microsoft Project allows you to collaborate with other team members.
Microsoft Project is extremely useful for project managers, not their teams as a whole.
Microsoft Project allows you to enter and view information in numerous ways.
When is it possible that you would not need the sophisticated features of a software program?
With large audiences
With startup companies
When more than one team is working together
With small projects

## Slide 104: Module Eight: Review Questions
Which of these statements is not true of the Gantt chart?
A Gantt chart is a type of bar chart that illustrates a project schedule.
Gantt charts can be easily customized to show resources, costs, and other important information.
Gantt charts illustrate the start and finish dates of each task, as well as task dependencies and links.
They have become a common technique for representing the phases and activities of a project work breakdown structure, as they can be understood by a small audience.
Which of these is an additional benefit of using the Gantt chart?
It helps you assign tasks to several other project manager’s team.
Arrows can be drawn from task to task, indicating the logical progression of work.
They can be color-coded for different task phases or responsibilities.
They can post the diagram in a central location.

## Slide 105: Module Eight: Review Questions
When building the network diagram as a team, what is the first step?
Write all steps out on sticky notes
Place sticky notes in order
Tape a large sheet to the wall
Draw arrows to indicate task links
How will using the network diagram to identify a critical path help?
It will help if you need to assign tasks to another project manager’s team.
It will help if an element of the triple constraint changes and you must alter your plan.
It will help if a task in the statement of work needs updating.
It will help if you need to keep all tasks and responsibilities the same.

## Slide 106: Module Eight: Review Questions
Which planning tool will be best to use for outlining who is responsible for what during the project?
The RACI Char
The Network Diagram.
The Gantt Chart
The Microsoft Project
How would you start to make a RACI chart?
Customize each cell to show resources, costs, and other important information.
Tasks are each placed in a box and each box is placed in chronological order.
Create a chart with tasks and put each task in the appropriate cell.
Create a chart with tasks listed on the left hand side and resources listed across the top.

## Slide 107: Module Eight: Review Questions
What does the “I” in RACI stand for?
Keep individualized
Keep informed
Include
Improvise
Which of these describes the Microsoft Project?
A program that allows the user to use the Gantt chart, the Network Diagram, and the RACI chart all at once
A template used by the RACI chart
A popular project management application
A little-known project management organizer

## Slide 108: Module Eight: Review Questions
Which of these statements is not true of Microsoft Project?
Microsoft Project stores information about resources, schedules, tasks, budgets, and more.
Microsoft Project allows you to collaborate with other team members.
Microsoft Project is extremely useful for project managers, not their teams as a whole.
Microsoft Project allows you to enter and view information in numerous ways.
When is it possible that you would not need the sophisticated features of a software program?
With large audiences
With startup companies
When more than one team is working together
With small projects

## Slide 109: Module Nine: Executing the Project
We have spent a lot of time talking about what the project will do and making plans for how to do it. Finally, it is time to get to work and put our plans into action.
You can only elevate individual performance by elevating that of the entire system.
W. Edwards Deming
Notes: You can only elevate individual performance by elevating that of the entire system.
W. Edwards Deming
We have spent a lot of time talking about what the project will do and making plans for how to do it. Finally, it is time to get to work and put our plans into action.

## Slide 110: Establishing Baselines
Formal end of the planning phase
Original plan
Measuring stick
Communicated to all stakeholders
Notes: There is actually one final task to complete before we can start work on our project. Establishing the baseline indicates the formal end of the planning phase and the beginning of project execution and control.
The baseline is your original plan, containing the original scope, cost, and time. This gives you a measuring stick throughout the project. For example, let’s say that your baseline budget was $20,000. If, after the first task, you have spent $15,000, you know you’re in trouble. You can then evaluate the situation and prepare an action plan – hopefully before things get too out of hand.
The baseline should be communicated to all stakeholders and the project team. Scope and resources can be outlined in text format. Cost and time can be displayed as a graph. Or, you can use a graphic scheduling tool (like a Gantt chart or network diagram) to display the original plan and track where you are. (More on that in a moment!)
Estimated Time
10 minutes
Topic Objective
To understand what a baseline is and its use in project management.
Topic Summary
Establishing the baseline indicates the formal end of the planning phase and the beginning of project execution and control.
The baseline is your original plan, containing the original scope, cost, and time. This gives you a measuring stick throughout the project.
Materials Required
List of categories
Planning Checklist
Prepare a list of categories before the workshop, or use the list below.
Height
Age
Birth month
Number of pets
Number of bones broken
Number of pieces of jewelry they are wearing
Number of projects they have managed or been part of
Number of siblings
Recommended Activity
After delivering the content for this module, engage participants in a quick energizer.
Divide participants into groups of ten to twelve. Explain that you are going to call out a category and they must line themselves up by those criteria. If you like, you can keep score or assign points.
Keep this activity quick and light.
Delivery Tips
If your group is smaller than twenty, do not split the groups up.

## Slide 111: Monitoring Project Progress
Status meetings
Regular status reports
Hands-on observation
Notes: As the project manager, it is your responsibility to monitor all the parts of your project to make sure they are continuing as planned. If issues arise, it is your responsibility to resolve them, or to escalate them to someone who can resolve them.
Some popular, effective methods of tracking project progress include:
Regular status meetings
Regular status reports
Hands-on observation
Recording data manually or electronically and generating reports (for example, spending to date versus total budget)
Your visual scheduling tools can also help you record project progress and communicate it to your team.
As tasks are completed, they can be crossed off the Gantt chart and/or the network diagram.
If new resources need to be added, they can be added to network diagram boxes.
If tasks need to be re-scheduled, they can be moved around on the network diagram.
Risks, accomplishments, and lessons learned can be posted next to tasks.
Estimated Time
10 minutes
Topic Objective
To understand how to monitor project progress.
Topic Summary
As the project manager, it is your responsibility to monitor all the parts of your project to make sure they are continuing as planned. You can use a variety of tools to do this.
Materials Required
Worksheet Two Case Study
Planning Checklist
Print out one copy of the Worksheet Two Case Study for each participant.
Recommended Activity
In groups of four to six, have participants identify what project monitoring tools would be most appropriate for the project at Super Shovels.
Review Questions
True or False: The project manager is responsible for fixing all project issues themselves.

## Slide 112: Triple Constraint Reduction Methods
Crashing: Reduce the schedule without changing the budget
Fast-Tracking: Where lag/lead time can be reduced or eliminated.
De-scoping: Removes items from the project scope to free up time and/or money.
Notes: Be forewarned: after all of your planning, it is very likely that one element of the triple constraint will change. Perhaps a team member has left the organization, the budget has been cut, or new technical requirements need to be met.
When approached with scope changes, don’t panic! There are three established methods that you can use to decide how to alter the course of the project.
Crashing: Reduce the schedule without changing the budget, or vice-versa (depending on project needs). This can be done by using cheaper resources, or by re-evaluating time estimates.
Fast-Tracking: Can be done with the schedule only. Looks at the schedule to see which tasks (if any) can be completed concurrently, and where lag/lead time can be reduced or eliminated.
De-scoping: Removes items from the project scope to free up time and/or money.
Make sure that you truly look at the big picture, and include short and long term benefits and consequences in your decision-making process.
Once you have performed careful analysis, gather documentation to back up your decision, clear the decision with the appropriate stakeholders, change the project plan accordingly, and communicate the plan change to everyone involved.
Estimated Time
10 minutes
Topic Objective
To understand how to adjust your project plans if a triple constraint element is changed.
Topic Summary
There are three established methods that you can use to decide how to alter the course of the project.
Crashing
Fast-tracking
De-scoping
Materials Required
Flip chart paper
Markers
Planning Checklist
Review the scenarios below before the workshop and come up with some ideas of your own.
Recommended Activity
Revisit the following scenarios with the group. Explore which reduction method would be appropriate for each scenario.
Budget is reduced by 25%
Building needs to be completed three months earlier
Product must have 99% purity instead of 95%
Need to renovate three office buildings instead of one
Delivery Tips
There are no “right” answers for this activity. The objective is to have participants see how changes can have a ripple effect.
Review Questions
Name one of the triple constraints.

## Slide 113: Module Nine: Review Questions
What indicates the formal end of the planning phase and the beginning of project execution and control?
Establishing the baseline
Maintaining and controlling
Initiating
Resolving risk
Who should the baseline be communicated to?
The project team and those working on the budget.
All stakeholders and the project team.
All stakeholders and direct supervisors.
The project team and direct supervisors.

## Slide 114: Module Nine: Review Questions
When establishing baselines, what can be outlined in text format?
The baseline
Cost and time
Scope and resources
Both a & b
If an issue arises, what is the responsibility of the project manager?
To resolve the issues
To escalate the issues to someone who can resolve them
To ensure that issues do not arise in the first place
Both a & b

## Slide 115: Module Nine: Review Questions
Which of these is not a popular, effective method of tracking project progress?
Regular status meetings
Hands-off observation
Recording data manually or electronically and generating reports
Regular status reports
Which of these is a good suggestion when using your visual scheduling tools?
Risks, accomplishments, and lessons learned can be posted only in a Gantt Chart.
If tasks need to be re-scheduled, they cannot be moved around on the network diagram.
As tasks are completed, they can be crossed off the RACI chart.
If new resources need to be added, they can be added to network diagram boxes.

## Slide 116: Module Nine: Review Questions
After all your planning, what is very likely to change?
One element of the triple constraint
The guidance of your shareholders
One of the members of your project management team
The deliverables of the project
Which of these is not an established method that you can use to decide how to alter the course of the project?
Projecting
Crashing
Fast-tracking
De-scoping

## Slide 117: Module Nine: Review Questions
When faced with scope changes, how can you reduce the schedule without changing the budget (or vice versa)?
This can be done by removing items from the project scope to free up money
This can be done by removing items from the project scope to free up time
This can be done by using cheaper resources, or by re-evaluating time estimates
This can be done with the schedule only
When using triple constraint reduction methods, what is important to remember?
Include short and long term benefits and consequences in your decision-making process
Don’t panic
Make sure that you truly look at the big picture
All of the above

## Slide 118: Module Nine: Review Questions
What indicates the formal end of the planning phase and the beginning of project execution and control?
Establishing the baseline
Maintaining and controlling
Initiating
Resolving risk
Who should the baseline be communicated to?
The project team and those working on the budget.
All stakeholders and the project team.
All stakeholders and direct supervisors.
The project team and direct supervisors.

## Slide 119: Module Nine: Review Questions
When establishing baselines, what can be outlined in text format?
The baseline
Cost and time
Scope and resources
Both a & b
If an issue arises, what is the responsibility of the project manager?
To resolve the issues
To escalate the issues to someone who can resolve them
To ensure that issues do not arise in the first place
Both a & b

## Slide 120: Module Nine: Review Questions
Which of these is not a popular, effective method of tracking project progress?
Regular status meetings
Hands-off observation
Recording data manually or electronically and generating reports
Regular status reports
Which of these is a good suggestion when using your visual scheduling tools?
Risks, accomplishments, and lessons learned can be posted only in a Gantt Chart.
If tasks need to be re-scheduled, they cannot be moved around on the network diagram.
As tasks are completed, they can be crossed off the RACI chart.
If new resources need to be added, they can be added to network diagram boxes.

## Slide 121: Module Nine: Review Questions
After all your planning, what is very likely to change?
One element of the triple constraint
The guidance of your shareholders
One of the members of your project management team
The deliverables of the project
Which of these is not an established method that you can use to decide how to alter the course of the project?
Projecting
Crashing
Fast-tracking
De-scoping

## Slide 122: Module Nine: Review Questions
When faced with scope changes, how can you reduce the schedule without changing the budget (or vice versa)?
This can be done by removing items from the project scope to free up money
This can be done by removing items from the project scope to free up time
This can be done by using cheaper resources, or by re-evaluating time estimates
This can be done with the schedule only
When using triple constraint reduction methods, what is important to remember?
Include short and long term benefits and consequences in your decision-making process
Don’t panic
Make sure that you truly look at the big picture
All of the above

## Slide 123: Module Ten: Maintaining and Controlling the Project
The fourth phase of project
management is maintaining and
controlling. Although it is part of the
execution phase, it is so important that
the PMBOK separates it out into its
own set of activities. This module will
give you some key tools for keeping
your project on track.
Trying is just a noisy way of saying no progress.
Warren Bennis
Notes: Trying is just a noisy way of saying no progress.
Warren Bennis
The fourth phase of project management is maintaining and controlling. Although it is part of the execution phase, it is so important that the PMBOK separates it out into its own set of activities. This module will give you some key tools for keeping your project on track.

## Slide 124: Making the Most of Status Updates
Tasks planned for the previous week
Tasks completed in the previous week
Tasks planned for the following week
Issues and risks identified
Notes: Regular, mandatory status meetings for all project team members should be a part of any project. These meetings will give team members a chance to connect, discuss issues, and solve problems. It will also give you the opportunity to coach team members and make sure you’re on top of what everyone is doing.
Status meetings should be tied in with status reports. We recommend that both items be completed weekly or bi-weekly, depending on your project. Also, remember that meetings and reports can be brief or detailed – it all depends on what level of control you need and how big the project is.
We recommend a Friday-Monday schedule, where reports are submitted on Friday (before the end of the day) and status meetings are held on Monday. If a holiday happens to occur, reports could be submitted on the Thursday, and meetings could take place on the Tuesday.
Status reports should contain the following items:
Team member name
Status report date
Tasks planned for the previous week
Tasks completed in the previous week
Tasks planned for the following week
Issues and risks identified (highlight those that require project manager attention)
Status meetings, then, are a review of tasks that each member completed for the previous week, what they have planned for the upcoming week, and what issues they have encountered or predict.
Again, status reports and meetings should be customized for your projects’ needs. Team members should also know that issues should be reported to the project manager as they arise.
Estimated Time
10 minutes
Topic Objective
To understand how to organize status reports and update meetings.
Topic Summary
Regular, mandatory status meetings for all project team members should be a part of any project. Status meetings should be tied in with status reports.
Materials Required
Flip chart paper
Markers
Recommended Activity
In a large group, create a do’s and don’ts list for status meetings.
Delivery Tips
If your group is larger than twenty, you may want to perform this activity in smaller groups.

## Slide 125: Managing Change
Change Request Number: | Change Requested On:
Change Requested By: | Change Submitted By:
Change Details: | Tasks Affected:
Approved or Rejected? | By:
Notes: Change management is another way of controlling your project. This process ensures that any changes, whether they are to the objectives, requirements, tasks, or design of a particular component, are approved by the project team.
At the beginning of the project, all stakeholders and team members must agree not to make any changes to the project plan or to the design of its components, and to instead follow a change management process. Then, when a change is required, a change management form is completed.
Example
Change Request Number:
Change Requested On:
Change Requested By:
Change Submitted By:
Change Details:
Tasks Affected:
Approved or Rejected?
By:
Then, the form is submitted to the project manager. The change is reviewed and a decision is made. In small projects, the review process may be done by the project manager. For larger projects, the project team or even a separate task force (typically called the Change Control Board, or CCB) is involved.
Estimated Time
10 minutes
Topic Objective
To become familiar with a basic change management process.
Topic Summary
At the beginning of the project, all stakeholders and team members must agree not to make any changes to the project plan or to the design of its components, and to instead follow a change management process. Then, when a change is required, a change management request is completed. A decision is then made by the project manager.
Materials Required
Worksheet Two Case Study
Module Ten questions from Worksheet Two
Planning Checklist
Print out one copy of the Worksheet Two Case Study and the Module Ten questions for each participant.
Recommended Activity
Divide participants into groups of four to six. Ask each group to answer the worksheet questions.
Delivery Tips
You can also have a large group discussion, and use the worksheet questions as a guide.

## Slide 126: Monitoring Risks
Be proactive
Keep an eye out for assumptions
Keep a record of actions
Notes: Remember the risk management plan that we built during the planning phase? Make sure it doesn’t stay on a shelf. Continue to monitor and add to it.
Here are some additional tips for making sure risks don’t ruin your project:
Be proactive. Have meetings with stakeholders and outside parties to ensure your risk assessment is accurate and that your action plan (if you have one) is valid.
Keep an eye out for assumptions. Make sure that they continue to hold true. Identify what could happen if those assumptions are unfulfilled.
Keep a record of what actions you take to mitigate risks.
Estimated Time
10 minutes
Topic Objective
To understand how to monitor risks during a project.
Topic Summary
During the execution of the project, you must continue to monitor risks and add to the risk management plan. (See Module Seven for more information.)
Materials Required
Worksheet Two Case Study
Planning Checklist
Print out one copy of the Worksheet Two case study for each participant.
Recommended Activity
In a large group, discuss what new risks might arise during our case study project.
Delivery Tips
This activity can also be performed in small groups.
Review Questions
Name one activity that you can perform to monitor risks.

## Slide 127: Module Ten: Review Questions
Which is the fourth phase of project management?
Planning
Maintaining and controlling
Preparing and executing
Initiating
How often is it recommended that status meetings and status updates be completed?
Weekly or bi-weekly
Monthly or bi-monthly
Every quarter, tied in with quarterly reports
Daily

## Slide 128: Module Ten: Review Questions
In a Friday-Monday schedule, if a holiday occurs on a Friday, when it recommended that status updates be submitted?
Thursday
Friday, even with the holiday
The following Monday
Wednesday
Which of these is not an item that should be contained within the status report?
Issues and risks identified
Status report date
Tasks planned for the previous week
Tasks planned for the following months

## Slide 129: Module Ten: Review Questions
What is a good rule of thumb for status reports and meetings?
Status meetings should be kept separate from status reports whenever possible.
Status meetings and reports should be kept brief.
Status meetings and reports should be kept intricately detailed.
Status meetings and reports should be customized for your projects’ needs.
What process assures that all changes are approved by the project team?
Status meetings and reports
Risk management
Change management
Project management team changes

## Slide 130: Module Ten: Review Questions
Who is the change management form submitted to?
Human resources
The project manager
The project management team
The stakeholders
For larger projects, who can be involved in managing change?
The project manager
The project management team
A separate task force
All of the above

## Slide 131: Module Ten: Review Questions
Which plan used during the planning phase can also be used in the maintaining and controlling phase?
Change management plan
Risk management plan
Status reports and updates
Communication plan
Which of these is not a helpful tip when using a risk management plan?
Have meetings with stakeholders and outside parties to ensure your risk assessment is accurate.
Keep a record of what actions you take to mitigate risks.
Be reactive when it comes to maintaining and controlling with stakeholders and outside parties.
Identify what could happen if assumptions are unfulfilled.

## Slide 132: Module Ten: Review Questions
Which is the fourth phase of project management?
Planning
Maintaining and controlling
Preparing and executing
Initiating
How often is it recommended that status meetings and status updates be completed?
Weekly or bi-weekly
Monthly or bi-monthly
Every quarter, tied in with quarterly reports
Daily

## Slide 133: Module Ten: Review Questions
In a Friday-Monday schedule, if a holiday occurs on a Friday, when it recommended that status updates be submitted?
Thursday
Friday, even with the holiday
The following Monday
Wednesday
Which of these is not an item that should be contained within the status report?
Issues and risks identified
Status report date
Tasks planned for the previous week
Tasks planned for the following months

## Slide 134: Module Ten: Review Questions
What is a good rule of thumb for status reports and meetings?
Status meetings should be kept separate from status reports whenever possible.
Status meetings and reports should be kept brief.
Status meetings and reports should be kept intricately detailed.
Status meetings and reports should be customized for your projects’ needs.
What process assures that all changes are approved by the project team?
Status meetings and reports
Risk management
Change management
Project management team changes

## Slide 135: Module Ten: Review Questions
Who is the change management form submitted to?
Human resources
The project manager
The project management team
The stakeholders
For larger projects, who can be involved in managing change?
The project manager
The project management team
A separate task force
All of the above

## Slide 136: Module Ten: Review Questions
Which plan used during the planning phase can also be used in the maintaining and controlling phase?
Change management plan
Risk management plan
Status reports and updates
Communication plan
Which of these is not a helpful tip when using a risk management plan?
Have meetings with stakeholders and outside parties to ensure your risk assessment is accurate.
Keep a record of what actions you take to mitigate risks.
Be reactive when it comes to maintaining and controlling with stakeholders and outside parties.
Identify what could happen if assumptions are unfulfilled.

## Slide 137: Module Eleven: Closing Out
You’ve reached the point where all the
tasks in your project plan have been
checked off: the widget is built, the
advertisements are on TV, and boxes
are being shipped to customers. Before
you consider the project complete,
however, there are a few more things
to be done.
The real problem is what to do with problem solvers after the problem is solved.
Gay Talese
Notes: The real problem is what to do with problem solvers after the problem is solved.
Gay Talese
You’ve reached the point where all the tasks in your project plan have been checked off: the widget is built, the advertisements are on TV, and boxes are being shipped to customers. Before you consider the project complete, however, there are a few more things to be done.

## Slide 138: Preparing for Closeout
Closure of a project can be difficult
Reviewing their performance
Help team members get through this tough time
Notes: As your project winds down, you may find team morale dropping, or anxiety increasing. Closure of a project can be difficult, particularly if the project has been long and/or difficult, or if team members will not be working together afterward.
To help team members get through this tough time, make sure they know what they will be working on after the project. Make sure they know who will be reviewing their performance. (If it is not you, let them know that you will pass on information about their performance to their regular supervisor. This expectation should have been set at the beginning of the project, too.) Encourage team members to come to you with questions.
Estimated Time
5 minutes
Topic Objective
To understand how to ensure a smooth transition for team members.
Topic Summary
As your project winds down, you may find team morale dropping, or anxiety increasing. Closure of a project can be difficult, particularly if the project has been long and/or difficult, or if team members will not be working together afterward.
Materials Required
Worksheet Two Case Study
Planning Checklist
Print out one copy of the Worksheet Two Case Study for each participant.
Recommended Activity
In a large group, brainstorm what closing activities might be required for this project.
Stories to Share
Sometimes, the closure of a project can represent the grieving process. For some people, it is a very serious time in their professional lives.
Delivery Tips
A ribbon-cutting ceremony to open the new office building could be one idea.

## Slide 139: Celebrating Successes
Take time to celebrate
Recognize each person for their contributions
Have a close-out meeting
Notes: After the project, take time to celebrate the things that the project team did well. Try to recognize each person for their contributions and accomplishments.
Team celebrations, of course, are also an important part of project close-out. It is a great idea to have a team party. Another excellent idea is to have a close-out meeting with stakeholders, team members, and other interested parties. This provides an opportunity to review the project’s accomplishments and challenges – and it ties in with our next topic.
Estimated Time
10 minutes
Topic Objective
To understand the important of having a celebration at the end of the project.
Topic Summary
After the project, take time to celebrate the things that the project team did well. Team celebrations, of course, are also an important part of project close-out.
Materials Required
Index cards
Markers
Craft supplies, such as glue, sparkles, cut-outs, etc. (if desired)
Planning Checklist
Have plenty of supplies on hand for this activity.
Recommended Activity
Place a stack of index cards and supplies in the middle of each table.
Explain to participants that recognition is an important part of our everyday lives that many people neglect. It is even more important when you are a project manager.
Ask participants to take a moment to take a pile of index cards and to write a compliment for each individual in the class on that card.
This is an easy, inexpensive way of recognizing your team members. It is also a good way to build team morale, particularly if team members are having a hard time getting along.
Stories to Share
Of course, celebrations should take place throughout the project. One easy way to do this is to make recognition part of your status meetings.
Delivery Tips
If your group is so large that all members have not had a chance to interact, divide the class into smaller groups, or limit the number of cards that each person must prepare.

## Slide 140: Learning from Project Challenges
Effort put into the task is not wasted
Apply these lessons to future projects
Lessons learned should be documented
Ensures everyone is aware of the challenges encountered
Notes: No project will go perfectly. There will always be a risk you didn’t anticipate, tasks that run longer than they should have, project team members that didn’t perform as you expected… If it can happen, it probably will!
Meeting with team members and stakeholders to identify lessons learned throughout the project is a valuable exercise for several reasons.
It ensures everyone is aware of the challenges encountered and what was done to resolve them.
If something is learned from a mistake or failed endeavor, then the effort put into the task is not entirely wasted.
Participants can apply these lessons to future projects and be more successful.
Lessons learned should be documented and included with final project documentation.
Estimated Time
5 minutes
Topic Objective
To understand how to identify lessons learned throughout the project.
Topic Summary
No project will go perfectly. Meeting with team members and stakeholders to identify lessons learned throughout the project is a valuable exercise.
Materials Required
Flip chart paper
Markers
Recommended Activity
In a large group, discuss what participants learned during the workshop.
Stories to Share
This activity is important for all projects, no matter what their size.
Delivery Tips
This activity can also be performed in small groups.
Review Questions
Why is it important to document lessons learned?

## Slide 141: Scope Verification
Were all needs met?
Were all deliverables met?
Are the stakeholders happy with the results?
Notes: Another important part of project closeout is scope verification. This is where stakeholders and team members meet to determine whether or not the project did what it set out to do.
This checklist can be used as a guide for scope verification.
Were all needs met? Were any wants met?
Were all SMART objectives achieved?
Were all deliverables met?
Are the stakeholders happy with the results? Are team members happy?
If the project team realizes that an important deliverable has been missed, there are two options.
Return to the planning phase and create a plan for completing the missed tasks.
Choose to leave this item as unmet and create a separate project for it.
Estimated Time
5 minutes
Topic Objective
To understand how to verify that your project did what it set out to do.
Topic Summary
This checklist can be used as a guide for scope verification.
Were all needs met? Were any wants met?
Were all SMART objectives achieved?
Were all deliverables met?
Are the stakeholders happy with the results? Are team members happy?
Materials Required
List of workshop objectives
Planning Checklist
Have the workshop objectives available on PowerPoint or on flip chart paper.
Recommended Activity
Go through the list of objectives and see if we learned everything we set out to do. This is a type of scope verification.
Delivery Tips
If any items were not covered in sufficient depth, be prepared to offer alternate resources.
Review Questions
What should the team do if they realize they forgot to do something?

## Slide 142: A Final To-Do List
Pass on appropriate project information
Ensure all payments have been made and paperwork submitted
Dispose of or return materials
Notes: In addition to scope verification and lessons learned, the following tasks should also be completed during closeout:
Pass on appropriate project information (training documentation, blueprints, troubleshooting information, etc.) to the appropriate people.
Ensure all payments have been made and paperwork submitted.
Dispose of or return materials.
All project documents, both electronic and paper, should be completed and compiled. Make sure to include the original document, the final document, and any revised versions. Key documents include:
Statement of work
Project charter
Project planning worksheet
Project schedule and related documents
Risk management plan
Communication plan
Change management requests
Team member evaluations
Lessons learned
Meeting minutes
Status reports
Estimated Time
5 minutes
Topic Objective
To ensure participants understand what activities need to be completed before the project can be considered finished.
Topic Summary
In addition to scope verification and lessons learned, there are some additional tasks that should be completed during closeout.
Materials Required
Action plans
Planning Checklist
Print out one action plan per participant.
Recommended Activity
Ask participants to create their own to-do list for after the workshop.
Delivery Tips
If participants are familiar enough with each other, it can be useful to have participants choose a buddy for follow-up after the workshop. Or, participants can identify someone back at the workplace to help them achieve their goals.

## Slide 143: Module Eleven: Review Questions
As your project winds down, what may you find happening?
Team morale dropping
Anxiety increasing
Closing of the project becoming difficult
All of the above
Which of these is a helpful way to help co-workers get through the closing of a project?
Make sure they know what they will be working on after the project.
Pass on comments about their work performance to their co-workers.
Try not to discuss performance review as this will only increase the difficulty.
Encourage team members to go to their human resources department with questions.

## Slide 144: Module Eleven: Review Questions
After the project, what should you take time to celebrate?
The anxiety your co-workers are experiencing.
The things the project team did well.
The risks and issues that were not avoided.
The relief the end of the project brings.
What is an important part of project close-out?
Status updates and reports
Risk management planning
A team celebration
Quickly focusing on the next project

## Slide 145: Module Eleven: Review Questions
Which of these statements is true about learning from project challenges?
Some projects go perfectly, and it’s important to learn what went wrong to get it perfect next time.
No project goes perfectly. If it can happen, it probably will!
There are always risks that you didn’t anticipate, but there are never tasks that run longer than they should have.
The best projects do not have challenges.
Which of these is not a good reason why meeting with team members and stakeholders to identify lessons learned is a valuable experience?
Participants can apply these lessons to future projects and be more successful.
It ensures everyone is aware of the challenges encountered and what was done to resolve them.
Lessons learned should be kept between the project manager and his team.
If something is learned from a mistake or failed endeavor, then the effort put into the task is not entirely wasted.

## Slide 146: Module Eleven: Review Questions
At which point in the project do stakeholders and team members meet to determine whether or not the project did what it set out to do?
Risk management plan.
When learning from project challenges.
Scope verification.
Celebrating successes.
Which of these questions can be used as a guide for scope verification?
Who else should we involve in this? Who might be affected?
What is a step in creating a network diagram?
What do we want the project to accomplish?
Were all needs met? Were any wants met?

## Slide 147: Module Eleven: Review Questions
If the project team realizes that an important deliverable has been missed, what is a good option?
Return to the planning phase and create a plan for completing the missed tasks.
Choose to leave the item at met as it is the end of the project.
Do whatever is necessary to ensure that stakeholders are happy on the return of their investment.
Apply lessons learned to future projects in order to be successful.
Which of these tasks is not completed during closeout?
Dispose of or return materials.
Complete a change management form at the end of the project.
Ensure all payments have been made and paperwork submitted.
Pass on appropriate project information to the appropriate people.

## Slide 148: Module Eleven: Review Questions
As your project winds down, what may you find happening?
Team morale dropping
Anxiety increasing
Closing of the project becoming difficult
All of the above
Which of these is a helpful way to help co-workers get through the closing of a project?
Make sure they know what they will be working on after the project.
Pass on comments about their work performance to their co-workers.
Try not to discuss performance review as this will only increase the difficulty.
Encourage team members to go to their human resources department with questions.

## Slide 149: Module Eleven: Review Questions
After the project, what should you take time to celebrate?
The anxiety your co-workers are experiencing.
The things the project team did well.
The risks and issues that were not avoided.
The relief the end of the project brings.
What is an important part of project close-out?
Status updates and reports
Risk management planning
A team celebration
Quickly focusing on the next project

## Slide 150: Module Eleven: Review Questions
Which of these statements is true about learning from project challenges?
Some projects go perfectly, and it’s important to learn what went wrong to get it perfect next time.
No project goes perfectly. If it can happen, it probably will!
There are always risks that you didn’t anticipate, but there are never tasks that run longer than they should have.
The best projects do not have challenges.
Which of these is not a good reason why meeting with team members and stakeholders to identify lessons learned is a valuable experience?
Participants can apply these lessons to future projects and be more successful.
It ensures everyone is aware of the challenges encountered and what was done to resolve them.
Lessons learned should be kept between the project manager and his team.
If something is learned from a mistake or failed endeavor, then the effort put into the task is not entirely wasted.

## Slide 151: Module Eleven: Review Questions
At which point in the project do stakeholders and team members meet to determine whether or not the project did what it set out to do?
Risk management plan.
When learning from project challenges.
Scope verification.
Celebrating successes.
Which of these questions can be used as a guide for scope verification?
Who else should we involve in this? Who might be affected?
What is a step in creating a network diagram?
What do we want the project to accomplish?
Were all needs met? Were any wants met?

## Slide 152: Module Eleven: Review Questions
If the project team realizes that an important deliverable has been missed, what is a good option?
Return to the planning phase and create a plan for completing the missed tasks.
Choose to leave the item at met as it is the end of the project.
Do whatever is necessary to ensure that stakeholders are happy on the return of their investment.
Apply lessons learned to future projects in order to be successful.
Which of these tasks is not completed during closeout?
Dispose of or return materials.
Complete a change management form at the end of the project.
Ensure all payments have been made and paperwork submitted.
Pass on appropriate project information to the appropriate people.

## Slide 153: Module Twelve: Wrapping Up
Although this workshop is coming to a close, we hope that your journey to improve your Project Management skills is just beginning. Please take a moment to review and update your action plan. This will be a key tool to guide your progress in the days, weeks, months, and years to come. We wish you the best of luck on the rest of your travels!
This feeling, finally, that we may change things - this is at the centre of everything we are. Lose that... lose everything.
Sir David Hare
Notes: Although this workshop is coming to a close, we hope that your journey to improve your project management skills is just beginning. Please take a moment to review and update your action plan. This will be a key tool to guide your progress in the days, weeks, months, and years to come. We wish you the best of luck on the rest of your travels!

## Slide 154: Words from the Wise
Yogi Berra
In theory there is no difference between theory and practice. In practice there is.
Dwight Eisenhower
Plans are nothing; planning is everything.
The reward for work well done is the opportunity to do more.
Jonas Salk:
Notes: Yogi Berra: In theory there is no difference between theory and practice. In practice there is.
Dwight Eisenhower: Plans are nothing; planning is everything.
Jonas Salk: The reward for work well done is the opportunity to do more.

## Slide 155: Communication Strategies
While we wait for everyone to join:
Think of a recent situation where you faced a communication challenge.
For Example: communicating a new process,
where communication or lack thereof affected productivity, or where communication impacted decision making on a project.
Our session will begin shortly.
Notes: SLIDE TIME: 15 minutes BEFORE START OF SESSION
Facilitator Note (Repeat several times, as needed as participants join.)
As participants join the session;
Say
Welcome! Thank you for joining the session early. This session will start in approximately __________-minutes. While we wait for everyone to join us, Think of a recent situation where you faced a communication challenge. For Example: communicating a new process, where communication or lack thereof affected productivity, or where communication impacted decision making on a project.
Also, in the Chat Box, provide a brief introduction that includes your business unit and role in the company.
Phone lines are, and will remain, open. However, if you anticipate background noise, please mute your phone or computer line yourself; if we experience any distracting noises, your line will be muted for you. Please do not, at anytime during this session, place your phone on HOLD. It broadcasts a repetitive music sound to all of us which disrupts the time we have together. Thank you so much for your understanding.
Facilitator Note
Mention there is a participant Handout that accompanies this session. Provide “Workshop Handout” file through WebEx file transfer functionality. Suggest to participants to save the workbook to their desktop, print it, and have it open and ready for the start of the session.
Transition:
SAY
It looks like just about all participants are on, we will wait about a minute more before we begin.
Facilitator Note
Repeat WebEx file transfer, as needed to ensure all participants have received the file. Confirm with participant who has it and who doesn’t. Provide transfer up to and including slide 3 if needed. If anyone joins after slide 3 use your judgement if to push again if it doesn’t interview with the session timing.

## Slide 156: Communication Strategies
Notes: Slide Time: 1:00
SAY/EXPLAIN
Hello and Welcome to Communication Strategies. Thank you for joining me today. My name is [_____] and I’ll be your Facilitator today.
NOTE: Say about 30 to 60-seconds about your background experience , degrees, years facilitating, etc.
Facilitator Note
Mention there is a participant Handout that accompanies this session. Provide “Workshop Handout” file through WebEx file transfer functionality. Suggest to participants to save the workbook to their desktop, print it, and have it open and ready for the start of the session. Ask participants to fill these out throughout the day as they learn new things and have ideas on how to incorporate the things we discuss into their lives.
SAY/EXPLAIN
Phone lines are, and will remain, open. If you anticipate background noise, please mute your phone or computer line yourself; if we experience any distracting noises, your line will be muted for you. Please do not, at anytime during this session, place your phone on HOLD. It broadcasts a repetitive music sound to all of us which disrupts the time we have together. Thank you so much for your understanding.
Transition:
SAY
Now, let’s review general house keeping items, our virtual environment, and what we will cover today.

## Slide 157: House Keeping
Please Turn Off Or Mute Cell Phones
Please Do Not Place Your Phone On HOLD
Ask Questions
Use The Chat To Make Comments
Reply To Each Other
RESPECT
CONFIDENTIALITY
PRACTICE
Notes: Slide Time: .30
ANIMATED SLIDE
SAY/EXPLAIN
We have 90-minutes together today. In order to get the most out of the session, I would like to go over a few house keeping items.
Please turn off your cell phones or turn it to vibrate.
Please do not, at anytime during this session, take incoming calls or place your phone on HOLD. It broadcasts repetitive music to all of us which disrupts the time we have together. Thank you so much for your understanding.
This is an interactive workshop. I encourage you to ask questions, use the chat to make comments, and reply to each other as we go over the material and activities.
I would like you to remember these three words: <Click> Respect, <Click> Confidentiality, <Click> Practice.
To get the most from this workshop, we must all work together, listen to each other, ask and answer questions, explore new ideas, make a few mistakes, and overall … participate! You will have plenty of opportunities to do all of these!

## Slide 158: Webinar Reminders
Notes: Slide Time: 3:00
FACILITATOR NOTEs
Demonstrate by using the preferred pointer tool (or thin dark line) to show each of the tools and features that you will be using during the session. Feel free to ask participants to follow along by using their tools during your walk through.
SAY
Many of you may have already used the tools I am about to show you. To make sure everyone is aware, I’m briefly going to cover the following tools we will use during today’s session:
The Chat Window: Which most of you have already used, is available by clicking on the Chat icon and a chat window will be available for you to respond and ask questions. When using the chat feature, be aware you will have the ability to chat to Everyone when responding to group or individual activities.
If you are having any technical difficulties, use the Chat to let me know. The issue may be a one-off type of thing. If we are finding the technical difficulty is preventing us from continuing the session, I will stop and address it right away. I don’t foresee any challenges, yet I would like us prepared, if it does occur.
The Icon features: Allow a quick way to assess questions asked. There is a list of Emoticons at the bottom of the Participant list.
A green check mark can mean you agree or yes; a red x means you disagree or no. Most of the time we will be using the phone, chat, and hand raise feature so that I can call on you to answer or comment on a topic.
We will also use the Pointer tool. The tool is on the upper left side of your screen. It is the arrow pointing to the right.
Let’s practice for a moment ensuring we all can use the tools. Remember, phone lines are always open.
FACILITATOR NOTEs
Wait a moment after each tool practice to allow participants to use their tool. Check to see if all participants are doing it. Call out those that are not, to see if they are having difficulties.
ASK
Use the pointer tool to point to your location of where you are currently taking this webinar.
Now, click the raise hand icon. (Okay great. Click it one more time to turn it off)
Some of you have already done this next one while we waited for the session to start. For those that did not, in the Chat Box, provide a brief introduction that includes your business unit and role at Thomson Reuters. (Name a few participants and their information that had responded before class started. As time available say one or two more that just completed the task.)
Transition:
ASK
Does anyone has any questions? (use open phone for dialog)

## Slide 159: Objectives
Communication – Methods and Impacts
Paraverbal Communication
Communicating with Meaning
Listening Skills
Questioning & Establishing Common Ground
Notes: Slide Time: 1:00
ANIMATED SLIDE
SAY
This session will provide you an overview of communication, the impacts, and brings to light things to consider when communicating as well as methods to communicate better.
Highlights include:
<Click> Communication – Methods and Impacts
Identify main methods and components of communication
Environmental factors and common barriers
<Click> Paraverbal Communication
Distinguish the power between good and bad paraverbal communication
Tips for pitch, tone, and speed
<Click> Communicating with Meaning
Identify the components of the STAR Model to speak clearly and with meaning
Practice applying the STAR Model to communicate
<Click> Listening Skills
Seven ways to listen better
Sending good signals to others
<Click> Questioning & Establishing Common Ground
Three types of questioning methods
Common ground checklist for communicating

## Slide 160: Why is this topic important to you?
What are the effects?
Why is knowing various Communication Strategies necessary?
Notes: Slide Time:
ANIMATED SLIDE
SAY
For the better part of every day, we are communicating to and with others. Whether it’s the speech you deliver in the boardroom, the level of attention you give your spouse when they are talking to you, or the look that you give to the cat, it all means something. This session will help to understand the different methods of communication and how to make the most of each of them. Today, you will learn tactics/tools/methodologies to assess the way you’re communicating, how you are listening to others, and apply approaches which will ultimately increase better communication among people receiving the message, and even how you are receiving them.
ASK
Why this topic is important to you? Share your answers to this question in the chat window.
FACILITATOR NOTEs
Start verbal dialog from several of the responses provided in chat.
ASK
<Click> Why is knowing various Communication Strategies necessary? Share your answers to this question in the chat window.
FACILITATOR NOTEs
Start verbal dialog from several of the responses provided in chat.
OR to prompt/start a dialogue.
FACILITATOR NOTES: (AHEAD OF TIME) Capture a real life story that happened in your experience (use 3rd person) and why knowing various communication strategies were import to know and apply to create a positive outcome/desired result.
<Click> So, what are the effects?
The effectiveness of your communication can have many different effects on your life, including items such as:
Level of stress
Relationships with others
Level of satisfaction with your life
Productivity and undesired outcomes
Ability to meet your goals and achieve your dreams
Ability to solve problems
FACILITATOR NOTEs
Thank the participants for responding and sharing.
Promote answers that were provided in the Chat.
Use engagement open-ended questions to gain more detail to an answer or statement.
Use participant names.
Call on a participant(s) to answer.

## Slide 161: The Big Picture
When you come right down to it, how many people speak the same language even when they speak the same language?
Russell Hoban
Notes: Slide Time:
SAY
In this section, we will define what is communication, how we communicate, communication barriers, and factors to consider when communicating. Let’s start by digging into our own communication experience.

## Slide 162: Your Communication Challenge
Think of a recent situation where you faced a communication challenge.
For Example: communicating a new process, where communication or lack thereof affected productivity, or where communication impacted decision making on a project.
Notes: Slide Time:
SAY/EXPLAIN
Let’s use the question I asked at the beginning of the session. Think of a recent situation where you faced a communication challenge.
For Example: communicating a new process, where communication or lack thereof affected productivity, or where communication impacted decision making on a project.
TELL
Take a moment to jot down your answer to this question on the first page of your worksheet question #1. You will need this information throughout the session.
Here is an example:
Ron and Amber were new hires and received their welcome packet informing them what would need to be completed the first few days on the job. Several of the items included technology related tasks like setting up their office email with footer information and registering for the internet email preferences.
Both were very knowledgeable in their field and with email, however were not familiar with the email application Outlook. They both had knowledge of and used Lotus Notes.
ASK
Would anyone like to share a recent situation?
Collectively we can look at and work on helping each other work through the challenge during today’s session!
FACILITATOR NOTEs
Start verbal dialog from several of the responses provided in chat.
POSSIBLY ASK
What kind of obstacles do you think you are/were facing?
What have you tried to overcome the communication challenge?
Share your answers to this question in the chat window.
[Facilitator Note: Ask if it is possible to use a participant’s answer to use an example during this session. OR - Think about using your own example from the last slide to start building on as the example to work through for the session.]
TRANSITION
SAY
Rest assured, during and even after this session, you will have tools and strategies to be able to apply various communication strategies to your situation. I encourage you to utilize the worksheet handout to jot down your thoughts and your answers as we go through the session.
FACILITATOR NOTEs
Thank the participants for responding and sharing.
Promote answers that were provided in the Chat.
Use engagement open-ended questions to gain more detail to an answer or statement.
Use participant names.
Call on a participant(s) to answer.

## Slide 163: What is Communication?
Interchange of thoughts
Speech
Writing
Signs
Notes: Slide Time:
ANIMATED SLIDE
SAY (should be a blank slide with title only)
Many people traditionally think of the spoken word. People who are hearing impaired, however, might think of sign language. People who are visually impaired might think of Braille as well as sounds.
The dictionary defines communication as, “the imparting or interchange of <Click> thoughts, <Click> opinions, or information by speech, <Click> writing, or <Click> signs.”
It is also defined as, “means of sending messages, orders, etc., including telephone/cell phone/internet orders/texts to name a few,” and in biology as an, “activity by one organism that changes or has the potential to change the behavior of other organisms.”
ASK When we say the word, “communication,” what do you think of? Share your answers to this question in the chat window.
FACILITATOR NOTEs
Start verbal dialog/chat dialog.
Now that we have established what is communication is – let’s add in the three main ways to communicate.

## Slide 164: How Do We Communicate?
Verbal
Paraverbal
Spoken
Non-Verbal
Written
Notes: Slide Time:
ANIMATED SLIDE
SAY/EXPLAIN
We communicate in three major ways: spoken, non-verbal, and written.
<Click> Spoken: There are two components to spoken communication.
<Click> Verbal: This is what you are saying. Example: We are using verbal communication right now.
<Click> With Paraverbal: This means how you say it – your tone, speed, pitch, and volume. Example: The tone of your voice and even pitch can convey confusion, authority, excitement and so on. We will dig much further into this topic shortly.
<Click> Non-Verbal: These are the gestures and body language that accompany your words. Some examples: arms folded across your chest, tracing circles in the air, tapping your feet, or having a hunched-over posture.
<Click> Written: Communication can also take place written via e-mail, social media, letters, etc.
TELL:
Look at your answer you put for answer #1. On your worksheet question #2, think about and provide the primary and secondary communication methods that were used for your situation.
ASK
Share your answers to this question in the chat window.
FACILITATOR NOTEs
Start verbal dialog from several of the responses provided in chat.
SAY
Today we will focus most of our attention today on communication strategies regarding Speech.
FACILITATOR NOTEs
Thank the participants for responding and sharing.
Promote answers that were provided in the Chat.
Use engagement open-ended questions to gain more detail to an answer or statement.
Use participant names.
Call on a participant(s) to answer.

## Slide 165: Environmental Factors in Communication
Spoken
Non-Verbal
Written
Method
Mass
Audience
Notes: Slide Time:
SAY/EXPLAIN
Other communication factors that we need to consider.
<Click> Method: The method in which the communicator shares his or her message is important as it has an effect on the message itself. Communication methods include person-to-person, telephone, e-mail, presentation, webcast, and many more!
<Click> Mass: The number of people receiving the message. Example: There may be only be a few people working on a project, or working on a project for a whole region or even larger scale.
<Click> Audience: The person or people receiving the message affect the message, too. Their understanding of the topic and the way in which they receive the message can affect how it is interpreted and understood. Example: Levels of interest in the message such as an email communication may apply to stakeholders verses everyone in the department. Maybe the message is valuable for an inter department where the impact is less for say another department.
Recommended Activity
TELL:
On your worksheet question #3, think about and provide the primary and secondary communication methods that were used for your situation.
ASK
Share your answers to this question in the chat window.
FACILITATOR NOTEs
Start verbal dialog from several of the responses provided in chat.
Delivery Tips
Another option: Involve the group in a discussion of how media has changed the course of major world events. One example is how the cell phones and texting changed the course of how we communicate.
With every good example, there can be negatives (such as the internet information can be one directional or not entirely factual as well as opportunities to discuss ways of working virtually. Play on your professional experience.
Involve the group in a discussion of how media has changed the course of how we receive information. (Facilitator Note: Thomson Reuters is an information company!)
Be sure to keep the discussion focused on aspects of communication, rather than political or religious beliefs.
FACILITATOR NOTEs
Thank the participants for responding and sharing.
Promote answers that were provided in the Chat.
Use engagement open-ended questions to gain more detail to an answer or statement.
Use participant names.
Call on a participant(s) to answer.
Ask if anyone have any questions so far?

## Slide 166: Overview of Common Barriers
Language / Culture
Location / Scheduling
Lack of knowledge
Spoken
Non-Verbal
Written
Method
Mass
Audience
Styles / Interests
Perspectives / Values
Technology
Notes: Slide Time:
SAY/EXPLAIN
On the surface, communication seems pretty simple. I talk, you listen. You send me an e-mail, I read it. Like most things in life, however, communication is far more complicated than it seems. As our methods of communication grow, so do the barriers. Let’s look at some of the most common barriers. Many things can impede communication.
Common barriers typically break down into many categories such as language, culture, and location. However, as organizations transcend a global workforce, more common barriers are scheduling issues, communication difficulties stemming from technologies, lack of mutual knowledge how people conduct business in their regions, and different communication styles, values, interests, and perspectives, just to name a few.
Let’s look at some examples with tips to reduce some of these barriers.

## Slide 167: Reducing Barrier Tips
Language / Culture
Location / Scheduling
Lack of knowledge
Styles / Interests
Perspectives / Values
Technology
Prepare
Learn about the culture
Research the individual on LinkedIn or social media to see what interests them
Ask
About their communication preference (email, phone, chat, webcam, etc)
Articulate the differences and come to an agreement on what would work for you both
Take Action
Make accommodations to foster trust
Leverage experience and perspectives
Suggest alternatives and options
Notes: Slide Time:
SAY/EXPLAIN
With any barrier, always use diplomacy and professionalism. Build trust and the relationship. Think about what you can do and not how the barrier is keeping you from communicating effectively.
It doesn’t matter if it is language, location perspectives or technology – some tips to increase communication and trust are Prepare, Ask, and Action.
Language / Culture: Prepare and learn about the culture, ask peers or others that have worked with that culture what they have found helpful. Use the available resources like Culture Wizard to get hands on references and tools to remove cultural and language barriers.
Styles / Interests: Do some research on social media, look up the individuals on the Hub to see their profile, how long they worked with the organization. You may find similarities and how their differences in experience can play a part in the success of your project.
Location / Scheduling: Ask what time of the day is best to communicate via phone. Use email to communicate at other times and when there is more wiggle room for time for an answer. Obviously, there are times that instant replies or discussion are needed to solve an immediate problems. Engage in the conversation early on so that you establish what will work.
Perspectives / Values: Listen to perspectives and what they value. You will be surprised that if you put yourself in their experience, you may relate or the perspectives will contribute to better decisions and innovation.
Lack of Knowledge: With any application or technology – if you are expecting someone to review a document using for example, track changes or particular fonts in powerpoint, provide a walkthrough of what you want or need, and explain how it will reduce time, or rework. Believe it or not, everyday, we learn something that adds to our tool belt of our career. Absorb the knowledge and share freely. It will actually build trust and strength the relationship.
Technology: Not every one is tech savvy, have the fast internet connection speeds to video chat, or possibly want to “chat” on messenger for long conversations. Ask how you can accommodate the technologies available and provide alternative and other options.
RECOMMENDED ACTIVITY
TELL:
On your worksheet question #4, reflect a few moments on what might have been a barrier. List known barriers that played a role in your situation or even jot down some of these reducing barrier tips.
ASK
Does anyone else have other tips that will help us overcome the barrier(s), possibly something that you used or found your boss or peer used? Share your answers to this question in the chat window.
FACILITATOR NOTEs
Start verbal dialog from several of the responses provided in chat.
FACILITATOR NOTEs
Thank the participants for responding and sharing.
Promote answers that were provided in the Chat.
Use engagement open-ended questions to gain more detail to an answer or statement.
Use participant names.
Call on a participant(s) to answer.
Transition:
Let’s talk about saying your message the way you want others to hear it.

## Slide 168: Communication Challenge
How has technology changed the course of how we communicate and how things are communicated to us?
www.
#
.com
email
@
Notes: Slide Time:
SAY/EXPLAIN
Recommended Activity
ASK - Stories to Share
Share good examples of how has technology changed the course of how we communicate and how things are communicated to us. Think about the ways we communicate.
Delivery Tips
With every good example, there can be negatives (such as the internet information can be one directional or not entirely factual as well as opportunities to discuss ways of working virtually. Play on your professional experience.
Involve the group in a discussion of how media has changed the course of how we receive information. (Facilitator Note: Thomson Reuters is an information company!)
Be sure to keep the discussion focused on aspects of communication.
FACILITATOR NOTEs
Thank the participants for responding and sharing.
Promote answers that were provided in the Chat.
Use engagement open-ended questions to gain more detail to an answer or statement.
Use participant names.
Call on a participant(s) to answer.
Ask if anyone have any questions so far?

## Slide 169: Paraverbal Communication Skills
The relationship is the communication bridge between people.
Alfred Kadushin
Notes: Slide Time:
Transition:
SAY
Paraverbal communication is one of the methods that can positively impact and negatively impact our message. Paraverbal communication can provide a entirely different meeting depending on the emphasis on words, pitch, tone, and speed. It can also impact the way we receive messages, too.

## Slide 170: Paraverbal Communication Skills
“I didn’t say you were wrong.”
“I didn’t say you were wrong.”
“I didn’t say you were wrong.”
Notes: Slide Time:
Animation slide
Transition:
SAY
Let’s try out a basic example of paraverbal communication by word emphasis.
SAY
<Click> “I didn’t say you were wrong.”
<Click> “I didn’t say you were wrong.”
<Click> “I didn’t say you were wrong.”
SAY
Could you hear the difference? Let’s test YOUR listening skills. : )
I am going to repeat these again. Listen to the emphasis on certain words and how it can imply different things.
“I didn’t say you were wrong.” Respond to this question USING THE X and GREEN CHECK MARK – is this implying it wasn’t me?
“I didn’t say you were wrong.” Respond to this question USING THE X and GREEN CHECK MARK – did this imply I communicated it in another way?
“I didn’t say you were wrong.” Respond to this question USING THE X and GREEN CHECK MARK – did I imply I said something else?
Now, let’s look at the three parts of paraverbal communication; which is the message told through the pitch, tone, and speed of our words when we communicate.

## Slide 171: Paraverbal Communication Skills
It’s not what you say, it’s how you say it.
Create a positive, authoritative tone by:
lowering the pitch of your voice a bit.
Smile! This will warm up anyone’s voice.
Sit up straight while talking and while listening.
Monitor your inner monologue. Negative thinking will seep into the tone of your voice
Notes: Slide Time:
Animation slide
Transition:
SAY
Did you ever hear the saying, “It is not what you say, its how you say it”?
The Truth about Tone
Did your mother ever say to you, “I don’t like that tone!” She was referring to the combination of various pitches to create a mood.
Here are some tips on creating a positive, authoritative tone.
Try lowering the pitch of your voice a bit.
Smile! This will warm up anyone’s voice.
Sit up straight while talking and while listening.
Monitor your inner monologue. Negative thinking will seep into the tone of your voice.
ASK - Action
Have you tried the “smile” when you spoke on the phone and even in person? How did it impact the conversation with a boss, peer, or customer?
This is one of the easiest strategies to implement and get the greatest result and the sometimes the hardest to remember. Smile.
Let’s give it a try.
How about we say something simple like: How are you doing today? And say it without smiling. Then again, when smiling. Hear the difference?
FACILITATOR NOTEs
Start verbal dialog from several of the responses provided in chat.

## Slide 172: The Power of Pitch, Tone & Speed
Examples of tones:
Rushed
Conversational
Bored
Worried
Examples of Pitch:
Happy
Indifferent
&
how people react to it
Your Voice
High = anxious / upset
Low = serious / authoritative
Notes: Slide Time:
SAY
Pitch can be most simply defined as the key of your voice. A high pitch is often interpreted as anxious or upset. A low pitch sounds more serious and authoritative. People will pick up on the pitch of your voice and react to it. Tone refers to the combination of various pitches to create a mood.
As well, variation in the pitch of your voice is important to keep the other party interested.
If you naturally speak in a very high-pitched or low-pitched voice, work on varying your pitch to encompass all ranges of your vocal cords.
(One easy way to do this is to relax your throat when speaking.) Make sure to pay attention to your body when doing this – you don’t want to damage your vocal cords.
SAY
We may not be aware but our tones can convey something completely different to someone else. Examples of tones include:
Rushed
Conversational
Bored
Worried
Happy
Indifferent
EXPLAIN A PERSONAL STORY [like this one]
I remember when I was working quietly at my desk when I received a chat message to connect with one of my peers regarding another project. I responded in the chat window “sure.” Seconds later, my phone rang. Since I knew who was calling I answered and not realizing somewhat low, “Hi, Jim. What’s up?” Jim immediately apologized for interrupting me and asked if I was in a bad mood. My tone and the pitch conveyed something completely different than my intentions.
ASK
What tone example did you have which was misinterpreted during one of your conversations? How did you know your tone was misinterpreted? Share your answers to this question in the chat window.
FACILITATOR NOTEs
Start verbal dialog from several of the responses provided in chat.
ASK
In what situation (when) and with whom do you stop and think about how you are going to sound before you speak? Your spouse, your boss, a customer?
Share your answers to this question in the chat window.
FACILITATOR NOTEs
Start verbal dialog from several of the responses provided in chat.
FACILITATOR NOTEs
Thank the participants for responding and sharing.
Promote answers that were provided in the Chat.
Use engagement open-ended questions to gain more detail to an answer or statement.
Use participant names.
Call on a participant(s) to answer.
Ask if anyone have any questions so far?

## Slide 173: The Strength of Pitch, Tone & Speed
Tremendous effect
Can make the listener feel anxious
Communicates importance
Moderate pace will seem natural
Notes: Slide Time:
SAY
The pace at which you speak also has a tremendous effect on your communication ability. From a practical perspective, someone who speaks quickly is harder to understand than someone who speaks at a moderate pace. Conversely, someone who speaks v-e---r----y s---l-----o---w---l---y will probably lose their audience’s interest before they get very far!
As with my prior example with Jim. The speed of which I said, “Hi Jim. What’s up?” could have possibly been interpreted as I was in a rush.
Speed also has an effect on the tone and emotional quality of your message. A hurried pace can make the listener feel anxious and rushed. A slow pace can make the listener feel as though your message is not important. A moderate pace will seem natural, and will help the listener focus on your message.
I remember when I worked in a call center and each representative had to record themselves speaking. The exercise reveled most people spoke too fast and at times, it was hard to understand the words that were said. One easy way to check your pitch, tone, and speed is to record yourself speaking. You can easily do this by leaving yourself a message on your phone. Work on speaking the way you would like to be spoken to. People tend to mirror the person they are speaking to which is a natural fit to communicate. Appropriately altering your pitch, tone, and speed will reduce common communication barriers and misinterpretations, the listener’s level interest, and the comprehensibility of your message.
Recommended Activity
ASK
What communication problems could be caused by speaking too slowly and too quickly.
FACILITATOR NOTEs
Start verbal dialog from several of the responses provided in chat.

## Slide 174: Speaking Like a STAR
Many attempts to communicate are nullified by saying too much.
Robert Greenleaf
Notes: Slide Time:
Transition:
SAY
Let’s look at the actual message you are sending by exploring the STAR acronym in conjunction with the six roots of open questions. (Who? What? When? Where? Why? How?)
You can ensure any message is clear, complete, correct, and concise, with the STAR acronym.

## Slide 175: STAR Model
SITUATION
TASK
ACTION
RESULT
Notes: Slide Time:
Animated Slide
SAY
Over time you will hear about the STAR Model and the various uses this acronym applies to such as, in business, during behavioral interviews, and even during guilt-free self promotion.
In four sentences or so, you should be able to answer each the STAR acronym. Depending how you answer them ie: in-full, partial, or possibly incomplete or not at all will provide you a good inclination if your message is, will be, or was complete, clear, and to the point.
Using the STAR Method can also help you communicate better, as well as when you are listening – to be able to ask for clarification.
The STAR Model will often use a combination of the six roots. (Who? What? When? Where? Why? How?)
In one sentence:
<Click> State what the situation is/was. Try to make this no longer than one sentence. If you are having trouble, ask yourself, “Where?”, “Who?”, and, “When?”. This will provide a base for message so it can be clear and concise.
<Click> State what your task is/was. Use the question, “What?” to frame your sentence, and add the “Why?” if appropriate.
<Click> State what action(s) you will take/took to resolve the problem. Use the question, “How?” to frame this part of the statement. The Action part will provide a solid description and state the precise actions that will resolve any issues.
<Click> Lastly, state the result of your action(s). This will often use a combination of the six roots. Again, a precise short description of the results that come about from your previous steps will finish on a strong definite note.
Ask if anyone have any questions so far?

## Slide 176: STAR Model
SITUATION
TASK
ACTION
RESULT
Notes: Slide Time:
Animated Slide
Facilitator Note: Before the workshop, prepare a STAR example from your own life.
SAY
Example: <Click> (S) During our weekly team meetings, several members dominated the meeting time with lengthy conversations regarding only their projects. <Click> (T) In order to provide time for everyone, I suggested we use a meeting agenda to ensure topics that needed to be addressed had a slotted time. <Click> (A) After providing an agenda template, we all entered our topics a few days prior to the next meeting. <Click> (R) We implemented the agenda at that next meeting and not only did we cover every item on the agenda, all of our team members had a chance to contribute, feel valued, and felt the time was well spent.
--- another example:
S: “On Tuesday, I was in a director’s meeting at the main plant.”
T: “I was asked to present last year’s sales figures to the group.”
A: “I pulled out my laptop, fired up PowerPoint, and presented my slide show.”
R: “Everyone was wowed by my prep work, and by our great figures!”
This format can be compressed for quick conversations, or expanded for lengthy presentations. We encourage you to try framing statements with STAR, and see how much more confident you feel when communicating.
RECOMMENDED ACTIVITY
TELL:
On your worksheet question #5, capture the STAR Model for your particular situation (from #1).
Share your answers to this question in the chat window.
FACILITATOR NOTEs
Start verbal dialog from several of the responses provided in chat.

## Slide 177: Listening Skills
When people talk, listen completely.
Ernest Hemingway
Notes: Slide Time:
Transition:
SAY
So far, we have discussed the components of sending a message: verbal, non-verbal, and paraverbal. Now, let’s turn the tables and look at how to effectively receive messages.

## Slide 178: Seven Ways to Listen Better Today
Listen, don’t talk
Avoid interruptions
10% talking
Related conversation
Do not offer advice
Be aware of your environment
Take notes if required
Notes: Slide Time:
SAY
Hearing is easy! For most of us, our body does the work by interpreting the sounds that we hear into words.
Listening, however, is far more difficult.
Listening is the process of looking at the words and the other factors around the words (such as our non-verbal communication), and then interpreting the entire message.
Here are seven things that you can do to start becoming a better listener right now.
<Click> When you’re listening, listen. Don’t talk on the phone, text message, clean off your desk, or do anything else.
Activity Example: Using the X or Green Check Mark: Answer this question? Did I include phone, text message, and draw in my last sentence about this bullet point?
- Engage dialog.
<Click> Avoid interruptions. If you think of something that needs to be done, make a mental or written note of it and forget about it until the conversation is over.
<Click> Aim to spend at least 90% of your time listening and less than 10% of your time talking.
<Click> When you do talk, make sure it’s related to what the other person is saying. Ask questions to clarify expand, and probe for more information.
<Click> Do not offer advice unless the other person asks you for it. If you are not sure what they want, ask!
<Click> Make sure the physical environment is conducive to listening. Try to reduce noise and distractions.
Examples: “Would you mind stepping into my office where I can hear you better?” is a great line to use.
If possible, be seated comfortably. Be close enough to the person so that you can hear them, but not too close to make them uncomfortable.
<Click> If it is a conversation where you are required to take notes, try not to let the note-taking disturb the flow of the conversation. If you need a moment to catch up, choose an appropriate moment to ask for a break.
FACILITATOR NOTEs
Start verbal dialog if possible.

## Slide 179: Understanding Active Listening
Try to identify where the other person is coming from
Listen attentively
Respond appropriately, either non-verbally, with a question, or by paraphrasing
Notes: Slide Time:
SAY
Although hearing is a passive activity, one must listen actively to listen effectively, and to actually hear what is being said.
There are three basic steps to actively listening.
1. Try to identify where the other person is coming from. This concept is also called the frame of reference. For example, your reaction to a bear will be very different if you’re viewing it in a zoo, or from your tent at a campsite. Your approach to someone talking about a sick relative will differ depending on their relationship with that person.
2. Listen to what is being said closely and attentively.
3. Respond appropriately, either non-verbally (such as a nod to indicate you are listening), with a question (to ask for clarification), or by paraphrasing. Note that paraphrasing does not mean repeating the speaker’s words back to them like a parrot. It does mean repeating what you think the speaker said in your own words. Some examples: “It sounds like that made you angry,” or, “It sounds like that cashier wasn’t very nice to you.” (Using the “It sounds like…” precursor, or something similar, gives the speaker the opportunity to correct you if your interpretation is wrong.”

## Slide 180: Sending Good Signals to Others
Non-verbal
Quasi-verbal
Verbal
Head nods and an interested facial expression will show the speaker that you are listening.
Show you are awake and interested in the conversation with “I see,” “I understand,”
Ask open questions using the six roots discussed earlier (who, what, where, when, why, how), paraphrase, and ask summary questions.
Notes: Slide Time:
When we are listening to others speak, there are three kinds of cues that we can give the other person. Using the right kind of cue at the right time is crucial for keeping good communication going.
Non-Verbal: Head nods and an interested facial expression will show the speaker that you are listening.
Quasi-Verbal: Show you are awake and interested in the conversation with “I see,” “I understand,”
Verbal: Asking open questions using the six roots discussed earlier (who, what, where, when, why, how), paraphrasing, and asking summary questions, are all key tools for active listening.
ASK
What other ways can you as a listener can show you are listening?
Share your answers to this question in the chat window.
FACILITATOR NOTEs
Start verbal dialog from several of the responses provided in chat.
Good questioning skills are another building block of successful communication. We have already encountered several possible scenarios where questions helped us gather information, clarify facts, and communicate with others. Let’s look at questioning techniques that you can use throughout the communication process.
Ask if anyone have any questions so far?

## Slide 181: Questioning Skills & Common Ground
The important thing is not to stop questioning.
Curiosity has its own reason for existing.
Albert Einstein
Notes: Slide Time:
Transition:
SAY
Good questioning skills are another building block of successful communication. We have already encountered several possible scenarios where questions helped us gather information, clarify facts, and communicate with others.

## Slide 182: Types of Questioning
Open-Ended
use one of six words as a root
Open questions are great conversation starters, fact finders, and communication enhancers. Use them whenever possible.
Closed-Ended
limits the answer to one word
Useful if you are searching for a particular piece of information, or winding a conversation down.
Probing
share more information
Clarification / Completeness and Correctness
Determining Relevance / Drilling Down
Notes: Slide Time:
SAY
We discussed open questions a bit when exploring the STAR model earlier. Open questions get their name because the response is open-ended; the answerer has a wide range of options to choose from when answering it.
Open-Ended: Open questions use one of six words as a root: Who? What? Where? When? Why? How?
Open questions are like going fishing with a net – you never know what you’re going to get! Open questions are great conversation starters, fact finders, and communication enhancers. Use them whenever possible.
Closed questions are the opposite of open questions; their very structure limits the answer to yes or no, or a specific piece of information.
Some examples include:
Do you like chocolate?
Were you born in December?
Is it five o’clock yet?
Although closed questions tend to shut down communication, they can be useful if you are searching for a particular piece of information, or winding a conversation down.
If you use a closed question and it shuts down the conversation, simply use an open-ended question to get things started again. Here is an example:
Do you like the Flaming Ducks hockey team?
Yes.
Who is your favorite player?
In addition to the basic open and closed questions, there is also a toolbox of probing questions that we can use. These questions can be open or closed, but each type serves a specific purpose. Let’s look at the types of probing questions categories.
Ask if anyone have any questions so far?

## Slide 183: Types of Probing Questioning
CLARIFICATION
Clarification questions often look like this:
“Please tell me more about…”
“What did you mean by…”
“What does … look like?” (Any of the five senses can be used here)
SUMMARIZING
Example: “So you picked out a dress, had to get it fitted three times, and missed the wedding in the end?”
Remember, paraphrasing means repeating what you think the speaker said in your own words.
COMPLETENESS AND CORRECTNESS
Some examples of these questions include:
“What else happened after that?”
“Did that end the …”
DETERMINING RELEVANCE
Some good ways to frame relevance questions are:
“How is that like…”
“How does that relate to…”
DRILLING DOWN
Useful helpers include:
“Describe…”
“What do you mean by…?”
“Could you please give an example?”
Notes: Slide Time:
ANIMATED SLIDE
SAY
As we go over probing types of questioning, think about which resonate with common situations that you face regularly and which ones you might want to take away from class and use right away. Remember each type serves a specific purpose.
<Click> Clarification
By probing for clarification, you invite the other person to share more information so that you can fully understand their message. Clarification questions often look like this:
“Please tell me more about…”
“What did you mean by…”
“What does … look like?” (Any of the five senses can be used here) <Click>
<Click> Completeness and Correctness
These types of questions can help you ensure you have the full, true story. Having all the facts, in turn, can protect you from assuming and jumping to conclusions – two fatal barriers to communication.
Some examples of these questions include:
“What else happened after that?”
“Did that end the …” <Click>
<Click> Determining Relevance
This category will help you determine how or if a particular point is related to the conversation at hand. It can also help you get the speaker back on track from a tangent.
Some good ways to frame relevance questions are:
“How is that like…”
“How does that relate to…” <Click>
<Click> Drilling Down
Use these types of questions to nail down vague statements. Useful helpers include:
“Describe…”
“What do you mean by…?”
“Could you please give an example?” <Click>
<Click> Summarizing
These questions are framed more like a statement. They pull together all the relevant points. They can be used to confirm to the listener that you heard what was said, and to give them an opportunity to correct any misunderstandings.
Example: “So you picked out a dress, had to get it fitted three times, and missed the wedding in the end?”
Be careful not to avoid repeating the speaker’s words back to them like a parrot. Remember, paraphrasing means repeating what you think the speaker said in your own words.

## Slide 184: Establishing Common Ground
Provides ways to:
Build relationships
Share ideas and perspectives
Open communication channels
Sharing personal experiences
Notes: Slide Time:
SAY
Keep an eye out for common ground while you are communicating.
Common ground provide ways to:
Build relationships
Share Ideas and Perspectives
Open communication channels (What are best communication methods – What time would be best for us to collaborate?
Sharing Personal Experiences
ASK
What are common grounds you have put into practice? What did you identify that needed to be done to establish common ground conversation?
FACILITATOR NOTEs
Start verbal dialog from several of the responses provided in chat.

## Slide 185: Common Ground Check List
Common ground key elements include:
Create guidelines for working together
Forum to ask/answer questions
Question assumptions – develop openness
Listen actively
Use open-ended and probing questioning
Be an active communicator
Use various ways to visually communicate
Be adaptable – persist through setbacks
Notes: Slide Time:
SAY
Keep an eye out for common ground while you are communicating.
Common ground key elements include:
Create guidelines for working together – encourage respect, collaboration, and dialog (use “we”, “us” and “our” when referring to the team.
Ask Questions – Solicit views – create expectations –
Question assumptions – develop openness – Use questions for clarity and dialogue for better understanding
Listen actively – Use open-ended questions and listening skills to get as much out of the conversation as possible.
Be an active communicator - participate in the communication
Use various ways to visually communicate (WebEx, Video Chat)
Be adaptable – persist through setbacks

## Slide 186: Wrapping Up
Communication is the real work of leadership
Nitin Nohria
Notes: Slide Time:
Transition:
SAY
Although this workshop is coming to a close, we hope that your journey to improve your communication skills is just beginning.
Let’s take these last few minutes to address future action items and additional resources.
ASK:
Are there any questions before we conclude with the last two slides?

## Slide 187: Action Items
What communication strategies will YOU
implement right way?
reflect on?
practice?
Notes: Slide Time:
SAY/EXPLAIN
Remember the handout which is available to remind you of some of things we spoke about and worked on together today.
Use the tools we visited today to help you with what and how you want to communicate your message. Align and apply the various communication strategies when you talk with your boss, peer, spouse, and even the cat.
Look at the questions on the screen and think about your responses. Create an action item for yourself and commit to answering them.
I am providing you at this time a survey link in the Chat window. Please take a minute or so to share your learning experience with us.

## Slide 188: Words from the Wise
Recommended Reading List
Burley-Allen, M. (1995). Listening: The Forgotten Skill. Wiley.
Carnegie, D. (1936). How to Win Friends and Influence People. Simon & Schuster.
Davis, M., & McKay, M. (2009). Messages: The Communication Skills Book. New Harbinger.
Fisher, R., Heen, S., & Patton, B. (2000). Difficult Conversations: How to Discuss what Matters Most . Penguin.
Lowndes, L. (2003). How to Talk to Anyone: 92 Little Tricks for Big Success in Relationships. McGraw-Hill.
Ury, W. (2007). The Power of a Positive No: How to Say No and Still Get to Yes. Bantam.
Two monologues do not make a dialogue.
Jeff Daly
Notes: Slide Time:
SAY/EXPLAIN
Thank you for attending!
Have a wonderful rest of the day!

## Slide 189: Worksheet
List known barriers.
1
2
3
4
Think of a recent situation where you faced a communication challenge.
What were the primary and secondary communication methods used?
Capture the environmental factors used in the situation.
SPOKEN
NON-VERBAL
WRITTEN
METHOD
MASS
AUDIENCE

## Slide 190: STAR Model
SITUATION
TASK
ACTION
RESULT